## Procurement Plan
ALBANIA SOCIAL ASSISTANCE MODERNIZATION PROJECT (SAMP)
Component 2: Technical Assistance to Strengthen Implementation Capacity for Social Assistance Programs
PROCUREMENT PLAN (Revised version of October 1, 2013 and updated by April 23, 2014)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 21 | 22
Ref. No. | Description of Assignment | Type | Selection Method | Review by Bank (Prior / Post) | Estimated Date of Initial TOR for the activity | Bank's "No-Objection" to the ToR | Publication of the Request of Expression of Interest | Expected Proposals Submission Date | Submission to the Bank of Shortlist and draft RFP | Bank's "No-objection" to the RFP and shortlist | Technical Evaluation Report | Bank's no-objection on Technical Evaluation Report | Submission of Final Evaluation Report | Draft Negotiated Contract | Bank's "No - Objection" | Expected Contract Signing | Expected Contract Completion Date | Final Contract Amount (Committed) | Final Disbursed Amount | Contractor's name | Contract Amendment (if any)
[5 empty] | Estimated Date of submission of ITQ and Technical Specification | Bank's "No-Objection" to the ITQ | Issuing date of Invitation to Quote | Expected date of quotations received | Evaluation Report | Bank's "No-objection" to the Evaluation Report | [5 empty] | Expected Contract Signing | Expected Contract Completion Date | Final Contract Amount (Committed) | Final Disbursed Amount | Contractor's name | Contract Amendment (if any)
ALBANIA SOCIAL ASSISTANCE MODERNIZATION PROJECT- TA COMPONENT
Sub-Component 2A | Revising Program Parameters for Improved Equity
SAMP/CS/CQ/01-2013 | 1.1 Design and delivery of training module and revision of administrative guidelines for social administrators on the scoring formula for NE for pilot areas. | CS | CQ | Post review | 2013-03-01 | 2013-03-12 | 2013-04-19 | 2013-05-22 | n/a | n/a | 2013-06-03 | 2013-06-04 | n/a | 2013-06-07 | n/a | 2013-07-01 | 2013-10-30 | 21276 | 20836 | Consortium – “Future Center & In Family for Family” Rr: Donika Kastrioti, P.14, Kati 6/2 1000, Tel: 35542275472, mobile: 069 60 90 561, e-mail: info@futurecenter.org Tirana, Albania
SAMP/CS/QCBS/01-2013 | 1.2 Design of new disability eligibility criteria based on the social model and international standards. | CS | QCBS | Prior review | 2013-10-31 | 2013-11-25 | 2013-11-27 | 2013-12-12 | 2014-01-11 | 2014-02-10 | 2014-04-23 | 2014-05-08 | 2014-05-23 | 2014-06-22 | 2014-07-12 | 2014-08-01 | 2014-12-25
SAMP/CS/IC/09-2014 | 1.2 (a) International expertise for Design of new disability eligibility criteria based on the social model and international standards. | CS | IC | Prior review | 2014-02-20 | 2014-02-27 | 2014-03-06 | 2014-03-20 | 2014-03-30 | 2014-04-06 | n/a | n/a | n/a | 2014-04-21 | 2014-04-26 | 2014-04-28 | 2014-12-25
SAMP/CS/IC/10-2014 | 1.2 (b) Local Expertise for Design of new disability eligibility criteria based on the social model and international standards. | CS | IC | Post review | 2014-02-20 | 2014-02-27 | 2014-03-06 | 2014-03-20 | 2014-03-30 | 2014-04-06 | n/a | n/a | n/a | 2014-04-21 | 2014-04-26 | 2014-04-28 | 2014-12-25
SAMP/CS/CQ/03-2014 | 1.3 Design business procedures and institutional arrangements (e.g. composition as well as functioning of disability evaluation commission) as necessitated by the Social Model. | CS | CQ | Prior review | 2014-10-31 | 2014-11-25 | 2014-11-27 | 2014-12-12 | 2015-01-09 | 2015-01-29 | n/a | n/a | n/a | 2015-02-28 | 2015-03-30 | 2015-04-01
SAMP/CS/IC/04-2013 | 1.4 National technical assistance to support Albanian Government in developing the new strategy for Protection and Social Inclusion | CS | SS | Prior review | 2013-05-10 | 2013-05-24 | n/a | 2013-06-03 | n/a | n/a | 2013-07-03 | n/a | n/a | 2013-06-12 | 2013-06-14 | 2013-06-17 | 2013-07-31 | 5750 | 5750 | Mrs. Vilma Kolpeja Rruga “Besim Imami”, No.115, mobile: 355 69 23 485 72 Tiranë, e-mail: vkolpeja@gmail.com
SAMP/CS/IC/05-2013 | 1.5 Local TA: Development of the new strategy for Protection and Social Inclusion. | CS | IC | Post review | 2013-02-12 | 2013-03-07 | n/a | 2013-06-03 | n/a | n/a | 2013-07-03 | n/a | n/a | 2013-06-04 | n/a | 2013-06-17 | 2013-07-31 | 3168 | 3168 | Mr. Zef Shala Rr. “MuhametGjollesha”, P.28, Sh. 1, Apt 5, Tirane Mobile: 0682125484 mobile: 355 67 39 825 51 Phone (home): (04) 2432 30 e-mail:z_shala@yahoo.com
Sub-Component 2B | Strengthening Benefits Administration for Improved Efficiency.
SAMP/CS/CQ/01-2014 | 2.1 Development of Functional Requirements for Disability Assistance MIS. | CS | CQ | Prior review | 2014-04-02 | 2014-04-09 | 2014-04-11 | 2014-04-26 | 2014-05-24 | 2014-06-13 | n/a | n/a | n/a | 2014-07-13 | 2014-08-12 | 2014-08-14
SAMP/CS/CQ/03-2013 | 2.2 Provide Technical Supervision of NE MIS development and implementation. | CS | CQ | Post review | 2013-06-04 | 2013-06-14 | 2013-06-19 | 2013-07-02 | n/a | n/a | 2013-07-24 | n/a | n/a | 2013-09-06 | n/a | 2013-09-09 | 2014-02-28 | 54940 |  | Consortium “COMARCH - Comarch SA Albanian Branch & CA Consulting” Rr. “Medar Shtylla”, Tirana, Albania Mobile: +355 66 215 99 99 , Tel: +48 694 464 84 wojclech.lechwacki@comarch.com, lechwacki@gmail.com
SAMP/CS/CQ/04-2014 | 2.3 Provide Technical Supervision of Disability Assistance MIS development and implementation. | CS | CQ | Post review | 2014-09-01 | 2014-09-26 | 2014-09-28 | 2014-10-13 | n/a | n/a | 2014-10-19 | n/a | n/a | 2014-11-02 | n/a | 2014-11-04
Sub-Component 2C | Promoting Transparency with Communications, Monitoring and Evaluation
SAMP/CS/QCBS/03-2013 | 3.1. Design and Implementation of Process Evaluation for Pilot Phase for NE reforms. | CS | QCBS | Prior review | 2013-08-28 | 2013-09-16 | 2013-10-16 | 2013-10-31 | 2013-11-30 | 2013-12-30 | 2014-03-12 | 2014-03-27 | 2014-04-26 | 2014-05-26 | 2014-06-15 | 2014-07-05
SAMP/CS/IC/06-2013 | 3.2 Refinement of Design of IE (including sampling), and analysis of baseline data (study) | CS | IC | Prior review | 2013-10-15 | 2013-11-04 | 2013-10-29 | 2013-11-12 | 2013-12-10 | 2013-12-30 | n/a | n/a | n/a | 2014-01-29 | 2014-02-28 | 2014-03-02
SAMP/CS/CQ/05-2013 | 3.3 Baseline Data Collection for Pilot Phase | CS | CQ | Prior review | 2013-10-20 | 2013-11-14 | 2013-11-16 | 2013-12-01 | 2013-12-29 | 2014-01-18 | n/a | n/a | n/a | 2014-02-17 | 2014-03-19 | 2014-03-21
SAMP/CS/CQ/06-2013 | 3.4 Implementation of the Communications Campaign for NE reforms (first phase). | CS | CQ | Prior review | 2013-03-27 | 2013-04-03 | 2013-04-19 | 2013-05-01 | 2013-06-13 | 2013-06-17 | n/a | n/a | n/a | 2013-08-26 | 2013-08-28 | 2013-09-02 | 2014-01-13 | 76945 | 13196 | Consortium “COMPORT & DANAE” Rr:”Hajdar Hidri”, 24/1, Mobile: 355 69 20 98 400 Tel: 355 4 258 170 e-mail: albcomport@albcomport.com Tirana, Albania
SAMP/CS/CQ/02-2014 | 3.5 Technical Assistance for Implementation of the Communications Campaign activities for NE reforms (first phase | CS | CQ | Prior review | 2014-04-11 | 2014-04-17 | 2014-04-17 | 2014-04-21 | 2014-04-25 | 2014-04-29 | n/a | n/a | n/a | 2014-04-29 | 2014-04-29 | 2014-04-30 | 2014-09-01
SAMP/CS/IC/07-2013 | 3.6 Implementation of the Communications Campaign for Disability Assistance reform (first phase). | CS | IC | Prior review | 2014-09-15 | 2014-10-05 | 2014-09-29 | 2014-10-13 | 2014-11-10 | 2014-11-30 | n/a | n/a | n/a | 2014-12-30 | 2015-01-29 | 2015-01-31
Sub-Component 2D | Project Implementation Support
4.1 - Project Management Team (PMT) Staffing Costs
SAMP/CS/IC/01-2012 | 4.1.1 - Project Manager | CS | IC | Prior review | 2012-07-17 | 2012-07-24 | n/a | n/a | 2012-09-19 | 2012-09-20 | n/a | n/a | n/a | 2012-12-11 | 2012-12-12 | 2012-12-15 | 2017-11-17 | 73,750.00 EUR 1,032,500 ALL |  | Ms. Suzana Papadhopulli Rruga Pjeter Budi, No.27, Tirana, Albania
SAMP/CS/IC/03-2012 | 4.1.2 - Procurement Officer | CS | IC | Prior review | 2012-07-17 | 2012-07-24 | n/a | n/a | 2012-09-19 | 2012-09-20 | n/a | n/a | n/a | 2012-12-11 | 2012-12-12 | 2012-12-15 | 2015-05-31 | 25,965.00 EUR 515,000 ALL |  | Ms. Elma Dogani Rr: Haxhi H Dalliu", P11.184/9, Apt.7, Tirana, Albania
SAMP/CS/IC/02-2012 | 4.1.3 - Financial management Officer | CS | IC | Prior review | 2012-07-17 | 2012-07-24 | n/a | n/a | 2012-09-19 | 2012-09-20 | n/a | n/a | n/a | 2012-12-11 | 2012-12-12 | 2012-12-15 | 2015-06-15 | 28,500.00 EUR 525,000.00 ALL |  | Ms. Marsela Shameti RR : Qemal Stafa, P 134/1 Ap 6, Tirana, Albania
SAMP/CS/IC/08-2013 | 4.1.4 - M&E Officer (part-time) | CS | IC | Prior review | 2013-07-11 | 2013-07-26 | September 13, 2013 October 4, 2013 December 9, 2013 | 2013-12-20 | 2014-01-31 | 2014-02-24 | n/a | n/a | n/a | 2014-04-10 | 2014-04-20 | 2014-04-22 | 2017-10-30
4.2 - Project Operational Costs
4.2.1- Equipment, Consumable, office supply & telephone charge
SAMP/G/SH/01-2013 | 4.2.1 (a) Purchase of IT Equipment for PMT Team | Goods | Shopping | Prior review | 2013-03-17 | 2013-03-18 | 2013-04-03 | 2013-04-18 | 2013-05-20 | 2013-05-24 | n/a | n/a | n/a | n/a | n/a | 2013-06-12 | 2013-06-26 | 538,000 ALL |  | BNT Electronics sh.p.k. Rr:”Pjeter Bogdani”, 39/1, Tirana, Albania Tel: +355 422 73 666 Fax: +355 422 73 777
SAMP/G/SH/02-2013 | 4.2.1( b) Purchase of Photocopy Machine for PMT Team | Goods | Shopping | Post review | n/a | n/a | 2013-06-12 | 2013-06-26 | 2013-07-02 | n/a | n/a | n/a | n/a | n/a | n/a | 2013-07-04 | 2013-09-19 | 175,900 ALL |  | Fastech sh.p.k. , Rr: “ Brigada VIII, Pll.8/1, e-mail: info@fastach.com.al e-mail: altinluli@fastech.com.al Tirana, Albania
SAMP/G/SH/03-2013 | 4.2.1 (.c) Purchase of a project accounting software application. | Goods | Shopping | Post review | 2013-05-28 | 2013-05-28 | 2013-06-25 | 2013-07-09 | 2013-07-10 | n/a | n/a | n/a | n/a | n/a | n/a | 2013-07-15 | 2013-07-29 | 533,666 ALL |  | IMB - Institute of Modeling in Business Bulevardi “Gjergj Fishta” Pallati 4/8/45 e-mail: xheni.kobuzi@imb.al www.imb.al Tel: 04 22 53 466 /Ext. 251
SAMP/G/SH/04-2014 | 4.2.1 (d) Bus renting for the implementation of the Communications Campaign activities for NE reforms (first phase) | Goods | Shopping | Prior review | 2014-04-25 | 2014-04-26 | 2014-04-26 | 2014-05-08 | 2014-05-09 | 2014-05-10 | n/a | n/a | n/a | n/a | n/a | 2014-05-11 | 2014-05-11
4.2.1 (e) Per diem & Telephone charges & Office Supply
4.2.2 Te part of the Employer Obligation - 16.7 %
4.2.3 Bank Charges
PROJECT COST
Formulas:
Expected Contract Completion Date = [Expected Contract Signing]+14
Expected Contract Completion Date = [Expected Contract Signing]
Note on R25: Elma: Original completion date was septemeber 2, 2014. Due to the contract termination this date is revised as January 14, 2014.
Note on T25: This is the final disbursement amount due to the contract termination.

## General Information
I. General
1. Project information:
Country: Albania
Borrower: Ministry of Labor , Social Affairs and Equal Opportunities (MOLSAEO)
Project Name: Social Assistance Modernization Project (SAMP)
Loan No.: 8141- AL
Project Implementing Agency: Project Implementation Team - Ministry of Labor , Social Affairs and Equal Opportunities (MOLSAEO)
2. Bank’s approval Date of the procurement Plan:
Original: March 21, 2013
Revision 1: February 17, 2014
Revision 2: April 29, 2014
Revision 3:
3. Date of General Procurement Notice: March 21, 2013
4. Period covered by this procurement plan: February 2013 to November 2017
II. Goods and non-consulting services
1. Prior Review Threshold: Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 of the Bank's Procurement Guidelines
| Procurement Method | Method Threshold | Prior Review Threshold
1 | Shopping (Goods) | <€75,000 | First contract
III. Consulting services
1. Prior Review Threshold: Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 of the Bank's Consultant Guidelines
| Procurement Method | Method Threshold | Prior Review Threshold
1 | QCBS | No ceiling | ≥€75,000
2 | FBS | No ceiling | ≥€75,000
3 | LCS | No ceiling | ≥€75,000
4 | CQS | <€100,000 | ≥€75,000
5 | SSS | Per para 3.10 of Consultant Guidelines | All
6 | Individual Consultants | Per paras 5.1 and 5.4 of Consultant Guidelines | Sole Source - All ; Competitive - >€35,000
| Shortlist comprising entirely national consultants (USD) | <€75,000
All TORs are subject to Bank's prior review
III. Procurement Packages with Methods and Time Schedule
See next sheets