China: GEF Technology Needs Assessment Project (TNA)

(P120932)

Procurement Plan

## I. General

1. Bank’s approval Date of the procurement Plan [April 23, 2012, Revision on June 18, 2012; Revision on July 10, 2012; Revision on May 3, 2013]

2. Date of General Procurement Notice. [April 22, 2012]

3. Period covered by this procurement plan: 2012-2015

## II. Goods, Works and Non-Consulting Services

1. Prior Review Threshold: Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement:

Procurement Methods and Prior Review Thresholds for

Goods Procured by PMO

|  | Procurement Method | Prior Review Threshold (US$) | Procurement Method Threshold (US$) |
| --- | --- | --- | --- |
| 1. | ICB | All ICB | For a goods contract, ≥1,000,000, ICB shall be used; <1,000,000, NCB may be used; <100,000, shopping may be used; DC |
| 2. | NCB | ≥500,000 |  |
| 3. | Shopping | NA |  |
| 4. | Direct Contracting (DC) | All DC |  |

2. Prequalification. Bidders for _______shall be prequalified in accordance with the provisions of paragraphs 2.9 and 2.10 of the Guidelines: Not applicable.

3. Proposed Procedures for CDD Components (as per paragraph. 3.17 of the Guidelines: Not applicable.

4. Reference to (if any) Project Operational/Procurement Manual: The PMO has prepared a procurement manual for the project, which has been reviewed by the Bank.

5. Any Other Special Procurement Arrangements: The proposed retroactive financing is subject to the payments being made starting from the end of the mission but within 12 months of the expected signing date of the legal agreement. The amount of retroactive financing shall be less than 10% of the total grant amount. In case of contracts to be procured by using retroactive financing, all such advance contracts (including prior and post review contracts) shall be subject to the Bank’s prior review.

##### 6. Procurement Packages with Methods and Time Schedule

| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Contract (Description) | Estimated Cost (US$ 1,000) | Procurement Method | Prequalification (yes/no) | Domestic Preference (yes/no) | Review by Bank (Prior / Post) | Expected Bid-Opening Date | Contract Duration |
| PMO-002-1 | 6 sets of working stations and 2 file cabinets | 1.2 | shopping | NA | No | Post | n/a | n/a |
| PMO-002-2 | 1 server | 3.2 | shopping | NA | No | Post | n/a | n/a |
| PMO-002-3 | 6 laptops | 6.6 | shopping | NA | No | Post | n/a | n/a |
| PMO-002-4 | 1 printer, 1 fax, 1 photocopier, 5 telephones | 1.7 | shopping | NA | No | Post | n/a | n/a |
| Total |  | 12.7 |  |  |  |  |  |  |

## III. Selection of Consultants

1. Prior Review Threshold and Selection Method: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:

Selection Method and Prior Review Threshold for

Consultants Procured by Implementing Agency

| Expenditure Category | Contract Value (US$) | Procurement Method | Bank Prior Review |
| --- | --- | --- | --- |
| Consultants | >= 300K | QCBS, QBS | Firms: First contract for each selection method and all contracts >=USD 300 K; Firms: All SSS contracts; Individual Consultant: any IC contract estimate ≥ US$50K; SSS for individual consultant: >=USD 20 K; All terms of reference for consultant contracts, regardless of contract value, will be subject to Bank prior review |
|  | < 300K | QCBS, QBS, CQS |  |
|  | N/A | SSS |  |
|  | N/A | IC |  |
| Notes: | QCBS: Quality- and Cost-Based Selection QBS: Quality-Based Selection | CQS: Selection Based on the Consultants’ Qualifications SSS: Single Source Selection IC: Individual Consultant selection procedure NA: Not Applicable |

2. Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than US$500,000 equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.

3.  Any Other Special Selection Arrangements: N/A.

4. Consultancy Assignments with Selection Methods and Time Schedule

| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| --- | --- | --- | --- | --- | --- | --- |
| Seq. No. | Description of Assignment | Estimated Cost (US$ 000) | Selection Method | Review by Bank (Prior / Post) | Expected Proposals Submission Date | Contract Duration |
|  | Reference No. | Contract Description |  |  |  |  |  |
| 1 | TOS-001 | Meth. Devp, Tech Over-sight and Synthesis (7 consultant contracts) | Design and summary report for mitigation | 1 Intl. consultant | 50 | 81 | IC | Any IC contract estimate ≥ US$50K, Subject to Prior Review by Bank | July-12 | 2012-2015 |
|  |  |  |  | 1 Local consultants | 31 |  |  |  |  |  |
| 2 | TOS-002 |  | Design and summary report for adaptation | 1 Intl. consultant | 19 | 34 | IC |  |  |  |
|  |  |  |  | 1 Local consultant | 15 |  |  |  |  |  |
| 3 | TOS-003 |  | Provincial Assessment | 1 Intl. consultant | 21 | 57 | IC |  |  |  |
|  |  |  |  | 1 Local consultant | 24 |  |  |  |  |  |
| 4 | TOS-004 |  | Information System | 1 Local consultant | 33 | 33 | IC |  |  |  |
| 5 | M-001 | Mitigation (12 institutional contracts) | Coal mining and oil & gas exploration | 150 | 1330 | CQS | Post | Jul-13 | 18 months |
| 6 | M-002 |  | Thermal power | 150 |  | CQS | Post | Jul-13 | 18 months |
| 7 | M-003 |  | Renewable energy | 95 |  | CQS | Prior | Jul-13 | 18 months |
| 8 | M-004 |  | Iron and steel | 95 |  | CQS | Post | Jul-13 | 18 months |
| 9 | M-005 |  | Building materials manufacture | 125 |  | CQS | Post | Jul-13 | 18 months |
| 10 | M-006 |  | Chemical industry | 125 |  | CQS | Post | Jul-13 | 18 months |
| 11 | M-007 |  | Nonferrous metallurgy | 120 |  | CQS | Post | Aug-13 | 18 months |
| 12 | M-008 |  | Transportation | 150 |  | CQS | Post | Jul-13 | 18 months |
| 13 | M-009 |  | Residential and commercial buildings | 95 |  | CQS | Post | Jul-13 | 18 months |
| 14 | M-010 |  | Agriculture, forestry, and land use | 65 |  | CQS | Post | Jul-13 | 18 months |
| 15 | M-011 |  | Carbon capture and sequestration (CCS) | 95 |  | CQS | Post | Jul-13 | 18 months |
| 16 | M-012 |  | Waste Management | 65 |  | CQS | Post | Jul-13 | 18 months |
| 17 | A-001 | Adaptation (4 institutional contracts) | Agriculture, forests, ecosystems | 120 | 430 | CQS | Post | Jul-13 | 18 months |
| 18 | A-002 |  | Water resources | 120 |  | CQS | Post | Jul-13 | 18 months |
| 19 | A-003 |  | Urban | 95 |  | CQS | Post | Aug-13 | 18 months |
| 20 | A-004 |  | Disaster Forecast and Weather Monitoring | 95 |  | CQS | Post | Aug-13 | 18 months |
| 21 | PLA-001 | 1 institutional contract | Provincial level assessment | 372 | 372 | QCBS | Prior | Aug-13 | 18 months |
| 22 | PR-001 | Peer-review of technology appraisal (42 consultant contracts) | Technical reviews - sector assessment | 16 Intl. consultants | 96 | 200 | IC | Any IC contract estimate ≥ US$50K, Subject to Prior Review by Bank | May-13 | Spanning 28 months |
| 23 | PR-002 |  |  | 16 Local consultants | 64 |  |  |  | May-13 |  |
| 24 | PR-003 |  | Technical reviews - provincial assessment | 1 Intl. consultant | 10 |  | IC |  | Sep-13 |  |
| 25 | PR-004 |  |  | 1 Local consultant | 6 |  |  |  | Sep-13 |  |
| 26 | PR-005 |  | Technical specialists | 8 Intl. consultants | 24 |  | IC |  | To be confirmed |  |
| 27 | NTT –001 | 1 institutional contract | National TNA and Technology Transfer Capacity Building | 400 | 400 | QCBS | Prior | Aug-13 | two years |
| 28 | PTT- 001 | 4 institutional contracts | Provincial TNA and Technology Transfer Capacity Building | Guangdong | 95 | 380 | CQS | Post | June 2013 | two years |
| 29 | PTT- 002 |  |  | Liaoning | 95 |  | CQS | Post | June 2013 | two years |
| 20 | PTT- 003 |  |  | Jiangxi | 95 |  | CQS | Post | June 2013 | two years |
| 31 | PTT- 004 |  |  | Shaanxi | 95 |  | CQS | Post | June 2013 | two years |
| 32 | STT-001 | 2 institutional contracts | Sectoral TNA and Technology Transfer Capacity Building | Sector 1 | 95 | 190 | CQS | Post | July 2013 | two years |
| 33 | STT-002 |  |  | Sector 2 | 95 |  | CQS | Post | July 2013 | two years |
| 34 | PP-001 | 2 institutional contracts | Management of pilot program | 35 | 55 | CQS | Prior | contract negotiation started Apr 2013 | 26 months |
| 35 | PP-002 |  | Design of future technology transfer program | 20 |  | CQS | Post | Mar. 2014 | One year |
| 36 | PMO-001 | 4 individual consultant contracts | Project Manager | 50 | 155 | IC | Prior (advance) | Signed June 2012 | 36 months |
|  |  |  | Procurement officer | 35 |  | IC | Prior (advance) | Signed June 2012 | 24 months |
|  |  |  | Accountant | 25 |  | IC | Prior (advance) | Signed June 2012 | 24 months |
|  |  |  | Administrative Manager | 45 |  | IC | Prior (advance) | Signed June 2012 | 36 months |
| Total | 3705 |  |

# Text boxes

77847