## track renwewal
Egypt National Railways Restructuring Project (ENRRP)
Procurement Plan
Updated on April 21, 2014
Track renewal works
[5 empty] | REQUEST FOR PROPOSALS |  |  |  |  | EVALUATION |  |  | Contract signature
DESCRIPTION | UPDATE | Estimated Cost US$ | Selection Method | ToR | Request for Expressions of Interest | Short List | Conclude RfP | Wb No-objection to RfP | Invitation to submit proposals | Proposals due date | Combined Technical/Financial Evaluation Report | WB NO OBJECTION | Contract signature | Contract start date | send request to WB for contract extension | WB NO OBJCTION | Amendment to the contract | Duration | Contract end date
| PLANNED |  |  | done | done | done | done | done | 2010-04-01 | 2010-06-01 | 2010-08-01 | 2010-09-25 | 2010-10-10 | 2010-10-25 | 2014-05-02 | 2014-05-22 | 2014-06-06 | 52 month | 2016-02-06
Track renewal works |  | 84 Million $ | ICB
| ACTUAL | [7 empty] | 2010-04-10 | 2010-06-10 | 2010-08-10 | 2010-11-18 | 2011-04-07 | 2011-08-07 | 2014-05-02 | 28/5/2014 | 2014-06-14 | 57 month | 2016-05-06

## ENR NEW LAW
Study for the elaboration of the new railway law
[5 empty] | REQUEST FOR PROPOSALS |  |  |  |  | EVALUATION |  |  |  |  | CONTRACT
DESCRIPTION | UPDATE | Estimated Cost US$ | Selection Method | ToR | Request for Expressions of Interest | Short List | Conclude RfP | Wb No-objection to RfP | Invitation to submit proposals | Proposals due date | Technical Evaluation Report | Wb no-objection to Technical Evaluation Report | Public Opening of Financial proposals | Combined Technical/Financial Evaluation Report | Contract negotiation | WB no-objection to negotiated contract | Notification of award | Contract signature | Contract start date | Duration | Contract end date
| PLANNED |  |  | 2014-12-15 |  |  |  |  | 2014-12-20 |  |  |  | 2015-01-19 | 2015-01-24 | 2015-01-29 | 2015-02-18 | 2015-03-10 | 2015-04-09 | 2015-05-09 | 3 months | 2015-08-07
Study for the elaboration of the new railway law |  | 100.000$ | (Individual Consultant method)
ACTUAL
Formulas:
Invitation to submit proposals = [ToR]+5
Contract end date = [Contract start date]+90

## ETCS1
ETCS-1
[5 empty] | REQUEST FOR PROPOSALS |  |  |  |  | EVALUATION |  |  |  |  | CONTRACT
DESCRIPTION | UPDATE | Estimated Cost US$ | Selection Method | ToR | Request for Expressions of Interest | Short List | Conclude RfP | Wb No-objection to RfP | Invitation to submit proposals | Proposals due date | Technical Evaluation Report | Wb no-objection to Technical Evaluation Report | Public Opening of Financial proposals | Combined Technical/Financial Evaluation Report | Contract negotiation | WB no-objection to negotiated contract | Notification of award | Contract signature | Contract start date | Duration | Contract end date
| PLANNED | [6 empty] | 2014-01-22 | 2014-04-22 | 2014-06-21 | 2014-08-20 | 2014-09-04 | 2014-09-19 | 2014-09-29 | 2014-10-06 | 2014-10-13 | 2014-10-16 | 2014-10-26 | 2014-11-25 | 27months | 2017-02-12
ETCS-1 (Studies & bidding documents preparation) |  | 6 Million $ | QCBS
| ACTUAL |  |  |  | 2013-05-15 | 2013-11-06 | 2013-11-06 | 2014-01-22: 2014-01-20; 2014-04-22: 17 /4/2014; 2014-06-21: 26/6/2014
Formulas:
Contract end date = [Contract start date]+810

## ATP
Automatic train protection study
[5 empty] | REQUEST FOR PROPOSALS |  |  |  |  | EVALUATION |  |  |  |  | CONTRACT
DESCRIPTION | UPDATE | Estimated Cost US$ | Selection Method | ToR | Request for Expressions of Interest | Short List | Conclude RfP | Wb No-objection to RfP | Invitation to submit proposals | Proposals due date | Technical Evaluation Report | Wb no-objection to Technical Evaluation Report | Public Opening of Financial proposals | Combined Technical/Financial Evaluation Report | Contract negotiation | WB no-objection to negotiated contract | Notification of award | Contract signature | Contract start date | Duration | Contract end date
| PLANNED |  |  | 2014-10-15 | 2014-11-14 | 2014-12-29 | 2015-01-05 | 2015-01-20 | 2015-01-27 | 2015-02-26 | 2015-04-07 | 2015-04-22 | 2015-04-29 | 2015-05-29 | 2015-06-05 | 2015-06-12 | 2015-06-19 | 2015-06-26 | 2015-07-11 | 18 month | 2017-01-01
Study for the signaling system and automatic train protection on the remaining ENR secondary lines |  | 1.5 Million $ | QCBS
ACTUAL
Formulas:
Contract end date = [Contract start date]+540

## PSO
PSO study
[5 empty] | REQUEST FOR PROPOSALS |  |  |  |  | EVALUATION |  |  |  |  | CONTRACT
DESCRIPTION | UPDATE | Estimated Cost US$ | Selection Method | ToR | Request for Expressions of Interest | Short List | Conclude RfP | Wb No-objection to RfP | Invitation to submit proposals | Proposals due date | Technical Evaluation Report | Wb no-objection to Technical Evaluation Report | Public Opening of Financial proposals | Combined Technical/Financial Evaluation Report | Contract negotiation | WB no-objection to negotiated contract | Notification of award | Contract signature | Contract start date | Duration | Contract end date
| PLANNED |  |  | 2014-12-15 | 2014-12-20 | 2015-01-29 | 2015-02-13 | 2015-02-28 | 2015-03-10 | 2015-04-19 | 2015-05-19 | 2015-05-29 | 2015-06-13 | 2015-06-28 | 2015-07-08 | 2015-07-18 | 2015-07-28 | 2015-08-07 | 2015-08-27 | 12 month | 2016-08-26
Study for the development of the structure of the public service obligation contract between the state and ENR, including the compensation formula for loss-making short-distance passenger services required by the State |  | 250,000 usd | QCBS
ACTUAL
Formulas:
Contract end date = [Contract start date]+365

## cairo-alex
SIGNALING MODERNIZATION OF CAIRO - ALEXANDRIA CORRIDOR
2 STAGES BIDDING
Design, Supply and Installation
Description | Estimation US$ Million | Procurement method | Prior/Post review | Contract versus Planned Contractula versus actual | PREQUALIFICATION |  |  |  |  | BIDDING DOCUMENTS 1st STAGE |  |  | Coming into Force | EVALUATION 1st STAGE BIDDING | [5 empty] | BIDDING DOCUMENTS 2nd STAGE |  |  |  |  | EVALUATION 2nd STAGE BIDS |  |  |  | CONTRACT DURATION
[5 empty] | Prequalification documents | WB No-Objection | Advertising | Prequalification BER | Prequalification - WB NO to BER | Bidding documents | WB No-Objection | Advertising |  | 1st stage Technical Bids Opening | First Clarification Workshop | Second Clarification Workshop | First Draft Bid Evaluation Report | First Final Bid Evaluation Report | WB No-Objection | Bidding documents | WB No-Objection | Bidding documents | WB No-Objection | Invitation for 2nd stage bidding | Bid Opening | Bid Evaluation Report | WB No-Objection | Notification of award | Contract start date | Contract end date | Total Estimated Duration (years)
Signalling modernization CAIRO - ALEXANDRIA | 197 | ICB | Prior | As per Contract Date |  |  | 2008-08-20 | 2009-06-01 |  | 2009-06-15 |  | 2009-11-15 | 2010-04-29 | 2010-05-14 | 2010-06-18 |  | 2010-07-15 | 2010-11-12 | 2010-12-12 | 2010-11-19 | 2010-12-12 |  |  | 2010-12-19 | 2011-02-10 | 2011-03-09 | 2011-04-15 | 2011-04-22 | 2011-07-14 | 2015-07-23 | 4
|  |  |  | Planned Contractual |  |  | 2008-08-20 | 2009-06-01 |  | 2009-06-15 |  | 2009-11-15 | 2010-04-29 | 2010-05-14 | 2010-09-01 | 2011-07-01 | 2011-07-31 | 2011-11-28 | 2011-12-28 | 2011-12-05 | 2011-12-28 |  |  | 2012-01-04 | 2012-02-26 | 2012-03-24 | 2012-04-30 | 2012-05-07 | 2012-07-29 | 2016-07-28 | 4
|  |  |  | Further to WB Meeting 13 february 2012 |  |  | 2008-08-20 | 2009-06-01 |  | 2009-06-15 |  | 2009-11-15 |  | 2010-05-14 |  |  |  | 2011-08-15 | 2011-10-10 |  |  | 2012-02-20 | 2012-03-30 | 2012-05-01 | 2012-07-01 | 2012-10-01 | 2012-10-24 | 2012-11-01 | 2012-11-15 | 2016-11-15 | 4
|  |  |  | Further to ENR/SYSTRA Meeting 13 June 2012 | [20 empty] | 2012-08-01 | 2012-10-15 | 2012-10-30 | 2012-11-01 | 2012-11-15 | 2016-11-15 | 4
|  |  |  | Further to the WB request on 19 July 2012 | [20 empty] | 2012-09-01 | 2012-11-15 | 2012-11-30 | 2012-12-01 | 2012-12-15 | 2016-12-15 | 4
|  |  |  | Further to the WB request on 28 August 2012 | [20 empty] | 2012-10-01 | 2012-12-20 | 2013-01-04 | 2013-01-05 | 2013-01-19 | 2017-01-19 | 4
|  |  |  | Further to WB Meeting 10 September 2012 | [20 empty] | 2012-10-01 | 2012-12-27 | 2013-01-31 | 2013-02-07 | 2013-02-21 | 2017-02-20 | 4
|  |  |  | Actual |  |  |  |  | 2009-06-29 | 2009-09-10 |  | 2009-11-15 |  |  |  |  | 08/08/2011 rev.1 | 05/12/2011 rev.3 | 16/02/2012 rev.5 | 2011-12-01 | 2012-01-19 | 2012-02-21 | 2012-04-27 | 2012-04-30 | 2012-10-01 | 2012-12-20 | 2013-03-26 | 2013-04-09 | 2013-05-26 | 2017-05-26 | 4
Formulas:
First Clarification Workshop = [Coming into Force]+50
First Draft Bid Evaluation Report = [First Clarification Workshop]+27
First Draft Bid Evaluation Report = [Second Clarification Workshop]+30
First Final Bid Evaluation Report = [First Draft Bid Evaluation Report]+120
WB No-Objection = [First Final Bid Evaluation Report]+30
WB No-Objection = [BIDDING DOCUMENTS 2nd STAGE]+23
BIDDING DOCUMENTS 2nd STAGE = [First Final Bid Evaluation Report]+7

## bani-seuf- assuit
SIGNALING MODERNIZATION OF BENI SUEF - ASYUT CORRIDOR
2 STAGES BIDDING
Design, Supply and Installation 2 Stage Bidding
Description | Estimated Cost in US $ Million | Procurement method | Prior/Post review | Update | PREQUALIFICATION |  |  | PREQUALIFICATION |  | BIDDING DOCUMENTS 1ST STAGE |  |  | EVALUATION 1rst STAGE BIDDING |  |  | BIDDING DOCUMENTS 2nd STAGE |  |  | EVALUATION 2nd STAGE BIDS |  |  |  | CONTRACT DURATION
[5 empty] | Prequalification Documents | WB No-objection | Advertising | Prequalification BER | Prequalification - WB NO to BER | Bidding Documents | WB No-objection | Advertising | 1rst Stage Technical Bids Opening | Bid Evaluation Report | WB No-objection | Bidding Documents | WB No-objection | Invitation for 2nd Stage Bidding | Bid Opening | Bid Evaluation Report | WB No-objection | Notification of award | Contract start date | Contract end date | Total Estimated Duration (years)
Signalling modernization BENI SUEF - ASYUT | 322 | ICB | Prior | Planned | 2011-06-27 |  | 2011-09-01 | 2011-12-01 |  | 2011-10-01 |  | 2012-01-15 | 2012-05-15 | 2012-11-01 | 2012-12-15 |  |  | 2013-01-01 | 2013-03-01 | 2013-05-01 | 2013-06-15 | 2013-07-01 | 2013-08-01 | 2017-07-31 | 4
|  |  |  | Further to WB Meeting 13 february 2012 | 2011-08-27 |  | 2011-11-01 | [8 empty] | 2012-04-15 | 2012-05-28 | 2012-06-15 | 2012-10-15 | 2013-02-15 | 2013-03-30 | 2013-05-15 | 2013-06-01 | 2017-06-01 | 4
|  |  |  | 2012-03-12 | [5 empty] | 2012-04-15 | 2012-06-01 | 2012-06-15 | 2012-10-15 | 2013-01-15 | 2013-02-15 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-07-01 | 2013-09-01 | 2013-10-15 | 2013-11-01 | 2013-12-01 | 2017-12-01 | 4
|  |  |  | 2012-09-03 | [5 empty] | 2012-04-15 | 2012-09-11 | 2012-09-25 | 2013-01-25 | 2013-04-27 | 2013-05-28 | 2013-06-11 | 2013-07-12 | 2013-08-11 | 2013-10-11 | 2013-12-12 | 2014-01-25 | 2014-02-11 | 2014-03-13 | 2018-03-13 | 4
|  |  |  | Further to WB Meeting 10 September 2012 | [6 empty] | 2012-09-21 | 2012-10-04 | 2013-02-03 | 2013-05-06 | 2013-06-06 | 2013-06-20 | 2013-07-22 | 2013-08-21 | 2013-10-21 | 2013-12-22 | 2014-01-30 | 2014-02-16 | 2014-03-18 | 2018-03-17 | 4
|  |  |  | Revised Dec 013 | [5 empty] | 17//04/2012 | 2012-09-24 | 2013-01-12 | 2013-06-17 | 2014-01-22 | 2014-02-15 | 2014-01-22 | 2014-02-15 | 2014-02-21 | 2014-04-24 | 2014-07-26 | 2014-08-28 | 2014-09-16 | 2014-11-01 | 2018-10-31 | 4
|  |  |  | Revised June 2014 | [6 empty] | 2012-09-24 | 2013-01-12 | 2013-06-17 | 2014-03-11 | 2014-04-03 | 2014-01-30 | 2014-04-03 | 2014-04-30 | 2014-07-20 | 2014-10-06 | 2014-10-31 | 2014-11-11 | 2014-12-11 | 2018-12-11 | 4
|  |  |  | Actual | [5 empty] | 2012-05-13 | 2012-09-24 | 2013-01-12 | 2013-05-17 | 23/1/2014 | 2014-04-04 | 30/1/2014 | 2014-04-04 | 2014-04-30 | 20/7/2014

## studies for developing
Study for developing (i) principles for contribution of the State in financing railway infrastructure and (ii) a cost allocation formula to assign the costs of railway infrastructure to the freight and passenger business units (track access charge)
[5 empty] | REQUEST FOR PROPOSALS |  |  |  |  | EVALUATION |  |  |  |  | CONTRACT
DESCRIPTION | UPDATE | Estimated Cost US$ | Selection Method | ToR | Request for Expressions of Interest | Short List | Conclude RfP | Wb No-objection to RfP | Invitation to submit proposals | Proposals due date | Technical Evaluation Report | Wb no-objection to Technical Evaluation Report | Public Opening of Financial proposals | Combined Technical/Financial Evaluation Report | Contract negotiation | WB no-objection to negotiated contract | Notification of award | Contract signature | Contract start date | Duration | Contract end date
| PLANNED |  |  | 2015-01-11 | 2015-01-16 | 2015-03-09 | 2015-03-14 | 31/3/2015 | 2015-04-08 | 2015-05-29 | 2015-06-29 | 2015-07-14 | 2015-07-31 | 2015-08-19 | 2015-08-28 | 2015-09-11 | 2015-09-28 | 2015-11-16 | 2015-11-11 | 18 months | 2017-05-13
Study for developing (i) principles for contribution of the State in financing railway infrastructure and (ii) a cost allocation formula to assign the costs of railway infrastructure to the freight and passenger business units (track access charge) |  | 400.000 $ | QCBS
ACTUAL

## new staff policy
Study for developing a strategy to rationalize staffing through defining new operational procedures and a new staff policy flexible to market needs as well as transparent procedures for merit-based selection of managers
[5 empty] | REQUEST FOR PROPOSALS |  |  |  |  | EVALUATION |  |  |  |  | CONTRACT
DESCRIPTION | UPDATE | Estimated Cost US$ | Selection Method | ToR | Request for Expressions of Interest | Short List | Conclude RfP | Wb No-objection to RfP | Invitation to submit proposals | Proposals due date | Technical Evaluation Report | Wb no-objection to Technical Evaluation Report | Public Opening of Financial proposals | Combined Technical/Financial Evaluation Report | Contract negotiation | WB no-objection to negotiated contract | Notification of award | Contract signature | Contract start date | Duration | Contract end date
| PLANNED |  |  | 2014-12-07 | 2014-12-27 | 2015-01-06 | 2015-01-11 | 2015-01-28 | 2015-02-01 | 2015-03-14 | 2015-04-13 | 2015-04-30 | 2015-05-09 | 2015-05-29 | 2015-06-08 | 2015-07-30 | 2015-08-09 | 2015-08-19 | 2015-09-06 | 12 Months | 2016-09-05
Study for developing a strategy to rationalize staffing through defining new operational procedures and a new staff policy flexible to market needs as well as transparent procedures for merit-based selection of managers |  | 250,000 $ | QCBS
ACTUAL