## General Aspects
Procurement Plan |  | Credit No xx-XK | Project ID P147402
Project Name: Kosovo Health Project
I. General
Agreed date of procurement Plan
Original: | 2014-03-03
Date of General Procurement Notice: Published on UNDB online on xxxx
II. Goods and Works
1. Prior Review Threshold: Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement:
| Procurement Method | Threshold (Euro) | Prior Review
1 | ICB (Goods) | ≥ 150,000 | All
2 | NCB (Goods) Packages | ≤ 150,000 | First 2
3 | ICB (Works) Packages | ≥ 715,000 | All
4 | NCB (Works) Packages | ≤ 715,000 | First 2
5 | Shopping (Goods and Works) | ≤ 75,000 in accordance with 3.5 of the Procurement Guidelines | First Contract
6 | Direct Contracting* | In accordance with paragraph 3.7 of the Procurement Guidelines | When certain goods are available only from a particular supplier or in cases where compatibility with existing equipment so requirew, these goods may be procured following the Direct contracting method with prior approval from the Bank.
7 | Commercial Practice | In accordance with paragraph 3.13 of the Guidelines up to Euro 1,500,000 million for goods and works
* all Contracts subject to justification
2. Manuals: the client will prepare a draft Project Operations Manual which should include a section of Procurement Arrangements to be followed under the project.
Detailed original procurement contracts for goods, consulting services are enclosed in the next excel spread sheet
III. Selection of Consultants
1. Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:
| Selection Method | Threshold (Euro) | Prior Review
1. | Competitive Methods (Firms) QCBS | ≥ 75,000
2 | FBS | In accordance with paragraph 3.5 of the Consultants Guidelines
3 | Competitive Methods (Firms) CQ | In accordance with paragraph 3.7 of the Consultant's Guidelines | First Contract
4 | LCS | In accordance with paragraph 3.6 of the Consultants Guidelines
5. | Individual Consultants (IC) | ≤ 40,000 in accordance with Section V of the Consultants Guidelines
6. | Single Source (Firms and Individuals)* | In accordance with paragraph 3.8.3.11 of the Consultants Guidelines | All
7. | ToRs for Consulting Contracts
* all Contracts subject to justification
2. Short list comprising entirely of national consultant: Short list of consultants for services, estimated to cost less thant Euro 75,000 equivalent per contract,
may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultants Guidelines.

## PP
| Project Name: Kosovo Health Project |  |  | PP at Negotions
| Project ID Number: P147402 |  |  | Credit No: IDA- | [10 empty] | Closing date: 10/30/2019
Original: | 2014-03-06 | [5 empty] | `
Update date:
Sub Total (Works)
Package Nr. | Description of Contract Package | Procurement Type | Procurement method | Bank's review (Prior/Post) | Estimated cost of the Project, Euro | Estimated cost of the Project, USD | Actual Contract Amount | Disbursed Amount | Physical Progress (%) | Payment to Vendor (%) | Retroactive Financing Euro | Procurement Status | Bid Document/ITQ/RFP/TOR and SPN/EOI sent to the Bank | Bank's NO objection to Bid Document/RFP | Issue date of the Bid Document/ITQ/RFP | Bid opening/Proposal Submission | Bid evaluation report sent to the Bank | Bank's NO to the Bid Evaluation Report | Draft Contract sent to the Bank | Bank's no objection to Contract award | Contract signing date | Contract completion date | Name of the Bidder/Supplier/Consultant
Component 1: Building institutional capacity to improve financial proctection and quality care
Sub-component 1.1: Improving financial protection
A.1.1 | Outpatient Drug Benefit
A.1.1.1 | Designing Outpatient Drug Benefit Scheme | CS | QCBS | Prior | #VALUE! | 125000 | [5 empty] | Planned | 2014-09-01 | 2014-09-05 | 2014-09-08 | 2014-10-06 | 2014-10-20 | 2014-10-24 | 2014-11-10 | 2014-11-12 | 2014-11-14 | 2015-03-13 |  | S
Revised
Actual
A.1.1.2 | Outsourcing Outpatient Drug Benefit Management | CS | QCBS | Prior | #VALUE! | 445000 | [5 empty] | Planned | 2015-01-12 | 2015-01-16 | 2015-01-19 | 2015-02-16 | 2015-03-09 | 2015-03-13 | 2015-04-13 | 2015-04-17 | 2015-04-27 | 2017-05-05
Revised
Actual
A.1.2 | HIF Information System
A.1.2.1 | Development of technical specifications for system platform for HIF information system | CS | IC | Post | 30000 | #VALUE! |  |  |  |  | 3000 | Planned | 2014-06-02 | 2014-06-06 | _ | _ | 2014-07-01 | 2014-07-09 | 2014-07-16 | 2014-07-18 | 2014-07-21 | 2015-02-15
Revised
Actual
A.1.2.2 | System Platform for HIF information system (hardware, system software) | G/SIIS | ICB | Prior | #VALUE! | 800000 | [5 empty] | Planned | 2014-12-01 | 2015-02-02 | 2015-02-09 | 2015-03-23 | 2015-04-13 | 2015-04-27 | 2015-05-11 | 2015-05-15 | 2015-05-18 | 2015-11-30
Revised
Actual
A.1.2.3 | IT equipment and communication infrastructure for HIF/HFA staff | G | SH | Post | #VALUE! | 90000 | [5 empty] | Planned | 2015-08-31 | 2015-09-04 | 2015-09-07 | 2015-09-21 | 2015-09-25 | 2015-09-30 | 2015-10-02 | _ | 2015-10-05 | 2015-11-15
Revised
Actual
A.1.2.4 | Adjustment of HIF information system (Software) | CS | SSS | Prior | #VALUE! | 50000 | [5 empty] | Planned | 2015-10-12 | 2015-10-16 | _ | _ | _ | _ | 2015-11-02 | 2015-11-06 | 2015-11-13 | 2015-12-15
Revised
Actual
A.1.2.5 | Adjustment of information systems in PHC and hospitals (Software) | CS | SSS | Prior | [7 empty] | Planned | 2015-10-12 | 2015-10-16 | _ | _ | _ | _ | 2015-11-02 | 2015-11-06 | 2015-11-13 | 2015-12-15
[5 empty] | #VALUE! | 75000 | [5 empty] | Revised
Actual
A.1.2.6 | Clean-up of the registry of insured persons (Multiple individual contracts) | CS | IC | Post | #VALUE! | 60000 | [5 empty] | Planned | 2014-12-01 | 2014-12-05 | _ | _ | 2015-01-05 | _ | 2015-01-12 | _ | 2015-01-15 | 2015-07-31
Revised
Actual
A.1.3 | Support to Implement Mandatory health insurances
A.1.3.1 | Development of Documents for HIF and Preparatory Studies | CS | IC | Prior | #VALUE! | 105000 | [5 empty] | Planned | 2014-09-15 | 2014-09-19 | _ | _ | 2014-10-13 | 2014-10-17 | 2014-10-27 | 2014-10-31 | 2014-11-14 | 2015-04-30
Revised
Actual
A.1.3.2 | HIF Management Coaching: FM, IT (Multiple Contracts) | CS | IC | Post | #VALUE! | 175000 | [5 empty] | Planned | 2015-01-19 | 2015-01-23 | _ | _ | 2015-02-16 | 2015-02-20 | 2015-02-27 | 2015-03-03 | 2015-03-06 | 2015-12-31
Revised
Actual
A.1.4 | DRG Implementation
A.1.4.1 | DRG Software for HIF/HFA | G | SH | Post | #VALUE! | 70000 | [5 empty] | Planned | 2015-01-26 | _ | 2015-01-28 | 2015-02-11 | 2015-02-18 | - | 2015-02-25 | _ | 2015-03-02 | 2015-04-30
Revised
Actual
A.1.5 | Communication Campaign
A.1.5.1 | Development of the Communications strategy | CS | QCBS | Prior | #VALUE! | 550000 | [5 empty] | Planned | 2014-09-01 | 2014-09-05 | 2014-09-08 | 2014-10-10 | 2014-10-27 | 2014-10-31 | 2014-11-24 | 2014-11-28 | 2014-12-15 | 2019-09-20
Revised
Actual
A.1.5.2 | HIF website | CS | CQS | Prior | #VALUE! | 35000 |  |  |  |  | #VALUE! | Planned | 2014-08-18 | 2014-08-22 | 2014-08-25 | 2014-09-08 | _ | _ | 2014-09-29 | 2014-10-03 | 2014-10-13 | 2014-12-31
Revised
Actual
Sub-component 1.2: Improving Quality of Care
A.2.1 | Medical Equipment for MCH for hospitals Separated into 7 lots | G | ICB | Prior | 1845105 | #VALUE! | [5 empty] | Planned | 2014-09-01 | 2014-09-15 | 2014-09-19 | 2014-11-03 | 2014-11-24 | 2014-12-08 | 2014-12-15 | 2014-12-19 | 2014-12-22 | 2015-12-31
Revised
Actual
A.2.1.1 | LOT 1: Endoscopy and OR equipment | G |  |  | 231600 | #VALUE!
A.2.1.2 | LOT 2: Laboratory equipment | G |  |  | 69400 | #VALUE!
A.2.1.3 | LOT 3: Monitoring equipment | G |  |  | 336900 | #VALUE!
A.2.1.4 | LOT 4: Neonatology equipment | G |  |  | 422900 | #VALUE!
A.2.1.5 | LOT 5: Medical instruments and sterilization | G |  |  | 205550 | #VALUE!
A.2.1.6 | LOT 6: Diagnostic imaging equipment | G |  |  | 464000 | #VALUE!
A.2.1.7 | LOT 7: Hospital equipment and furniture | G |  |  | 114755 | #VALUE!
A.2.2 | Medical Equipment Specialist to prepare technical specifications/bidding documents | CS | IC | Post | #VALUE! | 20000 |  |  |  |  | #VALUE! | Planned | 2014-06-02 | _ | _ | 2014-06-16 | 2014-06-23 | - | 2014-06-27 | - | 2014-06-30 | 2015-01-31
Revised
Actual
A.2.3 | Development of Capitation Performance Payments Manual | CS | QCBS | Prior | #VALUE! | 210000 |  |  |  |  | #VALUE! | Planned | 2014-05-01 | 2014-05-08 | 2014-05-12 | 2014-06-09 | 2014-06-16 | 2014-06-20 | 2014-07-07 | 2014-07-09 | 2014-07-11 | 2016-10-31
Revised
Actual
A.2.4 | Consultancy to develop ToRs for IPH information system | CS | IC | Post | #VALUE! | 50000 | [5 empty] | Planned | 2015-02-02 | _ | _ | 2015-02-23 | 2015-03-02 | - | 2015-03-16 | - | 2015-03-20 | 2016-03-21
Revised
Actual
A.2.5 | IPH information system | G/SIIS | ICB | Prior | #VALUE! | 400000 | [5 empty] | Planned | 2015-08-10 | 2015-08-14 | 2015-08-17 | 2015-09-28 | 2015-10-16 | 2015-10-23 | 2015-10-28 | 2015-10-03 | 2015-11-02 | 2016-07-04
Revised
Actual
A.2.6 | Additional Computer equipment for IPH | G | SH | Post | #VALUE! | 50000 | [5 empty] | Planned | 2015-09-28 | 2015-10-02 | 2015-10-05 | 2015-10-19 | 2015-10-26 | 2015-10-30 | 2015-11-09 | 2015-11-11 | 2015-11-16 | 2016-07-04
Revised
Actual
A.2.7 | e-prescription System in pilot regions: Consultancy to develop ToRs | CS | IC | Prior | #VALUE! | 70000 | [5 empty] | Planned | 2014-05-04 | _ | _ | 2015-05-18 | 2015-05-25 | - | 2015-06-01 | - | 2015-06-08 | 2015-12-31
Revised
Actual
A.2.8 | Development of ehealth Development Framework and Capacity Building (1 International for the whole process) | CS | IC | Post | #VALUE! | 22000 |  |  |  |  | #VALUE! | Planned | 2014-06-02 | _ | _ | 2014-06-20 | 2014-06-27 | - | 2014-07-04 | - | 2014-07-20 | 2015-04-30
Revised
Actual
A.2.9 | Development of ehealth Development Framework and Capacity Building (1 International for end review) | CS | IC | Post | #VALUE! | 8000 | [5 empty] | Planned | 2015-01-19 | _ | _ | 2015-02-02 | 2015-02-09 | - | 2015-02-23 | - | 2015-03-01 | 2015-04-30
Revised
Actual
A.2.10 | Development of ehealth Development Framework and Capacity Building (1 Local for assessment) | CS | IC | Post | #VALUE! | 5000 |  |  |  |  | #VALUE! | Planned | 2014-06-02 | _ | _ | 2014-06-20 | 2014-06-27 | - | 2014-07-04 | - | 2014-07-20 | 2015-04-30
Revised
Actual
A.2.11 | Development of ehealth Development Framework and Capacity Building (1 Local for support to strategic planning) | CS | IC | Post | #VALUE! | 5000 |  |  |  |  | #VALUE! | Planned | 2014-06-02 | _ | _ | 2014-06-20 | 2014-06-27 | - | 2014-07-04 | - | 2014-07-20 | 2015-04-30
Revised
Actual
A.2.12 | Development of a maintenance system for existing equipment at hospitals | CS | CQS | Prior | 40000 | #VALUE! |  |  |  |  | 4000 | Planned | 2014-07-07 | 2014-07-11 | 2014-07-14 | 2014-07-28 | 2014-08-04 | 2014-08-08 | 2014-08-15 | 2014-08-22 | 2014-09-01 | 2014-12-31
Revised
Actual
A.2.13 | Technical Audit for Capitation PerformancePayments | CS | QCBS | Prior | 175000 | #VALUE! | [5 empty] | Planned | 2015-01-12 | 2015-01-16 | 2015-01-19 | 2015-02-16 | 2015-03-02 | 2015-03-06 | 2015-03-27 | 2015-04-03 | 2015-04-13 | 2019-09-30
Revised
Actual
Monitoring and Evaluation
ME.1 | Strengthening of health sector monitoring capacities at IPH | CS | CQS | Post | 60000 | #VALUE! | [5 empty] | Planned | 2014-10-01 | 2014-10-08 | 2014-10-22 | 2014-11-05 | - | - | 2014-11-19 | - | 2014-11-24 | 2016-12-15
Revised
Actual
Component 3: Project Management
PM.1 | PCU Project Coordinator | CS | IC | Prior | 120600 | #VALUE! |  |  |  |  | 12600 | Planned | 2014-02-28 | 2014-03-01 | 2014-03-03 | 2014-03-17 | 2014-03-21 | 2014-03-24 | 2014-03-28 | 2014-03-31 | 2014-04-01 | 2019-10-31
Revised
Actual
PM.2 | IT Coordinator (national) | CS | IC | Prior | 106400 | #VALUE! |  |  |  |  | 10400 | Planned | 2014-03-10 | 2014-03-14 | 2014-03-17 | 2014-03-31 | 2014-04-04 | 2014-04-07 | 2014-04-11 | 2014-04-14 | 2014-04-15
Revised
Actual
PM.3 | Communication Specialist | CS | IC | Prior | 91000 | #VALUE! |  |  |  |  | 7000 | Planned | 2014-04-14 | 2014-04-18 | 2014-04-21 | 2014-05-05 | 2014-05-12 | 2014-05-16 | 2014-05-26 | 2014-05-30 | 2014-06-02
Revised
Actual
PM.4 | Bilingual Administrator Assistant/Secretary | CS | IC | Prior | 52000 | #VALUE! |  |  |  |  | 4000 | Planned | 2014-04-14 | 2014-04-18 | 2014-04-21 | 2014-05-05 | 2014-05-12 | 2014-05-16 | 2014-05-26 | 2014-05-30 | 2014-06-02
Revised
Actual
PM.5 | Financial Management Specialist | CS | IC | Prior | 93100 | #VALUE! |  |  |  |  | 9100 | Planned | 2014-03-10 | 2014-03-14 | 2014-03-17 | 2014-03-31 | 2014-04-04 | 2014-04-07 | 2014-04-11 | 2014-04-14 | 2014-04-15
Revised
Actual
PM.6 | Procurement Specialist | CS | IC | Prior | 93100 | #VALUE! |  |  |  |  | 9100 | Planned | 2014-03-10 | 2014-03-14 | 2014-03-17 | 2014-03-31 | 2014-04-04 | 2014-04-07 | 2014-04-11 | 2014-04-14 | 2014-04-15
Revised
Actual
PM.7 | Monitoring and Evaluation Specialist | CS | IC | Prior | 91000 | #VALUE! |  |  |  |  | 7000 | Planned | 2014-04-14 | 2014-04-18 | 2014-04-21 | 2014-05-05 | 2014-05-12 | 2014-05-16 | 2014-05-26 | 2014-05-30 | 2014-06-02
Revised
Actual
PM.8 | POM Preparation | CS | IC | Prior | 11000 | #VALUE! |  |  |  |  | 11000 | Planned | 2013-12-20 | 2013-12-23 | 2013-12-24 | 2014-01-13 | 2014-01-23 | 2014-01-24 | 2014-02-03 | 2014-02-03 | 2014-02-07 | 2014-08-15 | Tamar Gotsade
[12 empty] | Revised | - | - | - | - | - | - | - | - | -
[12 empty] | Actual | 2013-12-20 | 2013-12-23 | 2013-12-24 | 2014-01-13 | 2014-01-23 | 2014-01-24 | 2014-02-03 | 2014-02-03 | 2014-02-07
PM.9 | Office equipment and furniture for PCU | G | SH | Prior | 37000 | #VALUE! |  |  |  |  | 37000 | Planned | 2014-07-28 | 2014-07-31 | 2014-08-01 | 2014-08-18 | 2014-08-22 | 2014-08-25 | - | - | 2014-09-01 | 2014-09-15
Revised
Actual

## OC
Sub Total (Works)
Package Nr. | Description of Contract Package | Procurement Type | Estimated cost of the Project, Euro | Estimated cost of the Project, USD | Status | Comments/Explanations | Additional information
Component 1: Building institutional capacity to improve financial proctection and quality care
Sub-component 1.1: Improving financial protection
OC.1 | Training from international experts to design and implement policies, systems design and operational documents for HIF (Staff Secondments) | OC | 72992.7007 | 100000 | Planned | Secondments of staff from another HIF to Kosovo
Revised
Actual
OC.2 | DRG license | OC | 145985.4015 | 200000 | Planned
Revised
Actual
OC.3 | Translation of DRGs | OC | 36496.3504 | 50000 | Planned
Revised
Actual
Sub-component 1.2: Improving Quality of Care
OC.4 | In country travel for central level staff staff MoH and HIF | OC | 10000 | 13700 | Planned
Revised
Actual
Monitoring and Evaluation
OC.5 | Production of Studies and Surveys | OC | 36496.3504 | 50000 | Planned | Studies for M&E undertaken by IPH
Revised
Actual
Component 2: Strengthening primary care
OC.6 | Capitation based performance payments (No procurement required, since capitation payments) |  | 9160017.7355 | 12549224.2977 | Planned
Revised
Actual
Component 3: Project Management
OC.7 | PCU Office Running Cost | OC | 97810.219 | 134000 | Planned | Includes operating costs for PCU. Based on MoH communication, premises will be provided by the MoH, so rent is not included here. Vehicle to be provided by MoH.
Revised
Actual
OC.8 | PCU Staff Travel | OC | 10000 | 13700 | Planned | PCU travel to support the Project
Revised
Actual
OC.9 | Loan Audits for first 18 months | OC | 175000 | 239750 | Planned | 5 year contract with auditor. No re-advertisement needed.
Revised
Actual

## Training
Sub Total (Works)
Package Nr. | Description of Contract Package | Procurement Type | Estimated cost of the Project, Euro | Estimated cost of the Project, USD | Status | Comments/Explanations | Additional information
Component 1: Building institutional capacity to improve financial proctection and quality care
Sub-component 1.1: Improving financial protection
Tr.1 | 1. Trainings for HIF/HFA staff on mandatory health insurance. 2. Media training for Ministry and HIF staff 3. Within Internal Communications Campaign of MoH: Trainings for facility staff | TR | 364963.5036 | 500000 | Planned | Includes training for HIF staff on health insurance implementation and media training for key functionaries in Ministry and HIF to improve media interaction skills. For internal communications: 'Townhalls' or workshops on health insurance for facility staff
Revised
Actual
Tr.2 | Training and study tours for DRG Implementation | TR | 364963.5036 | 500000 | Planned | To confirm number of participants for training and study tours for HFA/HIF staff, hospital staff
Revised
Actual
Sub-component 1.2: Improving Quality of Care
Tr.3 | Development of eHealth Development Capacity Building, Study tours, training, and workshops | TR | 43795.6204 | 60000 | Planned
Revised
Actual
Tr.4 | Training for MoH, Municipality and PHC facility staff on the capitation payments manual and implementation | TR | 72992.7007 | 100000 | Planned | Training of Municipality, HIF and facility staff to implement capitation payments, scheme, reporting, quality standard and quality improvement mechanism. The number to be trained should also depend on plans to scale up.
Revised
Actual
Monitoring and Evaluation
-
Component 2: Strengthening primary care
-
Component 3: Project Management
Tr.5 | Training /seminars/workshops (launch) | TR | 56000 | 76720 | Planned | Project launch workshop; Trainings on POM for PCU staff and key MoH staff; FM training for PCU FM consultant; Procurement training for Procurement consultant, and IT procurement training for Procurement and IT consultant
Revised
Actual

## Disbursements 2014-2016
Tentative Disbursements in EUR
FY | 2014 | 2015 | 2016
In PP | 542296.3504 | 2244917.0693 | 3096760.1934
Capitation Payments | - | 274985.2 | 2406185.0355
Total | 542296.3504 | 2519902.2693 | 5502945.229
Retroactive Financing | 258507 | - | -