## General Aspects
Procurement Plan |  | Credit No. 5219-MD | Project ID: P143202
Moldova Emergency Agriculture Support Project (MEASP)
I. General
Agreed date of procurement Plan
Original: | 2013-03-31
Date of General Procurement Notice: Published on UNDB online on _______, 2013
II. Goods and Works
1. Prior Review Threshold: Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement:
| Procurement Method | Threshold | Prior Review
1 | NCB (Works) | ≦ $1,000,000 | First 2
2 | ICB (Goods and Works) | > $200,000 | All
3 | Shopping (Goods and Works) | ≦ $100,000 (for Goods) / ≦ $200,000 (for Works) | First one
4 | Direct Contracting* | N/A | All
* all Contracts subject to justification
2. Prequalification. Bidders shall be pre-qualified in accordance with the provisions of paragraphs 2.9 and 2.10 of the Guidelines: Procurement of Goods, Works, and Non-Consulting Services under IBRD Loans and IDA Credits & Grants by World Bank Borrowers, January 2011
3. Any Other Special Procurement Arrangements: None
Detailed original procurement contracts for goods, consulting services are enclosed in the next excel spread sheet
III. Selection of Consultants
1. Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:
| Selection Method | Threshold | Prior Review
1 | Competitive Methods (Firms) QCBS | > $300,000 | All
2 | Competitive Methods (Firms) QBS | > $100,000 | All
3 | Competitive Methods (Firms) LCS | > $100,000 | All
4 | Competitive Methods (Firms) CQ | > $100,000 / ≦ $300,000 | All
5 | Individual Consultants (IC) | > $50,000 | All
6 | Single Source (Firms and Individuals)* | N/A | All
7 | ToRs for Consulting Contracts | N/A | All
* all Contracts subject to justification

## PP ver. 1.1
Moldova Emergency Agriculture Support Project (MEASP)
|  |  | Project ID: P143202 |  |  |  |  | Credit No. 5219-MD |  |  |  |  | Closing date: | 2014-09-01
|  | Original: | 2013-03-31
|  | Update date: | 2013-11-15
Procurement category | # | Contract # | Description of goods | Procurement Status | Component Nr. | Procurement Type | Procurement method | Bank's review (Prior/Post) | Source of finance MDTF | Source of finance IDA | Draft Bidding Docs and SPN | Bank's NO objection to bidding docs/Specs | Invitation for bids | Bid opening | Bid evaluation report | Bank's no objection to Contract award | Contract Number | Contract signing date | Contract completion date | Winning bidder name&Country | Remarks | Amount reduced from previous estimates | Disbursed as of 19 Sept. 08 ( to verify) | IV Quarter 2008 | First Half 2009 | Second Half 2009 | Total
(Goods) | 1 | MEASP/G/SH-1 (Lot 1) | IT equipment & network; office furniture for central offrice AIPA (Lot 1 furniture) | Planned | B | G | SH | Post |  |  | 2013-10-24 | N/A | 2013-10-25 | 2013-11-04 | 2013-11-04 | N/A | MEASP/G/SH-1.1 | 2013-11-05 | 2014-01-04 | „Mob-Elita” S.R.L, Moldova |  | #REF! | #REF! |  |  |  | #REF!
|  |  |  | Revised | [16 empty] | BB to follow up | #REF! |  | 150000 | 350000 | #REF! | #REF!
|  |  |  | Actual | [6 empty] | 2013-10-24 |  | 2013-10-25 | 2013-11-04 | 2013-11-04 | N/A |  | 2013-11-05
| 2 | MEASP/G/SH-1 (Lot 3) | IT equipment & network; office furniture for central offrice AIPA (Lot 3 network) | Planned | B | G | SH | Post |  |  | 2013-10-24 | N/A | 2013-10-25 | 2013-11-04 | 2013-11-04 | N/A | MEASP/G/SH-1.2 | 2013-11-05 | 2013-12-05 | „Marient & Co” S.R.L., Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-10-24 |  | 2013-10-25 | 2013-11-04 | 2013-11-04 | N/A |  | 2013-11-05
| 3 | MEASP/G/SH-1 (Lot 2) (only one quotation received, re-advertised) | IT equipment & network; office furniture for central offrice AIPA (Lot 2 IT equipment) | Planned | B | G | SH | Post |  |  | 2013-10-24 | N/A | 2013-10-25 | 2013-11-04 | 2013-11-04 | N/A |  | 2013-11-05 | 2014-01-04
|  |  |  | Revised | [6 empty] | 2013-11-18 |  | 2013-11-19 | 2013-11-30 | 2013-12-05 | N/A |  | 2013-12-06 | 2014-02-04
Actual
| 4 | MEASP/G/SH-2 | GPS Equipment for AIPA | Planned | B | G | SH | Post |  |  |  | N/A | 2013-10-25 | 2013-12-09 | 2013-12-30 | 2014-01-13 |  | 2014-01-20 | 2014-04-20
Revised
Actual
| 5 | MEASP/G/SH-3 (Lot 1) | Vehicles for AIPA (Lot 1 off road cars) | Planned | B | G | SH | Prior |  |  | 2013-08-09 | 2013-08-09 | 2013-08-12 | 2013-08-22 | 2013-09-03 | 2013-09-13 | MEASP/G/SH-3.1 | 2013-09-20 | 2013-11-19 | „AutoFrame-FM” S.R.L, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-08-09 | 2013-08-09 | 2013-08-12 | 2013-08-22 | 2013-09-03 | 2013-09-13 |  | 2013-09-20
| 6 | MEASP/G/SH-3 (Lot 2) | Vehicles for AIPA (Lot 2 sedan cars) | Planned | B | G | SH | Prior |  |  | 2013-08-09 | 2013-08-09 | 2013-08-12 | 2013-08-22 | 2013-09-03 | 2013-09-13 | MEASP/G/SH-3.2 | 2013-09-17 | 2013-12-16 | “DAAC-Autosport” S.R.L., Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-08-09 | 2013-08-09 | 2013-08-12 | 2013-08-22 | 2013-09-03 | 2013-09-13 |  | 2013-09-17
| 7 | MEASP/G/NCB-1 | GIS System for AIPA | Planned | B | G | NCB | Prior |  |  |  | N/A | 1899-12-31 | 1900-01-21 | 1900-02-04 | N/A |  | 1900-02-11 | 1900-05-12
Revised
Actual
|  |  | Sub Total (Goods) | [18 empty] | #REF! | #REF! | 150000 | 350000 | #REF! | #REF!
Procurement category |  | Contract # | Description of Assignment | Procurement Status | Component Nr. | Procurement Type | Procurement method | Bank's Review (Prior/ Post) | Source of finance MDTF | Source of finance IDA | Preparation of TOR, Selection criteria, budget | Bank's no objection for TOR, Selection criteria, budget | RFP/RFEoIs issued | Technical and Financial Proposal (CVs) receipt | Bank's no objection to Technical (and Financial) evaluation | Bank's no objection to contract signature | Contract Number | Contract signing date | Contract completion date | Winning bidder name&Country | Remarks | Amount reduced from previous estimates | Disbursed as of 19 Sept. 08 ( to verify) | IV Quarter 2008 | First Half 2009 | Second Half 2009 | Total
(Consultant Services - Consulting Firms) | 5 | MEASP/CS/CQ-1 | Modifications and Maintenance of AIPA online software | Planned | B | CS | CQ | Post |  |  | 2013-10-18 | 2013-10-24 | 2013-11-01 | 2013-12-09 | 2013-12-12 | 2013-12-19 |  | 2013-12-21 | 2014-08-30
Revised
|  |  |  | Actual | [6 empty] | 2013-10-18 | 2013-10-24 | 2013-11-01
| 6 | MEASP/CS/SSS-1 | Awareness, Grievance and Training in fodder imporevements | Planned | B | CS | SSS | Prior |  |  | N/A | N/A | N/A | N/A | N/A | 2013-07-26 | MEASP/CS/SSS-1 | 2013-07-26 | 2014-08-30 | National Agency for Rural Development (ACSA) NGO
Revised
|  |  |  | Actual | [6 empty] | N/A | N/A | N/A | N/A | N/A | 2013-07-26 |  | 2013-07-26
| 7 | MEASP/CS/SSS-2 | Posta Moldovei Services | Planned | A | CS | SSS | Prior |  |  | N/A | N/A | N/A | N/A | N/A | 2013-07-19 | MEASP/CS/SSS-2 | 2013-07-19 | 2013-12-31 | State Enterprise "Posta Moldovei" |  | #REF! | #REF! |  |  |  | #REF!
|  |  |  | Revised | [16 empty] | BB to follow up | #REF! |  | 150000 | 350000 | #REF! | #REF!
|  |  |  | Actual | [6 empty] | N/A | N/A | N/A | N/A | N/A | 2013-07-19 |  | 2013-07-19
| 8 | MEASP/CS/LCS-1 | Project financial audit | Planned | C | CS | LCS | Post |  |  | 2013-11-18 | 2013-11-25 | 2013-11-28 | 2013-12-28 | 2014-01-18 | 2014-02-02 |  | 2014-02-07 | 2014-08-30
Revised
Actual
| 9 | MEASP/CS/LCS-2 | Project operational audit | Planned | C | CS | LCS | Post |  |  | 2013-11-18 | 2013-11-25 | 2013-11-28 | 2013-12-28 | 2014-01-18 | 2014-02-02 |  | 2014-02-07 | 2014-08-30
Revised
Actual
(Consultant Services - Individual Consultants) | 10 | MEASP/CS/IC-1/Balti | 11 individual consultants for field offices | Planned | B | CS | IC | Post |  |  | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A | MEASP/CS/IC-1/Balti | 2013-10-15 | 2014-04-14 | Natalia Gutu, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A |  | 2013-10-15
| 11 | MEASP/CS/IC-1/Cahul |  | Planned | B | CS | IC | Post |  |  | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A | MEASP/CS/IC-1/Cahul | 2013-10-15 | 2014-04-14 | Svetlana Sava, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A |  | 2013-10-15
| 12 | MEASP/CS/IC-1/Causeni |  | Planned | B | CS | IC | Post |  |  | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A | MEASP/CS/IC-1/Causeni | 2013-10-15 | 2014-04-14 | Nicolae Untu, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A |  | 2013-10-15
| 13 | MEASP/CS/IC-1/Chisinau |  | Planned | B | CS | IC | Post |  |  | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A | MEASP/CS/IC-1/Chisinau | 2013-10-15 | 2014-04-14 | Marina Umanet, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A |  | 2013-10-15
| 14 | MEASP/CS/IC-1/Edinet |  | Planned | B | CS | IC | Post |  |  | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A | MEASP/CS/IC-1/Edinet | 2013-10-15 | 2014-04-14 | Vlad Macovei, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A |  | 2013-10-15
| 15 | MEASP/CS/IC-1/Floresti |  | Planned | B | CS | IC | Post |  |  | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A | MEASP/CS/IC-1/Floresti | 2013-10-15 | 2014-04-14 | Natalia Podlesnova, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A |  | 2013-10-15
| 16 | MEASP/CS/IC-1/Orhei |  | Planned | B | CS | IC | Post |  |  | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A | MEASP/CS/IC-1/Orhei | 2013-10-15 | 2014-04-14 | Elena Lupan, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A |  | 2013-10-15
| 17 | MEASP/CS/IC-1/Ungheni |  | Planned | B | CS | IC | Post |  |  | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A | MEASP/CS/IC-1/Ungheni | 2013-10-15 | 2014-04-14 | Oxana Ciobanu, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A |  | 2013-10-15
| 18 | MEASP/CS/IC-1/UTAG |  | Planned | B | CS | IC | Post |  |  | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A | MEASP/CS/IC-1/UTAG | 2013-10-15 | 2014-04-14 | Renata Popa, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-11 | N/A | N/A |  | 2013-10-15
| 19 | MEASP/CS/IC-12 | Individual consultants for payment execution | Planned | B | CS | IC | Post |  |  | 2013-09-10 | 2013-09-10 | 2013-09-13 | 2013-09-27 | N/A | N/A | MEASP/CS/IC-12 | 2013-10-15 | 2014-04-14 | Rodica Rozlovan, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-09-10 | 2013-09-10 | 2013-09-13 | 2013-09-27 | N/A | N/A |  | 2013-10-15
| 19 | MEASP/CS/IC-13 | Individual consultants for payment execution | Planned | B | CS | IC | Post |  |  | 2013-09-10 | 2013-09-10 | 2013-09-13 | 2013-09-27 | N/A | N/A | MEASP/CS/IC-13 | 2013-10-15 | 2014-04-14 | Diana Ter, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-09-10 | 2013-09-10 | 2013-09-13 | 2013-09-27 | N/A | N/A |  | 2013-10-15
| 20 | MEASP/CS/IC-14 | Individual consultants for financial management. Administration and Control Department | Planned | B | CS | IC | Post |  |  | 2013-09-10 | 2013-09-10 | 2013-09-13 | 2013-09-27 | N/A | N/A | MEASP/CS/IC-14 | 2013-10-15 | 2014-04-14 | Cristina Luca, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-09-10 | 2013-09-10 | 2013-09-13 | 2013-09-27 | N/A | N/A |  | 2013-10-15
| 20 | MEASP/CS/IC-15 | Individual consultants for financial management. Administration and Control Department | Planned | B | CS | IC | Post |  |  | 2013-09-10 | 2013-09-10 | 2013-09-13 | 2013-09-27 | N/A | N/A | MEASP/CS/IC-15 | 2013-10-15 | 2014-04-14 | Diana Stanciu, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-09-10 | 2013-09-10 | 2013-09-13 | 2013-09-27 | N/A | N/A |  | 2013-10-15
| 21 | MEASP/CS/IC-16 | Individual consultants for support of IT system (2 consultants) | Planned | B | CS | IC | Post |  |  | 2013-09-18 | 2013-09-18 | 2013-09-20 | 2013-09-30 | N/A | N/A | MEASP/CS/IC-16 | 2013-10-15 | 2014-04-14 | Dumitru Beznos, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-09-18 | 2013-09-18 | 2013-09-20 | 2013-09-30 | N/A | N/A |  | 2013-10-15
| 21 | MEASP/CS/IC-17 | Individual consultants for support of IT system (2 consultants) | Planned | B | CS | IC | Post |  |  | 2013-09-18 | 2013-09-18 | 2013-09-20 | 2013-09-30 | N/A | N/A | MEASP/CS/IC-17 | 2013-10-15 | 2014-04-14 | Alexandr Arman, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-09-18 | 2013-09-18 | 2013-09-20 | 2013-09-30 | N/A | N/A |  | 2013-10-15
| 22 | MEASP/CS/IC-18 | Individual consultants for in-field inspection (2 consultants) | Planned | B | CS | IC | Post |  |  | 2013-09-10 | 2013-09-10 | 2013-09-13 | 2013-09-27 | N/A | N/A | MEASP/CS/IC-18 | 2013-10-15 | 2014-04-14 | Vitalie Mihai, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-09-10 | 2013-09-10 | 2013-09-13 | 2013-09-27 | N/A | N/A |  | 2013-10-15
| 22 | MEASP/CS/IC-19 | Individual consultants for in-field inspection (2 consultants) | Planned | B | CS | IC | Post |  |  | 2013-09-10 | 2013-09-10 | 2013-09-13 | 2013-09-27 | N/A | N/A | MEASP/CS/IC-19 | 2013-10-15 | 2014-04-14 | Marta Dima, Moldova
Revised
|  |  |  | Actual | [6 empty] | 2013-09-10 | 2013-09-10 | 2013-09-13 | 2013-09-27 | N/A | N/A |  | 2013-10-15
|  |  | Sub Total (Consultant Services) | [5 empty] | 0 | 1578668 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Disbursement Estimates
Procurement category |  | Contract # | Description items | Procurement Status | Component Nr. | Procurement Type | Procurement method | Bank's Review (Prior/ Post) | Source of finance MDTF | Source of finance IDA | Preparation of TOR | Bank's no objection for TOR | RFP/ REI issued | Technical Proposal receipt | Bank's no objection for Technical proposal | Bank's no objection to contract signature | Bank's no objection to contract signature | Contract signing date | Contract completion date | Winning bidder name&Country
(Cash Grants) | 15 | MEASP/Cash Grants | Compensation for 2012 draught (seeding whinter wheat and spring corn) | Planned | A | GR | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  |  | Total Grants | [5 empty] | 0 | 0
Disbursement Estimates
|  |  | GRAND TOTAL | [5 empty] | 0 | 1578668 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Formulas:
Bid evaluation report = [Bid opening]
Bid evaluation report = [Bid opening]+5
Contract completion date = [Contract signing date]+60
Invitation for bids = [Draft Bidding Docs and SPN]+1
Bid opening = [Invitation for bids]+11
Contract signing date = [Bid evaluation report]+1
Contract signing date = [Bank's no objection to Contract award]+7
Bank's no objection to Contract award = [Bid evaluation report]+14