**Thailand HCFC Phaseout Project (P115761)**

83374

**Draft Procurement Plan**

**(Government Savings Bank)**

# 

## General

1. **Project information** : Thailand-HCFC Phaseout Project, Government Savings Bank

2. **Bank’s approval** **Date of the procurement Plan** : ……………….…..

1. **Date of General Procurement Notice** : ………………..……..
2. **Period covered by this procurement plan** : January 2014 – December 2018

##### II. Goods and Works and non-consulting services.

1. **Prior Review Threshold** : Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement :

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Procurement Method** | **Prior Review Threshold [[1]](#footnote-1)** | **Prior Review Condition** |
| 1. | Shopping (Goods) | < USD100,000 | First Contract |
| 2. | Commercial Practice (Sub-projects) | - | First Three Contracts |

**2. Proposed Procedures for Sub-project Components (as per paragraph. 3.13 of the Guidelines :** Using the commercial practice with detailed procedures referred in the relevant Project Implementation Manual.

**3. Reference to Project Implementation Manual :** To be prepared by DIW and GSB and reviewed and approved by the Bank.

**4. Any Other Special Procurement Arrangements** : Advance procurement and retroactive financing.

##### Procurement Packages with Methods and Time Schedule

**Goods under GSB-PMU**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** |
| **Ref. No.** | **Contract**  **(Description)** | **Procurement**  **Method** | **Prequalification (yes/no)** | **Domestic Preference**  **(yes/no)** | **Review**  **by Bank**  **(Prior / Post)** | **Expected**  **Bid-Opening**  **Date** | **Comments** |
| GSB- HPMP-GS-1 | Computers (2); Printer (1) | Shopping | No | No | Prior | January 2014 |  |
| GSB- HPMP-GS-2 | Office Desks/Chairs; File Cabinets | Shopping | No | No | Post | January 2014 |  |

##### III. Selection of Consultants

1. **Prior Review Threshold**: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants :

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Selection Method** | **Prior Review Threshold** | **Comments** |
| 1. | Competitive Methods  (Firms) | >USD100,000 |  |
| 2. | Single Source (Firms) | All |  |
| 3. | Individual Consultant | - | Except the long term positions |

**2. Short list comprising entirely of national consultants**: Short list of consultants for services, estimated to cost less than $500,000 equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.

**3. Any Other Special Procurement Arrangements** : Advance procurement and retroactive financing.

**4. Consultancy Assignments with Selection Methods and Time Schedule**

**Consultants under GSB-PMU**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **1** | **2** | **3** | **4** | **5** | **6** |
| **Ref. No.** | **Description of Assignment** | **Selection Method** | **Review**  **by Bank**  **(Prior / Post )** | **Expected**  **Proposal Submission**  **Date** | **Comment** |
| GSB-HPMP-CS-1 | Technical Officer (1) | 3 CVs/ Individual | Prior | January 2014 | Retroactive  36 months assignment |
| GSB- HPMP-CS-2 | Technical Officer (2) | 3 CVs/ Individual | Prior | January 2014 | Retroactive  24 months assignment |
| GSB-HPMP-CS-3 | Financial Officer | 3 CVs/ Individual | Prior | January 2014 | Retroactive  60 months |
| GSB-HPMP-CS-4 | Technology Transfer for HFC-32 Air-conditioning Technology | QCBS | Prior | February 2014 | Retroactive |
| GSB-HPMP-CS-5 | Technical assistance for micro enterprises in foam sector | Firm/CQS | Post | February 2014 | Retroactive |

1. Threshold for each procurement method. [↑](#footnote-ref-1)