Detailed Procurement Plan

Scaling-Up Participatory Sustainable Forest Management Project (P130222)

(IDA Project No: H 852-LA/TF015286)

(Revised as of January 14, 2016)

## General

1. 	Project information:

- Country/Borrower: Lao PDR

- Project Implementing Agency: National Project Management Office (NPMO), Department of Forestry (DoF), Ministry of Agriculture and Forestry (MAF) Provincial Agricultural & Forestry Office (PAFO) in 13 provinces (Khammouane, Savannakhet, Salavanh, Champasak, Attapeu, Sekong, Bolikhamxay, Vientiane, Sayabouly, Saysomboun, Bokeo, Luang Namtha and Oudomxay)

2.	Bank’s approval date of the procurement Plan:

- Original Plan:	April 9, 2013.

- First Revision:	April 29, 2014.

- Second Revision:  January 2, 2015.

- Third Revision: July 10, 2015.

- Forth Revision: January 14, 2016.

3.	Date of General Procurement Notice: Dec 27, 2013

4.	Period covered by this procurement plan: March 1, 2014 till December 2018

##### Works and Goods and Non-consultant Services

- Prior Review Threshold: Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement:

|  | Procurement Method | Contract Value Method (US$’000) | Prior Review Threshold (US$’000) | Comments |
| --- | --- | --- | --- | --- |
| 1. | NCB (Works) | 200 - < 2,000 | First NCB contract for Works |  |
| 2. | Shopping (Works) | < 200 | First shopping contract for Works. |  |
| 3. | ICB (Goods) | ≥ 600 | All ICB contractsfor goods |  |
| 4. | NCB (Goods) | 100 - < 600 | First NCB contract for goods |  |
| 5 | Shopping (Goods) | < 100 | First shopping contract for goods |  |
| 6 | Direct Contracting |  | All contracts |  |

- Prequalification. Not expected for the works/goods packages.

- Any Other Special Procurement Arrangements: None

- Procurement packages for Goods (prior and post reviews) with method and Time Schedule

| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Contract (Description) | Estimated Cost US$ | Procurement Method | Prequalification (yes/no) | Domestic Preference (yes/no) | Review by Bank (Prior / Post) | Expected Bid-Opening Date | Comments |
| Works |
| W01 | Construction of NPMO building. | 250,000 | NCB | No | No | Prior | May 2016 | First contract for NCB. Implemented by NPMO |
| W02 | Construction of new 24 district offices in 9 provinces |
| W02-1 | Phouvong DAFO, Attapeu Province. | 20,000 | Shopping | No | No | Post | February 2016 | Implemented by Provincial Forestry Section (PFS) |
| W02-2 | Houayxai DAFO, Bokeo Province. | 20,000 | Shopping | No | No | Post | September 2015 | Completed PHATTHANA Construction. |
| W02-3 | Meung DAFO, Bokeo Province. | 20,000 | Shopping | No | No | Post | September 2015 | Completed PHATTHANA Construction. |
| W02-4 | PhaOudom DAFO, Bokeo Province | 20,000 | Shopping | No | No | Post | September 2015 | Completed PHATTHANA Construction. |
| W02-5 | Tonpheung DAFO, Bokeo Province | 20,000 | Shopping | No | No | Post | September 2015 | Completed PHATTHANA Construction. |
| W02-6 | Mounlapamok DAFO, Champasak Province | 20,000 | Shopping | No | No | Post | September 2015 | Completed Inphoumy Construction. |
| W02-7 | Soukhouma DAFO, Champasak Province | 20,000 | Shopping | No | No | Post | September 2015 | Completed Inphoumy Construction. |
| W02-8 | Viengphoukha DAFO, Luang Namtha Province | 20,000 | Shopping | No | No | Post | December 2015 | Implemented by PFS. First Shopping for Works. |
| W02-9 | Nalea DAFO, Luang Namtha Province. | 20,000 | Shopping | No | No | Post | September 2015 | Completed Keovilay Construction. |
| W02-10 | Long DAFO, Luang Namtha Province. | 20,000 | Shopping | No | No | Post | September 2015 | Completed Keovilay Construction. |
| W02-11 | Beng DAFO, Oudomxay Province. | 20,000 | Shopping | No | No | Post | September 2015 | Completed KKFC Construction Co; Ltd. |
| W02-12 | Houn DAFO, Oudomxay Province. | 20,000 | Shopping | No | No | Post | September 2015 | Completed KKFC Construction Co; Ltd. |
| W02-13 | La DAFO, Oudomxay Province. | 20,000 | Shopping | No | No | Post | September 2015 | Implemented by PFS. Completed KKFC Construction Co; Ltd. |
| W02-14 | Namor DAFO, Oudomxay Province. | 20,000 | Shopping | No | No | Post | September 2015 | Completed KKFC Construction Co; Ltd. |
| W02-15 | Nga DAFO, Oudomxay Province. | 20,000 | Shopping | No | No | Post | September 2015 | Completed KKFC Construction Co; Ltd. |
| W02-16 | Pakbeng DAFO, Oudomxay Province. | 20,000 | Shopping | No | No | Post | September 2015 | Completed KKFC Construction Co; Ltd. |
| W02-17 | Xay DAFO, Oudomxay Province. | 20,000 | Shopping | No | No | Post | September 2015 | Completed KKFC Construction Co; Ltd. |
| W02-18 | Boten DAFO, Sayabouly Province. | 20,000 | Shopping | No | No | Post | February 2016 | Implemented by PFS |
| W02-19 | Hongsa DAFO, Sayabouly Province. | 20,000 | Shopping | No | No | Post | February 2016 | Implemented by PFS |
| W02-20 | Xienghon DAFO, Sayaboury Province. | 20,000 | Shopping | No | No | Post | February 2016 | Implemented by PFS |
| W02-21 | Khop DAFO, Sayabouly Province. | 20,000 | Shopping | No | No | Post | February 2016 | Implemented by PFS |
| W02-22 | Hom DAFO, Xaysomboun Province. | 20,000 | Shopping | No | No | Post | February 2016 | Implemented by PFS |
| W02-23 | Xaysomboun DAFO, Xaysomboun Province. | 20,000 | Shopping | No | No | Post | February 2016 | Implemented by PFS |
| W02-24 | Dakcheung DAFO, Sekong Province. | 20,000 | Shopping | No | No | Post | September 2015 | Completed: Khamvilay Construction. |
|  | Sub-Total for W02: | 480,000 |  |  |  |  |  |  |
| W03 | Office Renovation (4 district offices in 4 provinces) |
| W03-1 | Bokeo PAFO Office renovation | 20,000 | Shopping | No | No | Post | September 2015 | Completed PHATTHANA Construction. |
| W03-2 | Louang Namtha PAFO Office renovation | 20,000 | Shopping | No | No | Post | September 2015 | Completed Saysomboun Construction |
| W03-3 | Oudomxay PAFO Office renovation | 20,000 | Shopping | No | No | Post | September 2015 | Completed. KKFC Construction Co; Ltd. |
| W03-4 | Xaysomboun PAFO Office renovation | 20,000 | Shopping | No | No | Post | March 2016 | Implemented by PFS |
|  | Sub-Total for W03: | 80,000 |  |  |  |  |  |  |
|  | Grand Total for Works (W01+W02+W03) | 810,000 |  |  |  |  |  |  |
| Goods |
| G01 | Computers, printers and IT Accessories. | 1,121,915 | ICB | No | No | Prior | May 2015 | Completed ACE CS Intellect JV. |
| G01-1 | Notebook Computers and IT Accessories for Project’s Financial Management. | 30,000 | Shopping | No | No | Post | October 2014 | Completed SP Computer. |
| G01-2 | Power Back - UPS for Desktop Computers. | 65,000 | Shopping | No | No | Post | September 2015 | Completed Champa IT |
| G02 | Application server +storage, GIS computers, IT accessories. | 70,000 | Shopping | No | No | Prior/ Post | January 2015 | Completed Micro Info Computer. |
| G02.1 | GIS computers and IT accessories. | 10,000 | Shopping | No | No | Post | April 2016 | Implemented by NPMO. |
| G03 | Furniture |  |  |  |  |  |  |  |
| G03-1 | Furniture for New Office Building of NPMO. | 25,000 | Shopping | No | No | Post | December 2016. | Implemented by NPMO. |
| G03-1.1 | Furniture for DOF, DOFI, DAEC, DLM, DIMEX | 68,000 | Shopping | No | No | Post | October 2015 | Completed Mahasok Trading Sole Co. Ltd. |
| G03-2 | Furniture for Attapeu province and 1 District. | 6,000 | Shopping | No | No | Post | June 2016 | Implemented by PFS |
| G03-3 | Furniture for Bokeo province and 4 Districts. | 15,000 | Shopping | No | No | Post | June 2016 | Implemented by PFS |
| G03-4 | Furniture for PFS Bolikhamxay province. | 3,000 | Shopping | No | No | Post | June 2016 | Implemented by PFS |
| G03-5 | Furniture for PFS Champasak province and 2 Districts. | 9,000 | Shopping | No | No | Post | June 2016 | Implemented by PFS |
| G03-6 | Furniture for PFS Luang Namtha province and 3 Districts. | 15,000 | Shopping | No | No | Post | June 2016 | Implemented by PFS |
| G03-7 | Furniture for PFS Oudomxay province and 7 Districts. | 27,000 | Shopping | No | No | Post | June 2016 | Implemented by PFS |
| G03-8 | Furniture for PFS Vientiane province. | 6,000 | Shopping | No | No | Post | June 2016 | Implemented by PFS |
| G03-9 | Furniture for PFS Xaysomboun province and 2 Districts | 12,000 | Shopping | No | No | Post | June 2016 | Implemented by PFS |
| G03-10 | Furniture for PFS Sayabouly province and 4 Districts | 15,000 | Shopping | No | No | Post | June 2016 | Implemented by PFS |
| G03-11 | Furniture for PFS Sekong province and 1 District | 9,000 | Shopping | No | No | Post | June 2016 | Implemented by PFS |
|  | Sub-Total for G03 | 210,000 |  |  |  |  |  |  |
| G04 | Portable generator, | 12,800 | Shopping | No | No | Post | June 2016 | Implemented by NPMO. |
| G04.1 | Large display screens and wireless audio microphone | 8,800 | Shopping | No | No | Post | October 2015 | Completed Champa IT |
| G05 | Software “includes ACCPACC” | 20,000 | Shopping | No | No | Post | April 2014 | Completed; Motives Solution (Laos) Ltd. |
| G06 | Other Electronic and Field Equipment:(Silva, Suunto, Measuring Tape, Diameter Tape, Spencer Logger’s Tape) | 60,000 | Shopping | No | No | Post | February 2015 | Completed SM SURVEY EQUIPMENT SUPPLY. |
| G06-1 | Other Electronic and Field Equipment: ( Handheld GPS) | 37,000 | Shopping | No | No | Post | January 2015 | Completed SM SURVEY EQUIPMENT SUPPLY. |
| G06 - 2 | Other Electronic and Field Equipment: ( Sleeping bag and Tent) | 85,000 | Shopping | No | No | Post | December 2015 | Completed UniqTek Co; Ltd. |
| G07 | Radio equipment set, telephones and tablet computers (first lot only for testing) | 166,100 | Shopping | No | No | Post | June 2016 | Multiple contracts. |
| G08 | Satellite Images (RapidEye) 1stBatch * | 110,000 | Direct Contracting | No | No | Prior | April 2014 | Completed. Aruna Technology |
| G09 | Other remote sensing images | 300,000 | Direct Contracting | No | No | Prior | Late 2014-2018 | Completed. Aruna Technology |
| G10 | Topographic and other maps | 20,000 | Shopping | No | No | Post | Late 2014 – 2018 | Multiple contracts |
| G11 | SUV (3 Units)*, Double Cab Pick Up (72 units)* | 1,755,000 | ICB | No | No | Prior | November 2014 | Completed Lot 1: LAO TOYATA SERVICE CO; LTD. lot 2: ISUZU LAO SERVICE SOLE Co; LTD, |
| G12 | Motorbikes (755 units)* | 906,000 | ICB | No | No | Prior | March 2015 | Completed THAI YAMAHA MOTOR Co; Ltd. |
| G13 | Office Equipment: ( Scanner, Copier, Fax, LCD Projector, Wifi Router) | 230,000 | NCB | No | No | Prior | April 2016 | Implementing by NPMO. First NCB for Goods. |
| G14 | Meeting Room Sound System for NPMO. | 17,000 | Shopping | No | No | Post | December 2016 |  |
| G15 | IT equipment for DOFI | 50,000 | Shopping | No | No | Post | April 2016 |  |
| G16 | Field equipment for DOFI | 50,000 | Shopping | No | No | Post | April 2016 |  |
|  | Grand Total for Goods | 5,334,615 |  |  |  |  |  |  |
| Non – Consulting Services. |
| N01 | Transportation of 755 units of motorbikes to 13 project provinces. | 50,000 | Shopping | No | No | Post | June 2016. |  |
| N02 | Project Promotion Video Production. | 20,000 | Shopping | No | No | Post | December 2015 | Completed DANHO Media. |
|  | Grand Total for Non – Consulting Services. | 70,000 |  |  |  |  |  |  |
|  | Grand Total: W,G&N | 6,214,615 |  |  |  |  |  |  |

* priority

##### Selection of Consultants

- Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:

|  | Selection Method | Thresholds (US$,000) | Prior Review Threshold (US$’000) | Comments |
| --- | --- | --- | --- | --- |
| 1. | Competitive Methods (Firms) - Quality & Cost Based Selection (QCBS) and Quality Based Selection (QBS) | ≥300 | All Contracts |  |
|  | Least-Cost Selection (LCS) and Selection Based on Consultant Qualifications (CQS) | < 300 | ≥ 100 and/ or first Contract for hiring consulting firm regardless of value |  |
| 2. | Single Source (Firms) | - | All contracts |  |
| 3. | Individual Consultant | NA | >=10 for single source selection & all fiduciary consultants |  |

- Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than $200,000 equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.

- Any Other Special Selection Arrangements: None

- Consultancy Assignments with Selection Methods and Time Schedule

- For all contract amendments/extensions/ follow-on contracts, etc., the following guidelines shall apply: i) gross salary increases shall be limited to CPI plus a performance-based increase not to exceed 2%; ii) there shall be no increase in living  allowances or similar expenses unless explicitly authorized by MOF Decree.

| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Description of Assignment | Estimated Cost US$ | Selection Method | Review by Bank (Prior / Post) | Expected Proposals Submission Date | Comments |
| C01 | Project Financial Audit | 160,000 | CQS | Prior | March 2014 | The first contract for CQS. Completed. PriceWaterhouseCooper (Lao) Co; Ltd. |
| C02 | Design of project field offices/NPMO building, supervision of construction of NPMO building. | 50,000 | CQS | Post | February 2015 | Completed Souksavanh Consultants Sole Co, Ltd. |
| C03 | Sub-contracts with universities, private companies etc. | 960,000 | SSS/CQS | Prior/Post | April 2014 - 2018 |  |
| C03. 1 | Sub-contracts with universities, private companies etc. |  | SSS | Prior | April 2014 - 2018 | Completed. Souphanouvong University (C03-LPB1.2) |
| C03.2 | Sub-contracts with universities, private companies etc. |  | SSS | Post | April 2014 - 2018 | Completed Dongkhamxang Agriculture Technical School (C03.1-DKX) |
| C03.3 | Sub-contracts with universities, private companies etc. |  | SSS | Post | April 2014 - 2018 | Completed. Mouang Mai Agriculture and Forestry School (Bolikhamxay Province C03.1- BLK) |
| C03.4 | Sub-contracts with universities, private companies etc. |  | SSS | Post | April 2014 - 2018 | Completed. Savannakhet University, Faculty of Agriculture and Environment (C03 –ATP). |
| C03.5 | Sub-contracts with universities, private companies etc. |  | SSS | Post | April 2014 - 2018 | Completed National University of Laos, Faculty of Forestry Science (C03.1 –SKG). |
| C04 | Procurement Consultant (Short-Term International) | 128,000 | SSS | Prior | April 2014 - 2018 | Completed Ms. OithipMongkolsawath. |
| C05 | Procurement Consultant (National) | 150,000 | IC | Prior | February 2014 - 2018 | Completed. Mr. Bounsooli CHITTANON. |
| C06 | Senior Finance Management Consultant | 150,000 | IC | Prior | September 2013 - 2018 | Completed Mr. SaNguane CHINDARATH. |
| C07 | Financial Management Consultant (4 positions) |  | IC | Prior | September 2013 -2018 |  |
| C07.1 | Financial Management Consultant based in Southern Provinces. | 120,000 | IC | Prior | September 2013 - 2018 | Completed. Mr. Samlong KICHANDA. |
| C07.2 | Financial Management Consultant based in Northern Provinces. | 120,000 | IC | Prior | September 2013 | Completed. Ms. Nanthida SOUVANNA ASA. |
| C07.3 | Financial Management Consultant based in Northern Provinces. | 120,000 | IC | Prior | August 2015 | Completed. Mr. Viengxay VONGPHACHANH |
| C07.4 | Financial Management Consultant based in Middle Provinces. | 120,000 | IC | Prior | August 2015 |  |
| C08 | Project Assistants (79 positions) | 1,516,800 | IC | Post | September 2014 - 2018 | Completed. See Annex 1. |
| C09 | Other short term consultant (national) | 75,000 | IC | Prior/Post | - |  |
| C10 | Other short term consultant (international) | 60,000 | IC | Prior/Post | - |  |
| C11 | Forest Stewardship Council(FSC) auditors | 150,000 | SSS | Prior | Feb 2014- December 2018 | Completed. Rainforest Alliance Inc. |
| C12 | National Procurement Assistant | 80,000 | IC | Prior | August 2015 | Completed. Ms. Chintana XABANDITH. |
| C13 | National Consultant for Village Forestry | 150,000 | IC | Prior | February 2015 | Completed. Mr. Phonsavanh KEOASA. |
| C14 | Provincial Finance Assistant (Internship staff) | 9,600 | IC | Post | April 2015 | Completed. See Annex 2: |
| C15 | National Finance Assistant to DOF Finance Unit. | 30,000 | IC | Post | November 2015 | Completed: Mr. Chittaphone CHANHTHAVILAY |
| C16 | Village Forestry Advisor (international) | 187,000 | IC | Prior | October 2016 |  |
| C17 | Forest Management Advisor (international) | 224,000 | IC | Prior | October 2016 |  |
| C18 | Village Livelihood Development Advisor (international) | 160,000 | IC | Prior | October 2016 |  |
| C19 | M&E Advisor (international) | 340,000 | IC | Prior | October 2016 |  |
| C20 | National Forestry Consultant (Northern Provinces) | 136,000 | IC | Prior | October 2016 |  |
| C21 | National Forestry Consultant (Middle Provinces) | 136,000 | IC | Prior | October 2016 |  |
| C22 | National Forestry Consultant (Southern Provinces) | 136,000 | IC | Prior | October 2016 |  |
| C23 | National Livelihoods Development Consultant (Northern Provinces) | 136,000 | IC | Prior | October 2016 |  |
| C24 | National Livelihoods Development Consultant (Middle Provinces) | 136,000 | IC | Prior | October 2016 |  |
| C25 | National Livelihoods Development Consultant (Southern Provinces) | 136,000 | IC | Prior | October 2016 |  |
| C26 | GIS Consultant (national) | 40,000 | IC | Prior | October 2016 |  |
| C27 | Translator / Interpreter (national) | 64,000 | IC | Prior | October 2016 |  |
| C28 | Assistant to National Project Coordinator | 80,000 | IC | Prior | October 2016 |  |
|  | Grand Total for Consultants | 6,060,400 |  |  |  |  |

Annex 1: C08 Project Assistant.

| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Description of Assignment. | Estimated Cost US$. | Selection Method | Review by Bank (Prior/Post) | Expected Proposal Submission Date | Comments. |
| C08 | Project Assistant |  |  |  |  |  |
| C08.1 | VLD Project Assistant based in Pha - Oudom DAFO, Bokeo Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Xayadaeth SOUKHAPHONE. |
| C08.2 | VLD Project Assistant based in Houayxay DAFO, Bokeo Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Thongxay KEOCHANSY |
| C08.3 | VLD Project Assistant based in Meung DAFO, Bokeo Province. | 4,800 | IC | Post | September-2014 | Complete. Mr. Ekanan SINOORLAY |
| C08.4 | VLD Project Assistant based in Tonpheung DAFO, Bokeo Province. | 4,800 | IC | Post | September-2014 | Completed. Ms. Sonelideth SOUTHAMMAVONG. |
| C08.5 | PSFM Project Assistant based in Pha - Oudom DAFO, Bokeo Province. | 4,800 | IC | Post | September-2014 | Completed. Mrs. Enkeo XAYVONG. |
| C08.6 | PSFM Project Assistant based in Houayxay DAFO, Bokeo Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Somkit SAYBOUATHONG. |
| C08.7 | PSFM Project Assistant based in Meung DAFO, Bokeo Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Phounpasith SYPASERTH. |
| C08.8 | PSFM Project Assistant based in Tonpheung DAFO, Bokeo Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Khamnoy CHANHMANY. |
| C08.9 | VLD Project Assistant based in Sayabouly DAFO, Sayabouly Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Sy SYSAMOUT. |
| C08.10 | VLD Project Assistant based in Boten DAFO, Sayabouly Province. | 4,800 | IC | Post | September-2014 | Completed. Mrs. Vimone SOMPHARN. |
| C08.11 | VLD Project Assistant based in Hongsa DAFO, Sayabouly Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Thongkhoune SOUVATMOUNGKH. |
| C08.12 | VLD Project Assistant based in Khob DAFO, Sayabouly Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Phonesack ONMANY. |
| C08.13 | VLD Project Assistant based in Phieng DAFO, Sayabouly Province. | 4,800 | IC | Post | September-2014 | Completed. Ms. Phimphone SUKAPHONE. |
| C08.14 | VLD Project Assistant based in Xienghone DAFO, Sayabouly Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Sengvat XONG. |
| C08.15 | PSFM Project Assistant based in Sayabouly DAFO, Sayabouly Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Bounthasinh TINGBOUA |
| C08.16 | PSFM Project Assistant based in Boten DAFO, Sayabouly Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Niphonh CHANHTHAVONG. |
| C08.17 | PSFM Project Assistant based in Hongsa DAFO, Sayabouly Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Adisone INTHAPHORN. |
| C08.18 | PSFM Project Assistant based in Khob DAFO, Sayabouly Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Bounmark MAKEETHONG |
| C08.19 | PSFM Project Assistant based in Phieng DAFO, Sayabouly Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Linethong KOUBASITH. |
| C08.20 | PSFM Project Assistant based in Xienghone DAFO, Sayabouly Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Khonepaseuth ANOUSONE. |
| C08.21 | VLD Project Assistant based in Kaleum DAFO, Xekong Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Bountavisuk XAIYASON. |
| C08.22 | VLD Project Assistant based in Dakcheung DAFO, Xekong Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Sikham KHAMPHOUMY. |
| C08.23 | PSFM Project Assistant based in Kaleum DAFO, Xekong Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Saysamone CHOUMSYSAVNH. |
| C08.24 | PSFM Project Assistant based in Dakcheung DAFO, Xekong Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Chanpheng NARVILAISAN. |
| C08.25 | VLD Project Assistant based in Nalae DAFO, LouangNamtha Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Set SOULIXAY. |
| C08.26 | VLD Project Assistant based in Viengphoukha DAFO, LouangNamtha Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. khammixay MANISONE. |
| C08.27 | VLD Project Assistant based in Long DAFO, LouangNamtha Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Thony XAYACHACK. |
| C08.28 | PSFM Project Assistant in based Viengphoukha DAFO, LouangNamtha Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Anong XAYACHACK. |
| C08.29 | PSFM Project Assistant in Long DAFO, LouangNamtha Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Sainuan SY ONCHANH. |
| C08.30 | PSFM Project Assistant based in Nalae DAFO, LouangNamtha Province. | 4,800 | IC | Post | September-2014 | Completed. Ms. Kheuam MORVANHXAY. |
| C08.31 | VLD Project Assistant based in Houn DAFO, Oudomxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Singthong SOUDTHIVONG |
| C08.32 | VLD Project Assistant based in Beng DAFO, Oudomxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Thongphoun LOUANGSIDA. |
| C08.33 | VLD Project Assistant based in Xay DAFO, Oudomxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Sisavath TOULAKOUN. |
| C08.34 | VLD Project Assistant based in Namor DAFO, Oudomxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Somsak DUENSAVANH. |
| C08.35 | VLD Project Assistant based in Nga DAFO, Oudomxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Viengxay KEOVILAY. |
| C08.36 | VLD Project Assistant based in La DAFO Oudomxay Province. | 4,800 | IC | Post | September-2014 | Completed. Ms. Dy SYAMPHAY. |
| C08.37 | VLD Project Assistant based in Parkbeng DAFO, Oudomxay Province. | 4,800 | IC | Post | September-2014 | Completed. Ms. Tamon SAIYASAN |
| C08.38 | PSFM Project Assistant based in Parkbeng DAFO, Oudomxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Thony XAYASITH. |
| C08.39 | PSFM Project Assistant based in Namor DAFO, Oudomxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Sombuth SOUDAPHONE. |
| C08.40 | PSFM Project Assistant based in Beng DAFO, Oudomxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Ounheuan XAYAPHONE. |
| C08.41 | PSFM Project Assistant based in La DAFO, Oudomxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Phonethavy CHINDALA. |
| C08.42 | PSFM Project Assistant based in Nga DAFO, Oudomxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Thongsouk KEOPHILA. |
| C08.43 | PSFM Project Assistant based in Houn DAFO, Oudomxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Invanh PHIATHEP. |
| C08.44 | PSFM Project Assistant based in Xay DAFO, Oudomxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr.Bounthavy KEOPANHYA. |
| C08.45 | VLD Project Assistant based in Sanamxay DAFO, Attapeu Province. | 4,800 | IC | Post | September-2014 | Completed. Mr Thepthida OUDOMPHANH |
| C08.46 | VLD Project Assistant based in Phouvong DAFO, Attapeu Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Phonexay SENGPHACHAN |
| C08.47 | VLD Project Assistant based in Xaysetha DAFO, Attapeu Province. | 4,800 | IC | Post | September-2014 | Completed. Mr Kedsana VONGNALAD |
| C08.48 | PSFM Project Assistant based in Xaysetha DAFO, Attapeu Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Thanongsack VONGNANEE. |
| C08.49 | PSFM Project Assistant based in Sanamxay DAFO, Attapeu Province. | 4,800 | IC | Post | September-2014 | Completed. Mr Phonevina XAYABOUD |
| C08.50 | PSFM Project Assistant based in Phouvong DAFO, Attapeu Province. | 4,800 | IC | Post | September-2014 | Completed. Mr Phonepasith SESANGCHAN |
| C08.51 | VLD Project Assistant based in Bolikhan DAFO, Bolikhamxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Sonthany INTHANOUSONE |
| C08.52 | VLD Project Assistant based in Parksan DAFO, Bolikhamxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Soisavath SISOMBATH |
| C08.53 | VLD Project Assistant based in Parkading DAFO, Bolikhamxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Soubanh KEOMUNG |
| C08.54 | VLD Project Assistant based in Viengthong DAFO, Bolikhamxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Viengxay MOUA |
| C08.55 | PSFM Project Assistant based in Bolikhan DAFO, Bolikhamxay Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Soulin XAYYALATH |
| C08.56 | PSFM Project Assistant based in Moulapamok DAFO, Champasack Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Nutthasin CHANHTHAPHIM |
| C08.57 | PSFM Project Assistant based in Soukhoumma DAFO, Champasack Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Xam SAYYASING |
| C08.58 | PSFM Project Assistant based in Bajieng DAFO, Champasack Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Phoukhao PHOUTTHAVONG |
| C08.59 | VLD Project Assistant based in Soukhomma DAFO, Champasack Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Khaokeo PHOUMSAVATH |
| C08.60 | VLD Project Assistant based in Moulapamok DAFO, Champasack Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Phaiphanom XAYYALATH. |
| C08.61 | VLD Project Assistant based in Anouvong DAFO, Saysomboun Province. | 4,800 | IC | Post | September-2014 | Completed. Mr Xongchang Ngiakaoleng |
| C08.62 | PSFM Project Assistant in based Anouvong DAFO, Saysomboun Province. | 4,800 | IC | Post | September-2014 | Completed. Mr Khamsao Khamsavanh |
| C08.63 | PSFM Project Assistant based in Kasi DAFO, Vientiane Province. | 4,800 | IC | Post | September-2014 | Completed. Mr Soumounsay XAYAVONG. |
| C08.64 | PSFM Project Assistant based in Maet DAFO, Vientiane Province. | 4,800 | IC | Post | September-2014 | Completed. Mr khamsy DAOPASERTH |
| C08.65 | VLD Project Assistant based in Vangveing DAFO, Vientiane Province. | 4,800 | IC | Post | September-2014 | Completed. Ms khonsavanh KEOPHOMMA. |
| C08.66 | VLD Project Assistant based in Kasi DAFO, Vientiane Province. | 4,800 | IC | Post | September-2014 | Completed. Mr Viley PHOMMACHIT. |
| C08.67 | VLD Project Assistant based in Maet DAFO, Vientiane Province. | 4,800 | IC | Post | September-2014 | Completed. Mr Vilasak PHITAENG. |
| C08.68 | VLD Project Assistant based in Vangvieng DAFO, Vientiane Province. | 4,800 | IC | Post | September-2014 | Completed. Mr Toukta PHILAVONG |
| C08.69 | VLD-PSFM Project Assistant based in Parklai DAFO, Sayabouly Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Inta VINANMA. |
| C08.70 | VLD-PSFM Project Assistant based in Lamman DAFO, Xekong Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Soutchai PHOMMACHANH. |
| C08.71 | VLD-PSFM Project Assistant based in Sanxay DAFO, Xekong Province. | 4,800 | IC | Post | September-2014 | Completed. Mr Siha BOUDSADY |
| C08.72 | VLD-PSFM Project Assistant based in Salavanh PAFO. | 4,800 | IC | Post | September-2014 | Completed. Mr. Vathana XAYAPHET. |
| C08.73 | VLD-PSFM Project Assistant based in Savannakhet PAFO. | 4,800 | IC | Post | September-2014 | Completed. Ms. Siphandone PHIEWONE |
| C08.74 | PSFM-VLD Project Assistant based in Sanakham DAFO, Vientiane Province. | 4,800 | IC | Post | September-2014 | Completed. Mr They VANSY |
| C08.75 | PSFM-VLD Project Assistant based in Meun DAFO, Vientiane Province. | 4,800 | IC | Post | September-2014 | Completed. Mr Inpone VORLAVONG. |
| C08.76 | PSFM-VLD Project Assistant based in Feuang DAFO, Vientiane Province. | 4,800 | IC | Post | September-2014 | Completed. Mr. Boukhao SAYACHACK. |
| C08.77 | PSFM-VLD Project Assistant based in Khammouane PAFO. | 4,800 | IC | Post | September-2014 | Completed. Mr. Phousaming KHOUANPASA. |

Annex 2: Provincial Finance Assistant (Internship Staff).

| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Description of Assignment | Estimated Cost US$ | Selection Method | Review by Bank (Prior/Post) | Expected Proposals Submission Date | Comments |
| C14 | Provincial Finance Assistant. (Internship Staff) |  | IC | Post | April 2015 |  |
| C14.1 | Provincial Finance Assistant. Based in Sayabouly Province. | 1,200 | IC | Post | April 2015 | Completed. Ms. Phompha SILISOMBATH. |
| C14.2 | Provincial Finance Assistant. Based in Vientiane Province. | 1,200 | IC | Post | April 2015 | Completed. Ms. Amphaivanh ALOUNSAVATH. |
| C14.3 | Provincial Finance Assistant. Based in Khammouane Province. | 1,200 | IC | Post | April 2015 | Completed. Ms. Pananh SILUBSY. |
| C14.4 | Provincial Finance Assistant. Based in Salavanh Province. | 1,200 | IC | Post | April 2015 | Completed. Mr. Sengchanh VORASANE |
| C14.5 | Provincial Finance Assistant. Based in Savannakhet Province. | 1,200 | IC | Post | April 2015 | Completed. Ms.Souban SENGNAVONG. |
| C14.6 | Provincial Finance Assistant. Based in Champasack Province. | 1,200 | IC | Post | April 2015 | Completed. Mr. Khamphay PHOMMALOUN |
| C14.7 | Provincial Finance Assistant. Based in Sekong Province. | 1,200 | IC | Post | April 2015 | Completed. Ms. Niphaphone KHAMPHASOUK |
| C14.8 | Provincial Finance Assistant. Based in Attapeu Province. | 1,200 | IC | Post | April 2015 | Completed. Ms. Phonethip SENGKEO. |
|  | Grand Total for Consultants | 9,600 |  |  |  |  |

# Text boxes

103651