汉江雅口航运枢纽工程（湖北内河航运能力提升项目）采购计划（2018）

Procurement Plan of Yakou Navigation Complex（Hubei Inland Waterway Improvement Project）（2018）

一、相关说明   NOTES

1.本采购计划更新时间：2018年1月17日

The Update Time of the Procurement Plan: January 17th, 2018

2.本项目总采公告时间：2016年9月14日

Published Date of GPN: September 14th, 2016

3.本采购计划覆盖时间：全部项目周期

The Covered Duration of the Procurement Plan: Whole Cycle of the Project

4.土建及供货安装前审限额：1500万美元

The Prior Review Threshold for Works and Supply & Installation: USD15 Million

5.货物前审限额：400万美元

The Prior Review Threshold for Goods: USD 4 Million

6.咨询公司前审限额：200万美元

The Prior Review Threshold for Firm Consultant : USD 2 Million

7. 个人咨询前审限额：40万美元

The Prior Review Threshold for Individual Consultant : USD 400,000

二、土建安装工程采购计划一览表

2.Procurement  Summary of Civil Works and Installation

表1          Table 1

| 序号 Item | 招标项目 Component | 采购范围及内容 Procurement Contents | 估算费用 （万元） Estimated cost (10000 Yuan) | 估算费用 （万美元） Estimated Cost (10000 US dollar) | 采购 方式 Procurement Method | 前审、 后审 Prior/Post Review | 采购时间 安排 Procurement Timetable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| W1 | 河道疏挖工程 River way Dredging | 左岸临时航道疏挖，左岸下游河道疏挖。Dredging for temporary navigable corridor and downstream riverway at left side bank | 1727.60 | 261.76 | NBF |  | 已于2016年8月完成采购 Procurement Completed in August 2016 |
| W2 | 进场道路工程（路基） Access Road(sub-grade) | 进场道路路基施工，长12公里。 Construction for the sub-grade of access road, with length of 12km | 1189.94 | 180.29 | NBF |  | 已于2016年8月完成采购 Procurement Completed in August 2016 |
| W3 | 进场道路工程（路面）Access Road(pavement) | Construction for the pavement of access road, with length of 12km | 487.17 | 73.81 | NBF |  | 2020.07 |
| W4 | 电站厂房、右岸土石坝及16孔泄水闸工程 Powerhouse, earth dam at right bank and 16 sluice gates | 一期围堰土石方填筑、防渗防护及拆除，电站厂房，16孔泄水闸，右岸土坝填筑、防护及防渗处理，导流堤，电站船闸连接段，鱼道工程，河道疏挖，电站、泄水闸、鱼道、补水渠金结安装，泄水闸启闭设备安装，降排水及四通一平等临时工程。 Earth filling, anti-seepage protection and dismantle for cofferdam at phase one, powerhouse, 16 sluice gates, earth filling, protection and anti-seepage treatment for earth dam at right bank, diversion dike, connection between power plant and ship lock, fish way, dredging, metal structure installation for power plant, sluice gates, fish way and replenishment channel, installation for hoist equipment of sluice gates, temporary works for dewatering and drainage as well as the accesses of water, road, electricity ,telecommunication and flattening construction yard | 66595.93 | 10090.29 | ICB | 前审 Prior Review | 已于2016年12月完成采购 Procurement Completed in December 2016 |
| W5 | 船闸及坝顶公路桥工程 Shiplock and road bridge on dam crest | 船闸土建工程，航道连接段及下游疏浚，围堰范围内坝顶公路桥，船闸金结及启闭设备安装，降排水及其他临时工程。 Civil works for ship lock, connections sections for navigable course and dredging at downstream, road bridge on dam crest within the cofferdam, installation of metal structure and hoist equipment for ship lock, dewatering and drainage works as well as other temporary works | 22713.13 | 3441.38 | ICB | 前审 Prior Review | 已于2017年4月完成采购 Procurement Completed in April 2017 |
| W6 | 左岸土石坝及28孔泄水闸工程 Earth dam at left bank and 28 sluice gates | 二期围堰土石方填筑、防渗防护及拆除，28孔泄水闸，左岸土坝填筑、防护及防渗处理，围堰范围内坝顶公路桥，泄水闸金结及启闭设备安装，降排水及四通一平等临时工程。 Earth filling, anti-seepage protection and dismantle for cofferdam at phase two,28 sluice gates, earth filling, protection and anti-seepage treatment for earth dam at left bank, road bridge on dam crest within the cofferdam, installation for hoist equipment of sluice gates, temporary works for dewatering and drainage as well as the accesses of water, road, electricity ,telecommunication and flattening construction yard | 39564.26 | 5994.58 | ICB | 前审 Prior Review | 2018.05～2018.09 |
| W7-W11 | 房屋及其它建筑工程 Housing and other construction | 坝区生产用房及管理处房屋土建、装潢工程及配套工程，联合生态调度基地（武汉）。 Civil works for manufacturing and administration housing, decoration and ancillary works and ecological dispatching base in Wuhan | 6304.11 | 955.17 | NBF |  | 2019.05～2019.09 |
| W12 | 增殖站土建及房建总图工程 Civil works for aquatic breeding stations and general engineering | 增殖站蓄水池、培育池、隔离池等，房建道路、停车场、给排水等。 Water storage pond for aquatic breeding station, cultivating pool, isolation pool, roads for housing, parking yard and water supply and drainage | 1770.59 | 268.27 | NBF |  | 2018.05～2018.09 |
| W13 | 机电设备安装工程 Installation of E&M works | 船闸、泄水闸、电站电气安装，发电机组及附属设备安装、调试。 Electrical installation for ship lock, sluice gates and power plant, installation and debugging for generating units and ancillary equipments | 4547.41 | 689.00 | NCB | 后审 Post Review | 已于2017年9月完成采购 Procurement Completed in September 2017 |
| W14- W15 | 电力接入系统及10KV备供电源工程 Power access system and 10KV for power supply | 接入系统线路建设工程，电力接入系统变电站间隔扩建及保护改造工程，枢纽工程10KV备供电源工程。 Cable construction for access system, expansion and protection works for the intervals of converting station of power access system | 1873.00 | 283.79 | NBF |  | 2018.06 |
| W16 | 环境保护工程 Environment Protection Works | 联合生态调度及其他环保工程。 Joint ecological dispatching and other environment works | 4845.87 | 734.22 | NBF |  | 2018.06 |
| W17 | 水土保持工程 Soil and water conservation works | 水土保持工程。 Soil and water conservation works | 2520.81 | 381.94 | NBF |  | 2018.06 |
| W18 | 工程及安全监测 Monitoring for engineering and safety | 施工期对所建工程进行安全监测。 Safety monitoring for engineering during construction periods | 839.73 | 127.23 | NBF |  | 已于2017年7月完成采购 Procurement Completed in July 2017 |

注： 1美元＝6.6元人民币，下同。

Note: 1US dollar=6.6 Yuan RMB hereinafter

三、货物采购计划一览表

3.Procurement Summary of Goods

表2 table2

| 序号 Item | 招标项目 Component | 采购范围及内容 Procurement Contents | 估算费用 （万元） Estimated cost (10000 Yuan) | 估算费用 （万美元） Estimated Cost (10000 US dollar) | 采购 方式 Procurement Method | 前审、 后审 Prior/Post Review | 采购时间 安排 Procurement Timetable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| G1 | 水轮发电机组及其附属设备 Turbine sets and ancillary equipment | 6台单机容量12.5MW的灯泡贯流式水轮发电机组及附属设备。 6*12.5MW flow-bulb turbine sets and ancillary equipments | 27426.18 | 4155.48 | NBF |  | 2018.1 |
| G2 | 泄水闸金属结构 Metal structure for sluice gate | 44孔泄水闸弧形门及其埋件、检修门及自动抓梁等。 44 arch sluice gates and their embedded parts, emergency gates, lifting beam and so on | 13215.83 | 2002.40 | ICB | 前审 Prior Review | 已于2017年12月完成采购 Procurement Completed in December 2017 |
| G3 | 船闸、电站厂房、鱼道金属结构 Metal structure for ship lock, powerhouse and fish way | 船闸上、下闸首共4扇人字闸门，4扇输水门、2扇检修闸门及2扇检修阀门及埋件等，电站上、下游检修门及埋件等。 4 herringbone sluice gates at upper and down lock head, 4 water conveyance gates, 2 emergency gates, 2 emergency valves en embedded parts, emergency gates and embedded parts of power house at upstream and downstream and so on | 6187.79 | 937.54 | NCB | 前审 Prior Review | 已于2017年9月完成采购 Procurement Completed in September 2017 |
| G4 | 船闸、泄水闸启闭设备 Hoist equipment for ship lock and sluice gates | 44孔泄水闸液压油缸、动力站，船闸人字门及阀门等液压油缸、动力站，相应的现地和集中监控系统。 Hydraulic jack and power station for 44 herringbone sluice gates and valves and corresponding on-site and concentrated monitoring system | 4983.57 | 755.09 | NCB | 前审 Prior Review | 已于2017年9月完成采购 Procurement Completed in September 2017 |
| G6 | 增殖站设备采购与安装 Equipment procurement and installation for aquatic breeding stations | 增殖站设备采购、安装。 Equipment procurement and installation for aquatic breeding stations | 461.15 | 69.87 | NBF |  | 2018.12 |
| G7 | 导助航设施、船舶 Navigating facilities and vessels | 航标、锚地趸船、清污船、应急救援船采购。 Procurement for Navigation marks, anchorage barge, cleaning ship, emergency rescue ship | 2667.27 | 404.13 | NBF |  | 2019.02 |
| XX01-02 | 信息化建设工程 Informatization engineering | 枢纽建设期间及建成后的信息化管理系统。 Informatization management system for on- gonging and as-built period of complex construction | 980.00 | 148.48 | NBF |  | 已于2017年1月完成采购 Procurement Completed in January 2017 |
| G8 | 泄水闸门机，进水、尾水门机，厂房及GIS桥机制造 Portal crane manufacturing for sluice gates, inflow water, tail water, powerhouse and GIS bridge crane | 泄水闸门机、进水门机、尾水门机、厂房桥机及GIS桥机采购。 Procurements of portal crane for sluice gates, inflow water, tail water, powerhouse and GIS bridge crane | 1989.31 | 301.41 | NCB | 后审 Post Review | 已于2018年1月完成采购 Procurement Completed in January 2018 |
| G9 | 厂房固定屋盖 Fixed roof cover for powerhouse | 厂房固定屋盖制作安装。 Fabrication and installation of fixed roof cover for powerhouse | 788.43 | 119.46 | NBF |  | 2018.06 |
| G11 | 电站电力变压器 Electrical transformer of powerhouse | 电站的电力变压器及附属设备的制造。(110kv变压器) Manufacturing of electrical transformer of powerhouse and ancillary equipments | 750.00 | 113.64 | NBF |  | 已于2017年5月完成采购 Procurement Completed in May 2017 |
| G12 | 电站升压开关站 Booster switch station of power plant | 110KVGIS及其附属设备，110KV户外敞开式高压设备，110KV电缆及终端。（GIS设备采购） 110KVGIS and its ancillary equipments, 110KV outdoor open high voltage equipment, 110KV cable and terminal | 430.00 | 65.15 | NBF |  | 已于2017年5月完成采购 Procurement Completed in May 2017 |
| G13 | 船闸、泄水闸电气系统 Electrical system for ship lock and sluice gates | 船闸、泄水闸控制系统，船闸、泄水闸高压配电柜。 Control system and high voltage distribution cabinets for ship lock and sluice gates | 1105.00 | 167.42 | NBF |  | 2017.12 |
| G14 | 厂房高压配电柜 High Voltage Distributing Cabinet for powerhouse | 厂房高压配电柜采购。 Procurement of high voltage distributing cabinet for powerhouse | 800.00 | 121.21 | NBF |  | 2017.12 |
| G15 | 电线电缆 Electric wire and cable | 厂房低压动力电缆、船闸配电及动力电缆，泄水闸配电及动力电缆。 Low voltage power cable for powerhouse, distributing and power cable for ship lock and sluice gates | 1557.00 | 235.91 | NBF |  | 2018.09 |
| G16 ～ G38 | 公用及其它设备 Public and other equipments | 巡查、维修车辆，电力变压器，厂用低压配电设备，电缆桥架，照明装置，柴油发电机组，直流系统，计算机监控，微机继电保护，通信，设备检修工器具，厂区水厂设备，厂用电梯、空压机设备、供排水泵，阀门，水情自动测报系统。 Cruise and maintenance vehicles, electrical transformers, low voltage distributing facilities for powerhouse, cable bridge crane, lighting facilities, diesel generator, DC system, computer monitoring , relay protection, communication, tools for equipment overhaul, water plant facilities, lifts, air compressor facilities, supply and drainage pump, valves, automatic detecting and reporting system for water situation | 3886.78 | 588.91 | NBF |  |  |

附：公用及其他设备采购清单表

Annex :Procurement List of Public and Other Equipment

| 序号 item | 采购项目 contents | 采购方式 Procurement method | 估算费用（万元） Estimated cost (10000 Yuan) | 估算费用 （万美元） Estimated Cost (10000 US dollar) | 采购时间安排Procurement timetable |
| --- | --- | --- | --- | --- | --- |
| G16 | 电力变压器 power transformer | NBF | 177.00 | 26.82 | 2018.06 |
| G17 | 厂用低压配电设备 Low voltage distributing facilities for powerhouse |  | 220.00 | 33.33 | 2018.05 |
| G18 | 电缆桥架 Bridge crane for cable |  | 425.61 | 64.49 | 2018.09 |
| G19 | 照明装置及其附属设备 Lighting and ancillary facilites |  | 188.00 | 28.48 | 2018.09 |
| G20 | 柴油发电机组 Diesel generating sets |  | 73.00 | 11.06 | 2018.06 |
| G21 | 直流系统 DC system |  | 129.43 | 19.61 | 2018.08 |
| G22 | 电站计算机监控系统 Computerized monitoring system of power plant |  | 357.93 | 54.23 | 2018.03 |
| G23 | 全厂公用辅助设备控制系统 Public ancillary equipment control system |  | 90.00 | 13.64 | 2018.08 |
| G24 | 微机继电保护系统 Relay protection system |  | 374.92 | 56.81 | 已于2017年12月完成采购 Procurement Completed in December 2017 |
| G25 | 电力调度数据网络接入设备、电厂通信 Power dispatching data network access equipment, power plant communication |  | 335.71 | 50.87 | 2018.09 |
| G26 | 设备预试、安全工器具 Equipment pre-test and safety tools |  | 52.87 | 8.01 | 2018.12 |
| G27 | 设备检修工器具 Equipment maintenance tool |  | 50.00 | 7.58 | 2018.12 |
| G28 | 厂区水厂设备采购安装 Procurement and installation of water plant equipment |  | 90.00 | 13.64 | 2019.03 |
| G29 | 消防设备 Fire-fighting equipment |  | 178.50 | 27.05 | 2019 |
| G30 | 厂房采暖通风设备 Plant heating and ventilation equipment |  | 65.67 | 9.95 | 2019 |
| G31 | 空压机设备和储气罐 Air compressor equipment and gas storage tank |  | 140.00 | 21.21 | 2018.07 |
| G32 | 油处理设备及滤水器 Oil treatment equipment and water filter |  | 116.53 | 17.66 | 2018.07 |
| G33 | 全厂长轴深井泵、供排水泵采购 Procurement of long shaft deep well pump and supply & drainage pump |  | 136.00 | 20.61 | 2018.01 |
| G34 | 自动化原件 Original automation |  | 53.75 | 8.14 | 2018.10 |
| G35 | 阀门 valve |  | 150.00 | 22.73 | 2018.10 |
| G36 | 电梯设备 Lifting facilities |  | 100.00 | 15.15 | 2018.05 |
| G37 | 水情自动测报系统 Automatic detecting and reporting system for water condition |  | 136.86 | 20.74 | 2018.4 |
| G38 | 巡查、维修及运输车辆 Inspection, maintenance and transport vehicles |  | 245.00 | 37.12 | 2019.03 |

四、咨询服务采购计划一览表

4.Procurement  Summary of consulting service

表3

| 序号 item | 项目或合同 Project or Contract | 估算费用 （万元） Estimated cost (10000 Yuan) | 估算费用 （万美元） Estimated Cost (10000 US dollar) | 采购 方式 Procurement Method | 前审、 后审 Prior/Post Review | 采购时间 安排 Procurement Timetable |
| --- | --- | --- | --- | --- | --- | --- |
| T1 | 航道信息系统（WIS）的开发和试点waterway information system (WIS) study and pilot | 132.00 | 20.00 | NBF |  | 2018-2019 |
| T2 | 航道信息系统安全管理IWT safety management | 132.00 | 20.00 | NBF |  | 2018-2019 |
| T3 | 累积性环境影响分析detailed cumulative effects assessment | 380.00 | 57.58 | NBF |  | 2018-2019 |
| T4 | 过鱼设施评估evaluation of fish facilities | 210.00 | 31.82 | NBF |  | 2018-2019 |
| T5 | 汉江沿江生态调度ecological scheduling along the Han River | 300.00 | 45.45 | NBF |  | 已于2017年8月完成采购 Procurement Completed in August 2017 |