## Goods & Works
REPUBLIC of TAJIKISTAN: Land Registration and Cadastre System for Sustainable Agriculture Project (LRCSP)
DRAFT
Budget for training on Additional Financing (April 2012 - March 2015) dated December 05, 2012
Item No: | Package number | Method | Plan/Act. | Cost Estimate US $ | Draft bidding documents and SPN | WB No-objection to bidding documents | Bidding documents issuance | Bids opening | Evaluation report | WB No-objection to contract award | Contract Signing | Contract Completion | Bank review | Comments
1 | Other local training (local workshops and conferences) | DC | Plan | 15,000.00 | Apr-13 | Apr-13 | N/A | N/A | N/A | N/A | Jun-13 | Aug-13 | Prior
Actual
2 | Other local training (local workshops and conferences) | DC | Plan | 15,000.00 | Apr-14 | Apr-14 | N/A | N/A | N/A | N/A | Jun-14 | Aug-14 | Prior
Actual
3 | Other local training (local workshops and conferences) | DC | Plan | 5,000.00 | Jan-15 | Jan-15 | N/A | N/A | N/A | N/A | Feb-15 | Feb-15 | Prior
Actual
4 | Abroad study tours (especially for BTI staff) | DC | Plan | 75,000.00 | May-13 | May-13 | N/A | N/A | N/A | N/A | Jul-13 | Jul-13 | Prior
Actual
5 | Abroad study tours (especially for BTI staff) | DC | Plan | 75,000.00 | May-14 | May-14 | N/A | N/A | N/A | N/A | Jul-14 | Jul-14 | Prior
Actual
6 | Monitoring and Evaluation workshops | DC | Plan | 30,000.00 | Apr-14 | Apr-14 | May-14 | May-14 | June-14 | June-14 | June-14 | June-14 | Prior
Actual
7 | Abroad study tours PMU staff | DC | Plan | 25,000.00 | Sept-12 | Sept-12 | N/A | N/A | N/A | June-12 | Dec-12 | Dec-12 | Prior
Actual
8 | Abroad study tours PMU staff | DC | Plan | 50,000.00 | Jan-13 | Jan-13 | N/A | N/A | N/A | Mar-13 | Apr-13 | Dec-13 | Prior
Actual
9 | Abroad study tours PMU staff | DC | Plan | 50,000.00 | Jan-14 | Jan-14 | N/A | N/A | N/A | Mar-14 | Apr-14 | Sept-14 | Prior
Actual
Procurement plan updated by: Davlatov J.