## Thresholds.
Procurement Plan
I. General
1. Project Information:
· Project Name: | Teacher Education Improvement Project
· Country: | West Bank and Gaza
· Project Code: | P 097315
2. Bank’s approval Date of the Procurement Plan: Oct.22.2012
3. Date of General Procurement Notice: July.21.2010
4. Period covered by this procurement plan: |  |  | First 18 months
Expenditure Category |  | Procurement | Contracts Subject to
|  | Method | Prior Review By the Bank (US$)
1. Goods |  | ICB | All contracts
|  | NCB | First contract regardless of its value
|  | Shopping | First contract regardless of its value
|  | Direct contracting | All contracts
2. Consulting Services
Firms |  | QCBS/QBS | First contract per each of the two methods and thereafter all contracts > 200,000
|  | CQS | First contract regardless of its value
|  | LCS | First contract regardless of its value
|  | SSS | All contracts
Individuals |  | IC | First contract regardless of its value and thereafter all contracts > US$100,000
|  | SSS | All contracts

## Goods
Schedule
|  |  |  | Stat. | Proc | WB
NO. | Component Reference | Description | No. of |  | Method | Rev | Prep. of | WB | Issue of | Bids submission/ | Evaluation | WB | Contract | Contract | Start | Comple. | Contractor
|  |  | Lots/ packages |  |  | Prior/ | Bidding | NO | Bidding | Openning | Report | NO | Award | Sig. | Date | Date
[6 empty] | Post | Docs |  | Docs
G01 | 1 | DSQ and NIET Office Equipment (RFQ-TEIP-01-2011) | 1 | P | S | Prior | May.05.2011 | May.12.2011 | May.15.2011 | May.25.2011 | June.05.2011 | June.10.2011 | June.12.2011 | June.15.2011 | June.15.2011 | Aug.01.2011
R
|  |  |  | A |  |  | April.05.2011 | May.05.2011 | May.08.2011 | May.18.2011 | June.13.2011 | June.24.2011 | June.26.2011 | June.27.2011 | June.27.2011 | Aug.28.2011 | BCI
|  |  |  | A | [9 empty] | June.26.2011 | June.26.2011 | June.27.2011 | EDISCO
|  |  |  | A | [9 empty] | June.27.2011 | June.27.2011 | Aug.09.2011 | CMC
G02 | 1 | DSQ and NIET Office Equipment (RFQ-TEIP-02-2011) | 1 | P | S | Post | June.19.2011 |  | June.20.2011 | June.30.2011 | NA | NA | July.15.2011 | July.20.2011 | July.20.2011 | Sep.15.2011
R
|  |  |  | A |  |  | July.01.2011 |  | July.05.2011 | July.13.2011 | Aug.2011 | NA | Aug.14.2011 | Aug.14.2011 | Aug.14.2011 | Aug.22.2011 | Ayava Co.
G03 | 1 | Schools ICT Equipment NCB-01-2012 | 2 | P | NCB | Prior | Nov.15.2011 | Nov.22.2011 | Dec.10.2011 | Jan.25.2012 | Feb.16.2012 | Feb.23.2012 | mar.01.2012 | Mar.09.2012 | Mar.09.2012 | May.20.2012
|  |  |  | R |  |  | Sep.15.2012 | Oct.02.2012 | Oct.15.2012 | Nov.20.2012 | Dec.03.2012 | Dec.15.2012 | Dec.25.2012 | Jan.05.2012 | Jan.15.2012 | April.30.2012
|  |  |  | A |  |  | Sep.20.2012 | Oct.22.2012 | Nov.12.2012
G04 | 1 | Arabic & English Books for NIET Library (RFQ-TEIP-03-2013) | 1 | P | S | Post | Jan.15.2013 | NA | Jan.15.2013 | Feb.02.2013 | Feb.10.2013 | NA | Feb.15.2013 | Feb.20.2013 | Mar.01.2013 | May.30.2013
R
A
Total
|  | Legend | P | Plan
|  |  | R | Revised
|  |  | A | Actual
|  |  | WB | World Bank

## Consultants Services
No. | Component Reference | Description | [5 empty] | Schedule
|  |  | Stat. |  | Select. | Contract type | WB
[5 empty] | Method |  | Rev | Prep. of | WB NO | REOI ADV. | Sub. Of EOIs | Short list | WB NO | Prep. Of | WB NO | Issue of | Sub. Of | Tech. Eval. | WB NO | Open. of Fin. Proposals | Invitation for Neg. | Neg./ Draft Contract | WB NO | Contract Signing | Start | Completion date | Consultant Name | Contract Status
[7 empty] | Prior/ | TOR | [5 empty] | RFP |  | RFP/ Invitations | Proposals | [7 empty] | date
Post
CS 01 | 3 | Assistant Procurement Officer | P |  | IC |  | Post | Feb 01.2010 | NA | NA | NA | Mar.10.2010 | NA | NA | NA | NA | NA | Mar.24.2010 | NA | NA | NA | April.04.2010 | April.18.2010 | April.18.2010 | June.01.2010 | Dec.31.2011 |  | Done
|  |  | R |  |  | TB
|  |  | A |  |  |  |  | Oct.12.2010 | NA | NA | NA | Oct.14.2010 | Oct.14.2010 |  |  |  |  | Oct.17.2010 | NA |  |  | Oct.17.2010 | NA | Oct.20.2010 | Nov.01.2010 | Dec.31.2011 | Isra Al Khayyat
CS 02 | 3 | Assistant Finance Officer | P |  | IC |  | Post | Feb.01.2010 | NA | Feb.17.2010 | NA | Mar.10.2010 | NA | NA | NA | NA | NA | Mar.24.2010 | NA | NA | NA | April.04.2010 | NA | May.02.2010 | May.02.2010 | Dec.31.2011 |  | Done
|  |  | R |  |  | TB
|  |  | A |  |  |  |  | Oct.12.2010 |  |  |  | Oct.14.2010 | [5 empty] | Oct.14.2010 |  |  |  | Oct.17.2010 |  | Nov.01.2010 | Nov.01.2010 | Dec.31.2011 | Mohammad Khalili | Done
CS 03 | 1 | West Bank Coordinator -Comp 1 | P |  | IC |  | Post | Dec.01.2010 | NA | Dec.17.2010 | NA | Oct.25.2010 | NA | NA | NA | NA | NA | Nov.02.2010 | NA | NA | NA | Nov.12.2010 | NA | Nov.15.2010 | Dec.01.2010 | Dec.31.2011 |  | Done
|  |  | R |  |  | TB
|  |  | A |  |  |  |  | Oct.01.2010 |  | Oct.07.2010 |  | Jan.25.2011 | [5 empty] | Feb.16.2011 |  |  |  | Feb.28.2011 |  | Feb.28.2011 | Mar.01.2011 | Feb.29.2012 | Abdullah Bsharat
CS 04 | 2 | West Bank Coordinator -Comp 2 | P |  | IC |  | Post | NA | Dec.01.2010 | Dec.17.2010 | NA | Oct.25.2010 | NA | NA | NA | NA | NA | Nov.02.2010 | NA | NA | NA | Nov.12.2010 |  | Nov.15.2010 | Dec.01.2010 | Dec.31.2011 |  | Done
|  |  | R |  |  | TB
|  |  | A |  |  |  |  | Oct.01.2010 |  | Oct.07.2010 |  | Feb.07.2011 | [5 empty] | Mar.01.2011 |  |  |  | April.20.2011 |  | April.27.2011 | May.15.2011 | May.14.2012 | Mahmoud Manasra
CS 05 | 1 | Intarnationl Technical Assistance for Comp. 1 | P |  | QCBS |  | Prior | Dec.01.2010 | Dec.08.2010 | Dec.22.2010 | Jan.01.2011 | Jan.30.2011 | Feb.07.2011 | Dec.22.2010 | Dec.28.2010 | Feb.08.2011 | Mar.10.2011 | Mar.31.2011 | April.07.2011 | April.14.2011 | May.08.2011 | May.11.2011 | May.18.2011 | May.22.2011 | June.01.2011 | May.02.2013 |  | Ongoing
|  |  | R |  |  | LS
|  |  | A | [6 empty] | July.16.2010 | Aug.05.2010 | Dec.09.2010 | Dec.20.2010 | Dec.09.2010 | Dec.20.2010 | Dec.21.2010 | Feb.07.2011 | Mar.03.2011 | Mar.13.2011 | Mar.21.2011 | Mar.30.2011 | April.13.2011 | May.01.2011 | May.02.2011 | May.10.2011 |  | CCCU
CS 06 | 2 | Intarnationl Teacher Education Institution for Comp 2 | P |  | QCBS |  | Prior | Dec.01.2010 | Dec.08.2010 | Dec.22.2010 | Jan.01.2011 | Jan.30.2011 | Feb.07.2011 | Dec.22.2010 | Dec.28.2010 | Feb.08.2011 | Mar.10.2011 | Mar.31.2011 | April.07.2011 | April.14.2011 | May.08.2011 | May.11.2011 | May.18.2011 | May.22.2011 | June.01.2011 | May.02.2013 |  | Ongoing
|  |  | R |  |  | LS
|  |  | A | [6 empty] | July.16.2010 | Aug.15.2010 | Dec.15.2010 | Dec.20.2010 | Dec.22.2010 | Dec.27.2010 | Jan.13.2011 | Feb.14.2011 | Mar.23.2011 | Aprl.15.2011 | April.21.2011 | April.8.2011 | May.05.2011 | May.11.2011 | May.15.2011 | June.01.2011 |  | ABU Consult Berlin GmbH
CS 07 | 1 | Teaching Practice Team -Comp 1- Gaza Area | P |  | SSS |  | Prior | Jan.31.2011 | Feb.08.2011 | NA | NA | NA | NA | Mar.01.2011 | NA | May.12.2011 | June.13.2011 | July.13.2011 | July.20.2011 | NA | July.20.2011 | July.20.2011 | July.27.2011 | Aug.01.2011 | Aug.012011 | June.30.2015 |  | Ongoing
|  |  | R |  |  | LS
|  |  | A |  |  |  |  | April.04.2011 | May.01.2011 |  |  |  |  | April.04.2011 | May.01.2011 | May.26.2011 | July.24.2011 | Oct.04.2011 | Oct.17.2011 |  | Oct.01.2011 | Oct.04.2011 | Oct.17.2011 | Oct.20.2011 | Oct.20.2011 | June.01.2015 | Al Azhar University
CS 08 | 1 | Teaching Practice Team -Comp 1- West Bank- North Area | P |  | SS |  | Prior | Jan.31.2011 | Feb.08.2011 | NA | NA | NA | NA | Mar.01.2011 | NA | May.12.2011 | June.13.2011 | July.13.2011 | July.20.2011 | NA | July.20.2011 | July.20.2011 | July.27.2011 | Aug.01.2011 | Aug.012011 | June.30.2015 |  | Ongoing
|  |  | R |  |  | LS
|  |  | A |  |  |  |  | April.04.2011 | May.01.2011 |  |  |  |  | April.04.2011 | May.01.2011 | May.26.2011 | July.25.2011 | Oct.31.2011 | Oct.31.2011 |  | Sep.20.2011 | Oct.31.2011 | Oct.31.2011 | Nov.01.2011 | Nov.01.2011 | June.01.2015 | AAUJ
CS 09 | 1 | Teaching Practice Team -Comp 1- West Bank- South Area | P |  | SS |  | Prior | Jan.31.2011 | Feb.08.2011 | NA | NA | NA | NA | Mar.01.2011 | NA | May.12.2011 | June.13.2011 | July.13.2011 | July.20.2011 | NA | July.20.2011 | July.20.2011 | July.27.2011 | Aug.01.2011 | Aug.012011 | June.30.2015 |  | Ongoing
|  |  | R |  |  | LS
|  |  | A |  |  |  |  | April.04.2011 | May.01.2011 |  |  |  |  | April.04.2011 | May.01.2011 | May.26.2011 | June.29.2011 | Aug.25.2011 | Sep.12.2011 |  |  | Aug.25.2011 | Sep.12.2011 | Sep.26.2011 | Sep.26.2011 | June.01.2015 | Bethlehem University
CS 10 | 1 | Teaching Practice Team -Comp 1- West Bank- Middle Area | P |  | SS |  | Prior | Jan.31.2011 | Feb.08.2011 | NA | NA | NA | NA | Mar.01.2011 | NA | May.12.2011 | June.13.2011 | July.13.2011 | July.20.2011 | NA | July.20.2011 | July.20.2011 | July.27.2011 | Aug.01.2011 | Aug.012011 | June.30.2015 |  | Cancelled
|  |  | R |  |  | LS
|  |  | A |  |  |  |  | April.04.2011 | May.01.2011 |  |  |  |  | April.04.2011 | May.01.2011 | May.26.2011 | July.25.2011 | [9 empty] | UNRWA
CS 11 | 2 | Upgrading Under Qualified Teachers -Com 2- West Bank- Middle Area | P |  | SS |  | Prior | May.20.2011 | May.27.2011 | NA | NA | NA | NA | May.20.2011 | May.27.2011 | June.01.2011 | July.01.2011 | Aug.01.2011 | NA | NA | Aug.08.2011 | Aug.20.2011 | Sep.01.2011 | Sep.10.2011 | Sep.10.2011 | June.01.2015 |  | Ongoing
|  |  | R |  |  | LS | [15 empty] | April.10.2012 | April.20.2012 | April.25.2012 | May.01.2012 | June.01.2015
|  |  | A |  |  |  |  | May.26.2011 | May.31.2011 |  |  |  |  | May.26.2011 | May.31.2011 | June.08.2011 | Oct.15.2011 | May.09.2012 | May.14.2012 |  | April.26.2012 | May.09.2012 | May.14.2012 | May.21.2012 | May.21.2012 | June.01.2015 | BZU
CS 12 | 2 | Upgrading Under Qualified Teachers -Com 2- West Bank- Jerusalem Area | P |  | SS |  | Prior | May.20.2011 | May.27.2011 | NA | NA | NA | NA | May.20.2011 | May.27.2011 | June.01.2011 | July.01.2011 | Aug.01.2011 | NA | NA | Aug.08.2011 | Aug.20.2011 | Sep.01.2011 | Sep.10.2011 | Sep.10.2011 | June.01.2015 |  | Ongoing
|  |  | R |  |  | LS
|  |  | A |  |  |  |  | May.26.2011 | May.31.2011 |  |  |  |  | May.26.2011 | May.31.2011 | June.08.2011 | Oct.16.2011 | Mar.14.2012 | Mar.19.2012 |  | Feb.01.2012 | Mar.14.2012 | Mar.19.2012 | Mar.25.2012 | Mar.25.2012 | June.01.2012 | Al Quds University
CS 13 | 2 | Upgrading Under Qualified Teachers -Com 2- West Bank- South Area | P |  | SSS |  | Post | May.20.2011 | May.27.2011 | NA | NA | NA | NA | May.20.2011 | May.27.2011 | June.01.2011 | July.01.2011 | Aug.01.2011 | NA | NA | Aug.08.2011 | Aug.20.2011 | Sep.01.2011 | Sep.10.2011 | Sep.10.2011 | June.01.2015 |  | Ongoing
|  |  | R |  |  | LS
|  |  | A |  |  |  |  | May.26.2011 | May.31.2011 |  |  |  |  | May.26.2011 | May.31.2011 | June.09.2011 | Oct.16.2011 | Mar.14.2012 | Mar.19.2012 |  | Feb.01.2012 | Mar.14.2012 | Mar.19.2012 | Mar.25.2012 | Mar.25.2012 | June.01.2015 | Hebron University
CS 14 | 2 | Upgrading Under Qualified Teachers -Com 2- West Bank- North Area | P |  | SSS |  | Prior | May.20.2011 | May.27.2011 | NA | NA | NA | NA | May.20.2011 | May.27.2011 | June.01.2011 | July.01.2011 | Aug.01.2011 | NA | NA | Aug.08.2011 | Aug.20.2011 | Sep.01.2011 | Sep.10.2011 | Sep.10.2011 | June.01.2015 |  | Ongoing
|  |  | R |  |  | LS
|  |  | A |  |  |  |  | May.26.2011 | May.31.2011 |  |  |  |  | May.26.2011 | May.31.2011 | June.09.2011 | Oct.21.2011 | Mar.01.2012 | Mar.09.2012 |  | Feb.01.2012 | Mar.01.2012 | Mar.09.2012 | Mar.18.2012 | Mar.18.2012 | June.01.2015 | An Najah University
CS 15 | 2 | Upgrading Under Qualified Teachers -Com 2- West Bank- Gaza Area | P |  | SSS |  | Post | May.20.2011 | May.27.2011 | NA | NA | NA | NA | May.20.2011 | May.27.2011 | June.01.2011 | July.01.2011 | Aug.01.2011 | NA | NA | Aug.08.2011 | Aug.20.2011 | Sep.01.2011 | Sep.10.2011 | Sep.10.2011 | June.01.2015 |  | Ongoing
|  |  | R |  |  | LS
|  |  | A |  |  |  |  | May.26.2011 | May.31.2011 |  |  |  |  | May.26.2011 | May.31.2011 | June.09.2011 | Oct.16.2011 | Mar.14.2012 | Mar.19.2012 |  | Feb.01.2012 | Mar.14.2012 | Mar.19.2012 | Mar.25.2012 | Mar.25.2012 | June.01.2015 | Al Azhar University
CS 16 | 1+2 | External Audit Firm | P |  | LCS |  | Prior | Dec.01.2010 | Dec.08.2010 | Dec.22.2010 | Jan.01.2011 | Jan.30.2011 | Feb.07.2011 | Dec.22.2010 | Dec.28.2010 | Feb.08.2011 | Mar.10.2011 | Mar.31.2011 | April.07.2011 | April.14.2011 | May.08.2011 | May.11.2011 | May.18.2011 | May.22.2011 | June.01.2011 | Dec.31.2012 | Talal Abu Ghazali Co. | Ongoing
|  |  | R |  |  | LS | [20 empty] | This Activity will be impleminted by the MoF
|  |  | A | [14 empty] | Feb.07.2012 |  |  |  | Feb.10.2012 | Feb.13.2012
CS 17 | 1+2 | M&E Consultant | P |  | IC |  | Post | May.12.2011 | NA | May.15.2011 | May.29.2011 | June.09.2011 | NA | NA | NA | NA | NA | June.28.2011 | NA | NA | July.10.2011 | NA | NA | July.10.2011 | July.15.2011 | June.02.2015 |  | Ongoing
|  |  | R |  |  | LS
|  |  | A |  |  |  |  | June.15.2011 | NA | July.21.2011 | July.31.2011 | Oct.09.2011 | NA |  |  |  |  | Oct.30.2011 | [5 empty] | Jan.02.2012 | Jan.02.2012 | June.02.2015 | Faisal Awartani
CS 18 | 3 | Assistant Procurement Officer | P |  | SSS |  | Prior | [20 empty] | Done
|  |  | R |  |  | TB | [20 empty] | Isra Al Khayyat
|  |  | A | [18 empty] | Oct.31.2011 | Oct.31.2011 | Jan.01.2012 | Jan.01.2012 | Dec.31.2012 | Renewal
CS 19 | 3 | Assitant Finance Officer | P |  | SSS |  | Prior | [20 empty] | Done
|  |  | R |  |  | TB | [20 empty] | Mohammad Khalili
|  |  | A | [18 empty] | Oct.31.2011 | Oct.31.2011 | Jan.01.2012 | Jan.01.2012 | Dec.31.2012 | Renewal
CS 20 | 1 | West Bank Coordinator -Comp 1 | P |  | SSS |  | Prior | [20 empty] | Ongoing
|  |  | R |  |  | TB | [20 empty] | Abdullah Bsharat
|  |  | A | [18 empty] | Jan.26.2012 | Jan.29.2012 | Mar.01.2012 | Mar.01.2012 | Dec.31.2013 | Renewal
CS 21 | 2 | West Bank Coordinator -Comp 2 | P |  | SSS |  | Prior | [20 empty] | Ongoing
|  |  | R |  |  | TB | [20 empty] | Mahmoud Manasra
|  |  | A | [18 empty] | April.20.2012 | May.01.2012 | May.15.2012 | May.15.2012 | Dec.31.2013 | Renewal
CS 22 | 1 | Teaching Practice Team -Comp 1- West Bank- Middle Area | P |  | SSS |  | Prior | [20 empty] | Ongoing
|  |  | R |  |  | LS
|  |  | A |  |  |  |  | April.04.2011 | May.01.2011 |  |  |  |  | April.04.2011 | May.01.2011 | Sep.09.012 | Oct.11.2012 | Nov.25.2012 | Dec.04.2012 | Oct.11.2012 | Nov.13.2012 | Nov.25.2012 | Dec.04.2012 | Dec.04.2012 | Dec.05.2012 | June.30.2015 | An Najah University
CS 23 | 1+2 | Gaza Coordinator | P |  | SSS |  | Prior | [14 empty] | Dec.15.2012 | Dec.25.2012 | Jan.01.2013 | Jan.01.2013 | Dec.31.2013 |  | Pending
|  |  | R |  |  | TB | [20 empty] | Hani Nigem
|  |  | A | [23 empty] | Renewal
CS 24 | 3 | Procurement Officer | P |  | SSS |  | Prior | [14 empty] | Nov.01.2012 | Nov.20.2012 | Jan.01.2013 | Jan.01.2013 | Dec.31.2013 | Isra Al Khayyat | Pending
|  |  | R |  |  | TB | [20 empty] | Renewal
|  |  | A | [18 empty] | Nov.25.2012
CS 25 | 3 | Finance Officer | P |  | SSS |  | Prior | [14 empty] | Nov.01.2012 | Nov.20.2012 | Jan.01.2013 | Jan.01.2013 | Dec.31.2013 | Mohammad Khalili | Pending
|  |  | R |  |  | TB | [20 empty] | Renewal
|  |  | A | [18 empty] | Nov.25.2012
CS 26 | 3 | Financial Manager | P |  | SSS |  | Prior | [14 empty] | Nov.01.2012 | Nov.20.2012 | Jan.01.2013 | Jan.01.2013 | Dec.31.2013 | Nadine Njoom | Pending
|  |  | R |  |  | TB | [20 empty] | Renewal
|  |  | A | [18 empty] | Nov.25.2012
CS 27 | 3 | Procurement Specialist | P |  | SSS |  | Prior | [14 empty] | Nov.01.2012 | Nov.20.2012 | Jan.01.2013 | Jan.01.2013 | Dec.31.2013 | Fadi Al Haj Ibrahim
|  |  | R |  |  | TB | [20 empty] | Renewal
|  |  | A | [18 empty] | Nov.25.2012
CS 28 | 3 | Administrative Assistant | P |  | SSS |  | Prior | [19 empty] | Feda Qtairi | ongoing
|  |  | R |  |  | TB | [20 empty] | the contract shall be financed under the TEP- AF from the period May 24- Dec.31.2012 and from TEIP for the period Jan.01- Dec.31.2013
|  |  | A | [18 empty] | April.05.2012 | April.16.2012 | April.17.2012 | May.24.2012 | Dec.31.2013
Total
|  | Legend | P | Plan
|  |  | R | Revised
|  |  | A | Actual
|  |  | WB | World Bank