## Sheet1
Project Information
Country: Austria
Project Name: Capacity Building for Water Supply and Wastewater Utilities
Grant №: TF012722
Implementing Agency: International Association of Water Supply Companies in the Danube Catchment Area (IAWD)
Bank's Approval Date of the Procurement Plan: February 14, 2014
Date of General Procurement Notice:
Period Covered with this Procurement Plan:
Grant Closing Date: October 15, 2015
Expenditure Category | Contract Value (US$) | Procurement Method | Bank Prior Review
Goods | <100 000 | Shopping | First contract
| NA | DC | All DC contracts
Non-consulting Services | <200 000 | Shopping | First contract
| NA | DC | All DC contracts
Consultant Services | >=300 000 | QCBS, QBS,FBS,LCS | First contract for firms, All contracts >= US$ 200 000 for firms; all contracts >=US$ 100 000 for individuals and all SSS contracts including all TORs irrelevant of the value of the contracts
| <300 000 | QCBS, QBS,FBS,LCS and CQS
| NA | SSS
| NA | IC
Notes | QCBS - Quality-and Cost Based Selection; QBS- Quality Based Selection; Fixed Budget Selection; LCS - Least-Cost Selection; CQS -Consultant's Qualification Selection; IC-Individual Consultants; DC-Direct Contract; SSS-Single (or Sole) Source Selection

## PP 140214 (clean)
|  | Procurement plan | [7 empty] | italic= | indicative
|  | Programme structure |  |  |  |  | Formal background |  |  | Procurement process
| Workpackage | Project |  | Process |  |  | Type | Selection Method | WB review | ToR ready, WB OK | Publishing | Date EoI | Shortlist, WB OK | Date Bids | Tech. eval., WB OK | Budget / Fin. eval an WB | Final WB OK | Contract signature
No. | Name | No. | Activity | No. | Name | Reference
4 | Operation | 1 | Technical Secretariat | 1 | Programme Coordinator | 1.1 | Individual Consultant | IC | prior | 2012-11-29 | 2012-12-10 | 2012-12-31 | 2013-03-20 | n.a. | 2013-04-10 |  | 2013-04-17 | 2013-06-07
4 | Operation | 1 | Technical Secretariat | 2 | Procurement Specialist | 1.2 | Individual Consultant | IC | prior | 2013-03-05 | 2013-03-06 | 2013-03-30 |  |  | 2013-04-22 |  | 2013-04-27 | 2013-06-07
4 | Operation | 2 | Financial management | 1 | Accounting & Financial Management Consultant | 2.1 | Consulting Company | LCS | prior | 2012-12-17 | 2012-12-17 | 2013-01-04 | 2013-02-12 | 2012-03-13 | 2013-03-21 | 2013-04-05 | 2013-04-12 | 2013-04-15
4 | Operation | 2 | Financial management | 2 | Program financial audit | 2.2 | Consulting Company | LCS | prior | 2013-10-11 | 14/10/2013 | 2013-11-18 | 2013-12-30 | 2014-02-12
4 | Operation | 3 | Tech. Sec. office | 1 | IT equipment for the TS | 3.1 | Goods | Shopping | prior | 2013-07-05 | 2013-07-05 |  |  | 2013-07-12 |  | 2013-07-23 | 2013-07-24 | 2013-07-24
4 | Operation | 3 | Tech. Sec. office | 2 | Annual Operating costs | 3.2 | Operating costs | Operating Costs | N.A.
1 | Regional | 4 | RS.3 Developm. Communication Platform | 1 | Web Side Designer incl. option 24 M support | 4.1 | Individual Consultant | IC | post | 2013-07-11 | Fri 12/07/13 | Fri 19/07/13 | [5 empty] | 2013-09-01
2 | National | 4 | NC.1 | 2 | Translation of DVGW standards into Serbian | 4.2 | Individual Consultant | 3 CVs | post | Fri 19/07/13 | [7 empty] | 2013-09-02
|  | 5 | RC.IV.1 Regional Results-based Asset Management Program | 1 | IT equipment for the AM Hub | 5.1 | Goods | Shopping | post | Fri 20/12/13 | Fri 17/01/14 |  |  | 2014-01-29 | 2014-01-30 |  |  | 2014-02-04
|  | 5 | RC.IV.1 Regional Results-based Asset Management Program | 2 | Establish and Operate an IAWD Asset Management Regional Service Hub located in Belgrade | 5.2 | Consulting Company | SSS | prior | 2014-01-31
|  | 5 | RC.IV.1 Regional Results-based Asset Management Program | 7 | Costs for Site Visits & Seminars, travels, accomodation over the project duration | 5.7 | Operating costs | Operating Costs
|  | 6 | 2.0 NC 2 Competetive Grant Window |  | Competitive Grant Window | 6. |  | acc. OM CGW | post
|  | 6 | Proposal 1 | 1 | National Commission of Public Utilities Regulation Improvement of the National Benchmarking System in the Water and Sanitation Sector in Ukraine | 6.1
|  | 6 |  | 1.1 | tbd | 6.1.1 | tbd | tbd
|  | 6 | Proposal 2 | 2 | Moldova National Ass of WSS Utilities (AMAC) Retraining of Managers, Chief Engineers, and Specialists of the Water and Sanitation Utilities | 6.2
|  | 6 |  | 2.1 | tbd | 6.2.1 | tbd | tbd
|  | 6 | Proposal 3 | 3 | Water Training Centre - FCFPPDA (ARA) | 6.3
|  | 6 |  | 3.1 | tbd | 6.3.1 | tbd | tbd
|  | 6 | Proposal 4 | 4 | Bulgarian Water Association BWA Benchmarking in Bulgarian Water Sector | 6.4
|  | 6 |  | 4.1 | Project Manager | 6.4.1 | Individual Consultant | IC | post |  | 2014-12-02 | 28/2/2014 | [5 empty] | 2014-07-03
|  | 6 |  | 4.2 | Water expert | 6.4.2 | Individual Consultant | IC | post |  | 20/03/2014 | 20/04/2014 | [5 empty] | 27/04/2014
|  | 6 |  | 4.3 | data collection & Processing expert | 6.4.3 | Individual Consultant | IC | post |  | 20/03/2014 | 20/04/2014 | [5 empty] | 27/04/2014
|  | 6 |  | 4.4 | IT Expert | 6.4.4 | Individual Consultant | IC | post |  | 20/03/2014 | 20/04/2014 | [5 empty] | 27/04/2014
|  | 6 |  | 4.5 | Events, Travels, etc | 6.4.5 | Operating costs | Operating Costs | post
|  | 6 |  | 4.6 | IT exquipment | 6.4.6 | Goods | Shopping | post
|  | 6 | Proposal 5 | 5 | Ass for Water Technology and Sanitary Engineer Editing of UTVSI DVGW Technical Rules for Drinking Water Supply in Serbian | 6.5
|  | 6 |  | 5.1 |  | 6.5.1 | tbd | tbd
|  | 6 | Proposal 6 | 6 | VIK Sarejewo Editing Technical rules for drinking water and wastewater in Bosnia language | 6.6
|  | 6 |  | 6.1 |  | 6.6.1 | tbd | tbd
|  | 6 | Proposal 7 | 7 | UC Waterworks East Sarejewo | 6.7
|  | 6 |  | 7.1 |  | 6.7.1 | tbd | tbd
|  | 6 | Proposal 8 | 8 | Macedonian Water Utility Assoc. ADKOM | 6.8
|  | 6 |  | 8.1 |  | 6.8.1 | tbd | tbd
|  | 6 | Proposal 9 | 9 | PUC Vodovod - Kumanovo Reduction of NRW | 6.9
|  | 6 |  | 9.1 |  | 6.9.1 | tbd | tbd
|  | 6 | Proposal 10 | 10 | SHUKOS Preparing project proposals and documentation for application | 6.10
|  | 6 |  | 10.1 |  | 6.10.1 | tbd | tbd
|  | 6 | Proposal 11 | 11 | SHUKALB DEVELOPING A FRAMEWORK AND BUSINESS MODEL FOR A REGIONAL WATER SUPPLY AND WASTEWATER TRAINING CENTER IN THE WESTERN BALKANS | 6.11
|  | 6 |  | 11.1 | Project Coordinator | 6.11.1 | Individual Consultant | IC 3CV | post |  | 20/01/2014 | 28/02/2014 | [5 empty] | 2014-07-03
|  | 6 |  | 11.2 | Project Manager | 6.11.2 | Individual Consultant | IC 3CV | post |  | 20/01/2014 | 28/02/2014 | [5 empty] | 2014-07-03
|  | 6 |  | 11.3 | Local Expert 1 | 6.11.3 | Individual Consultant | IC 3CV | post |  | 20/03/2014 | 20/04/2014 | [5 empty] | 27/04/2014
|  | 6 |  | 11.4 | Local Expert 2 | 6.11.4 | Individual Consultant | IC 3CV | post |  | 20/03/2014 | 20/04/2014 | [5 empty] | 27/04/2014
|  | 6 |  | 11.5 | Local Expert 3 | 6.11.5 | Individual Consultant | IC 3CV | post |  | 20/03/2014 | 20/04/2014 | [5 empty] | 27/04/2014
|  | 6 |  | 11.6 | Local Expert 4 | 6.11.6 | Individual Consultant | IC 3CV | post |  | 20/03/2014 | 20/04/2014 | [5 empty] | 27/04/2014
|  | 6 |  | 11.7 | International Expert | 6.11.7 | Individual Consultant | IC 3CV | post |  | 20/03/2014 | 20/04/2014 | [5 empty] | 27/04/2014
|  | 6 |  | 11.6 | International Travel, Accommodation | 6.11.6 | Operating costs | Operating costs | post
|  | 6 | Proposal 12 | 12 | SHUKALB DEVELOP A TRAINING COURSE FOR THE PREPARATION OF A STRATEGIC BUSINESS PLAN FOR WATER ASSOCIATIONS | 6.12
|  | 6 |  | 12.1 | Business Planning Expert | 6.12.1 | Individual Consultant | IC 3CV | post |  | 16/01/2014 | 28/02/2014 | [5 empty] | 2014-07-03
|  | 6 |  | 12.2 | Project Coordinator | 6.12.2 | Individual Consultant | IC 3CV | post |  | 16/01/2014 | 28/02/2014 | [5 empty] | 2014-07-03
|  | 6 |  | 12.3 | Project Manger | 6.12.3 | Individual Consultant | IC 3CV | post |  | 16/01/2014 | 17/03/2014 | [5 empty] | 24/03/2014
|  | 6 |  | 12.4 | Train the Trainers Expert | 6.12.4 | Individual Consultant | IC 3CV | post |  | 16/07/2014 | 15/08/2014 | [5 empty] | 22/08/2014
|  | 6 |  | 12.5 | Two Day Training Event | 6.12.5 | Operating costs | Operating Costs | post
|  | 6 | Proposal 13 | 13 | P.E. Vodovod Bistrica Biljelo Polje Strengthening the Capacity of Water Utilities in the Region with Benchmarking of Key Performance Indicators | 6.13
|  | 6 |  | 13 |  | 6.13 | tbd | tdd
|  | 6 | Proposal 14 | 14 | PUC Nis Improvement of integral water management in Serbia through cooperative responsible business performance of the water sector | 6.14
|  | 6 |  | 14.1 | Expert for water protection | 6.14.1 | Individual Consultant | IC 3CV | post
|  | 6 |  | 14.2 | Project assistant | 6.14.2 | Individual Consultant | IC 3CV | post
|  | 6 |  | 14.3 | Financial expert | 6.14.3 | Individual Consultant | IC 3CV | post
|  | 6 |  | 14.4 | Designer/Layouter | 6.14.4 | Individual Consultant | IC 3CV | post
|  | 6 |  | 14.5 | Fylers, Brochures, Furniture | 6.14.5 | Goods | Shopping | post
|  | 6 |  | 14.6 | Event, transportation, rent | 6.14.6 | Operating costs | Operating Costs | post
|  | 7 | RC III Utility Benchmarking | 1 | Carrying out a WSS Utility Benchmarking Progarm in the Danube Region | 7.1 | Consulting Company | SSS | prior
|  | 7 | RC III Utility Benchmarking | 5 | Costs for Bench Hub | 7.5 | Operating Costs Hub | Operating Costs | post
|  | 8 | RC 1 WSSS Associations Strengthening Support |  |  | 8.
|  | 8 |  | 11 | Bulgarian Association Business Plan | 8.11
|  | 8 |  | 11.1 | Business Planning Expert | 8.11.1 | Individual Consultant | IC 3CV | post
|  | 3 | Tech. Sec. office | 3 | Data Processing expert | 3.3 | Individual Consultant | IC 3CV | post |  | Fri 17/01/14 | 27/01/14
|  | 9 | RC V 2 Regional Commercial efficiency Program | 1 | Commercial Efficiciency Institution | 9.1 | Consulting Company | QCBS | prior
Formulas:
Final WB OK = [Tech. eval., WB OK]+7
Final WB OK = [Budget / Fin. eval an WB]+7
Tech. eval., WB OK = [Date EoI]+23
indicative = [italic=]