|  |
| --- |
| **Restructuring** **Status:** **Archived** |
| **Restructuring Type:** **Level two** |
| Last modified on date : 04/18/2013 |

|  |  |
| --- | --- |
| **1. Basic Information** | |
| Project ID & Name | P098496: TZ-Sci.&Tech. High Educ. Prog-Ph.1 (FY08 |
| Country | Tanzania |
| Task Team Leader | Arun R. Joshi |
| Sector Manager/Director | Sajitha Bashir |
| Country Director | Philippe Dongier |
| Original Board Approval Date | 05/27/2008 |
| Original Closing Date: | 06/30/2013 |
| Current Closing Date | 06/30/2013 |
| Proposed Closing Date [if applicable] | 02/28/2014 |
| EA Category | B-Partial Assessment |
| Revised EA Category | B-Partial Assessment-Partial Assessment |
| EA Completion Date |  |
| Revised EA Completion Date |  |

|  |  |  |
| --- | --- | --- |
| **2. Revised Financing Plan (US$m)** | | |
| **Source** | **Original** | **Revised** |
| BORR | 0.00 | 0.00 |
| IDA | 100.00 | 100.00 |
| **Total** | 100.00 | 100.00 |

|  |  |  |
| --- | --- | --- |
| **3. Borrower** | | |
| **Organization** | **Department** | **Location** |
| Ministry of Finance and Economic Affairs |  | Tanzania |

|  |  |  |
| --- | --- | --- |
| **4. Implementing Agency** | | |
| **Organization** | **Department** | **Location** |
| Ministry of Education & Vocational Training |  | Tanzania |

|  |  |  |
| --- | --- | --- |
| **5. Disbursement Estimates (US$m)** | | |
| **Actual amount disbursed as of 04/23/2013** **74.42** | | |
| **Fiscal Year** | **Annual** | **Cumulative** |
| 2012 | 0.00 | 74.42 |
| 2013 | 18.60 | 93.02 |
| 2014 | 6.98 | 100.00 |
|  | **Total** | **100.00** |

|  |  |
| --- | --- |
| **6. Policy Exceptions and Safeguard Policies** | |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes**  **Original/Current Project Development Objectives/Outcomes** |
| The Project Developmet Objective is to increase the quantity and quality of higher education graduates, with special emphasis on science, technology, and education, through an improved learning environment. |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|  |