## Procurement Plan Cover
PROCUREMENT PLAN
ISTANBUL SEISMIC RISK MITIGATION AND EMERGENCY PREPAREDNESS PROJECT
ADDITIONAL FINANCING
As of April 30, 2014 (Revision No.5)
I. General
1. Project Information
|  | Country |  |  | : | Turkey
|  | Borrower |  |  | : | Republic of Turkey
|  | Project Name |  |  | : | Istanbul Seismic Risk Mitigation and Emergency Preparedness Project Additional Financing
|  | Loan No |  |  | : | 8033-TU
|  | Implementing Agency |  |  | : | Istanbul Special Provincial Administration
| 2. Bank's Approval Date of the Procurement Plan: |  |  |  |  | Original: 03 March 2011; Revision No.1: 01 November 2011
Revision No. 2: 01 August 2012; Revision No.3: 01 January 2013
Revision No.4: 01 July 2013; Revision 4.01: November 05, 2013
Revision No.5: 30 April 2014
| 3. Date of General Procurement Notice: |  |  |  |  | 16 March 2011
| 4. Period Covered with this Procurement Plan: |  |  |  |  | 31 December 2013 - 31 December 2014
| 5. Loan Closing Date: |  |  |  |  | 2014-12-31
II. Goods and Works and Non-consulting services (Technical Services)
1. Prior Review Threshold : Procurement decisions subject to Prior Review by the Bank as stated in Appendix 1 to the
Procurement Guidelines.
|  |  | Procurement Method | Procurement Method Threshold |  | Prior Review Threshold
|  |  | International Competitive Bidding (ICB) | Contracts valued ≥$ 1,000,000 - Goods and related technical services |  | All contracts are subject to prior review
Contracts valued ≥$ 15,000,000 - Works and Non-consulting services
|  |  | National Competitive Bidding (NCB) | Contracts valued < $1,000,000 - Goods and related technical services |  | None of the NCB contracts is subject to prior review
|  |  |  | Contracts valued < $15,000,000 - Works and Non-consulting services |  | None of the NCB contracts is subject to prior review
|  |  | Shopping | Contracts valued <$ 100,000 - Goods and related technical services |  | None of the Shopping contracts is subject to prior review
Contracts valued < $ 100,000 - Works and Non-consulting services
|  |  | Direct Contracting | No threshold |  | All contracts are subject to prior review
III. Selection of Consultants
1. Prior Review Threshold : Selection decisions subject to Prior Review by the Bank as stated in Appendix 1 to the
Consultant Guidelines
|  |  | Selection Method | Selection Method Threshold |  | Prior Review Threshold
|  |  | Quality and Cost Based Selection (QCBS) | No threshold |  | Contracts valued ≥$ 350,000
|  |  | Least Cost Selection (LCS) | No threshold
|  |  | Fixed Budget Selection (FBS) | No threshold
|  |  | Selection Based on Consultants Qualification (CQS or CQ) | Contracts valued <$ 200,000 |  | None of the CQS contracts is subject to prior review
|  |  | Single Source Selection of Firms (SSS) | No threshold |  | All contracts are subject to prior review
|  |  | Individual Consultants (IC) | No threshold |  | Contracts valued ≥ $ 100,000. TORs of the all individual contracts are subject to Bank's prior review.
All single source selection of Individual Consultants are subject to Bank's prior review.
|  | - | The selections for financial management, audit, procurement or legal contracts financed by the project, even those are below the prior review threshold, shall be sent to the Bank for prior review.
|  | - | One in five post-review contracts will be reviewed during ex-post review of the Bank.
2. Short list comprising entirely of national consultants: Short list of consultants for services estimated to cost less
than US$300,000 equivalent per contract, may comprise entirely of national consultants in accordance with provisions
of paragraph 2.7 of the Consultant Guidelines.
IV. Any Other Special Procurement Arrangements:
- Logistical and organizational services for training shall be procured under contracts awarded on the basis of National Competitive Bidding and Shopping procedures. Training activities in the form of study tours, or participating in National or international workshops and training programs shall be procured in accordance with the procedures agreed with the Bank.
- Training activities not involving procurement will be initiated after obtaining Bank's no-objection for each individual case.
- Bank’s revisions in the Anti-corruption Guidelines, and cross-debarment of the firms due to May 2010 Procurement and Consultant Guidelines will be applicable to all contracts. The IPCU shall incorporate necessary provisions into the NCB documents in this regard. Latest NCB-Works documents available in the ECA-Procurement web-site shall be used.
V. Procurement Packages with Methods and Time Schedule
- The estimated costs in the attached tables (sheets) include all the taxes (including VAT).
- Domestic preference in accordance with Paragraph 2.55 and Appendix 2 of the Procurement Guidelines will not apply.
- Prequalification of bidders in accordance with Paragraph 2.9 of the Procurement Guidelines will apply only for the Contract No. WBAF-WB1-Yapim-1, Umraniye Pediatric and Maternity Hospital
- Logistic and organizational services required for the International and National Symposium, Seminars, Workshop, and other training programs shall be procured by Shopping procedures if the contract size is less than US$100,000 equivalent.
- In case of very large training programs, exceeding the threshold of US$100,000 equivalent the procurement would be advertised at least 30 days in advance in the national or international press as appropriate, and bidding documents agreed by the Bank will be used. All contracts exceeding the threshold of US$ 500,000 equivalent will be subject to Bank’s prior review.
- Any contract under the Project Incremental Operating Costs shall be procured in accordance with the procedures and thresholds specified in this Procurement Plan.
- For the contracts No: AF-GA5.1-5.5 and No: AF-CA1.2 Bank's no-objection will be obtained for the procurement method for each individual contract before initiating the procurement.
- In accordance with the Bank's general policy on financing from the loan account with reference to the loan closing date,
the Bank will finance eligible expenditures that are payable only for such goods, works and services that are included
in the Project and delivered, performed and completed on or before the closing date of the Loan, and in accordance with
the provisions of respective contract. The Bank's no-objection to the procurement plan is subject to the above financing policy
and IPCU's insuring, prior to signing/amending of such contracts, availability of funds from IPCU's own or other resources as may be
required for goods to be delivered or works to be performed or services to be completed after the Loan closing date of the Project.
The Bank financing of the eligible expenditures from the Loan shall not exceed Euro 109, 800,000 regardless of the planned amount
in this procurement plan.

## WBAF_ISMEP PP_April 30, 2014
Turkey - Istanbul Seismic Mitigation and Emergency Preparedness Project Additional Financing
Procurement Packages with Methods and Time Schedule
As of April 30, 2014 (Revision No.5)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 (Estimated Time Schedule)
| Category / Component | Item No. | Contract Number | Description | Type | Number of items/sub-packages | Estimated Contract Amount in US$ (#a) | Estimated Cost in Euro (#a) | Procurement Method (#c) | Method of Bank review Prior or Post (#b) | Prequalification/ Short Listing | (BD/RFP) | Bidding | Contract Execution | [5 empty] | Amount in Procurement Plan (Original) | Amount in Procurement Plan (Revision-1) | Amount in Procurement Plan (Revision-2) | Variation
[11 empty] | Invitation- Evaluation and Recommendation | (BD/RFP) Preparation | Bid / Proposal Invitation - Opening-Evaluation-Award | Contract Signing Date | Contract Amount (Including VAT) in the contract currency | Contract Amount (Including VAT) Euro equivalent | Contract initiated under the Original Loan - Contract Amount Disbursed from Original Loan as of 31 Dec 2012 in Euro | Amount to be Disbursed from the Additional Financing (Euro) | Contract Completion Date
| G |  |  | Goods
Enhancing Emergency Preparedness (Component A)
A1 |  | 1 |  | Upgrading of Emergency Communication System |  |  |  | 2434235.43 | [11 empty] | 2452200 | 2452200 | 1939800 | -457539
|  |  | AF-GA.1.1 | Communication Equipment for Public Agencies | G | 1 | 950000 | 695400 | NCB | Post Review | N.A | April 2014 | May - June 14 | July 2014 |  |  | _ | _ | Dec 2014
|  |  | AF-GA.1.2 | Microwave Links for DED | G | 1 | 97767.1448 | 71565.55 | NCB | Post Review | N.A | 2012-08-01 | 09.08.2012 02.10.2012 31.12.2012 | 2013-01-02 | 72577.994 | 72577.994 | _ | 71565.55 | 2013-07-26 | 512400 | 512400 | 0 | -431880
|  |  | AF-GA.1.3 Lot 1 | Radio Related Equipment for Hasdal DED (European Side) | G | 2 | 998155.8785 | 755604 | NCB | Post Review | N.A | December 2012 | 16.12.2012 30.01.2013 01.04.2013 | 2013-04-25 | 613831.72 | 613831.72 | _ | 613831.72 | 2014-01-29
|  |  | AF-GA.1.3 Lot 2 | Radio Related Equipment for Hasdal DED (European Side) | [9 empty] | 2013-07-14 | 141771.91 | 141771.91 |  | 141771.91 | 2014-05-28
|  |  | AF-GA.1.4 | PBX and IP Phones for Akfırat DED (Anatolian Side) | G | 1 | 201016.5301 | 147144.1 | NCB | Post Review | N.A | Nov 13 | Dec 13 | 2014-04-09 | 203000 | 147144.1 | _ | 147144.1 | 2014-12-31 | 402600 | 402600 | 402600 | -109800
|  |  | AF-GA.1.5 | Radio Related Equipment for Akfırat DED (Anatolian Side) | G | 1 | 950000 | 695400 | NCB | Post Review | N.A | 2014-04-04 | Apr - May 14 | May-June 14 |  |  | _ |  | 2014-11-01
|  |  | GA1.8 | Procurement of VSAT-HUB | G | 1 | 468600 | 69122.15 | NCB | Post Review | N.A | 2010-07-01 | 2010-07-09 | 2010-10-06 | 468600 | 398916.14 | 329793.99 | 69122.15 | 2013-12-19
[17 empty] | Estimated Total | 2434235.43
A2 |  | 2 |  | Disaster Management Information System |  |  |  | 12168466 | [11 empty] | 9076800 | 9076800 | 8674200 | -1403121
|  |  | AF-GA.2.1 | Back up of Kandilli Earthquake Monitoring System | MOVED TO ORIGINAL LOAN (Ln. 4784 TU Contract No: GA 2.8)
|  |  | AF-GA.2.2 | Akfırat DED (Anatolian Side) IT Related Equipment | G | 1 | 11000000 | 8052000 | ICB | Prior review | N.A | Dec 13 - Jan 14 | 2013-01-17 | 2014-05-01 |  |  | _ |  | Dec 2014 | 6039000 | 6039000 | 6039000 | -2269200
|  |  | AF-GA.2.3 | Akfırat DED (Anatolian Side) Audio Video Related Equipment | G | 1 | 2000000 | 1464000 | ICB | Prior review | N.A | Jan - Feb 14 | 2014-02-12 | 2014-05-02 |  |  | _ |  | Dec 2014 | 2635200 | 2635200 | 2635200 | -988200
|  |  | AF-GA.2.4 | Akfırat DED (Anatolian Side) Display Wall | G | 1 | 1215846.9945 | 890000 | ICB | Prior review | N.A | 2013-07-25 | 2013-10-01 | 2013-12-23 | 890000 | 890000 | _ | 890000 | 2014-06-21
|  |  | GA2.6 | Hasdal DED (European Side) IT Related Equipment | G | 1 | 6179400 | 1115466.15 | ICB | Prior review | N.A | 2012-02-29 | 2012-08-09 | 2012-08-31 | 6179400 | 4980327.91 | 3864861.76 | 1115466.15 | 2013-05-10
|  |  | GA2.7-Lot 1 | Hasdal DED (European Side) Audio Video Related Equipment | G | 1 | 3036708.9481 | 645772.4 | ICB | Prior review | N.A | 2012-07-27 | 2012-11-19 | 2012-12-13 | 2222870.95 | 2222870.95 | 1577098.55 | 645772.4 | 2013-12-26
[17 empty] | Estimated Total | 12167238.55
A3 |  | 3 |  | Support to Develop Operational Capability for Governor's Disaster Management Center (AYM) |  |  |  | 1414813.75 | [11 empty] | 1354200 | 1354200 | 1043100 | -402681
|  |  | AF-GA.3.1 | Procurement of Water Rescue Vehicle | G | 1 | 400000 | 292800 | NCB | Post Review | N.A | May-June 14 | June 14 | July 14 |  |  | _ |  | Dec 14 | 622200 | 622200 | 311100 | -311100
|  |  | AF-GA.3.2.1 | Akfırat DED (Anatolian Side) Furnishing | G | 1 | 95000 | 69540 | S | Post Review | N.A | 2014-05-01 | June 14 | July 14 |  |  | _ |  | Dec 2014 | 732000 | 732000 | 732000 | -366000
|  |  | AF-GA.3.2.2 | Akfırat DED (Anatolian Side) Office Equipments | G | 1 | 95000 | 69540 | S | Post Review | N.A | Aug 14 | Sep 14 | Oct 14 |  |  |  |  | Dec 14
|  |  | GA3.22-Lot 1 | Hasdal DED (European Side) Furnishing | G | 1 | 359467.2131 | 237760.58 | NCB | Post Review | N.A | 2012-05-02 | 2012-06-05 | 2012-09-07 | 627735 | 263130 | 25369.45 | 237760.58 | 2013-09-30
|  |  | GA3.22-Lot 2 | Hasdal DED (European Side) Furnishing | G | 1 | 82801.9126 | 54486.65 | NCB | Post Review | N.A | 2012-05-02 | 2012-06-05 | 2012-09-07 | 150260 | 60611 | 6124.25 | 54486.65 | 2013-09-30
|  |  | AF-GA3.3.1 | Procurement of Rescue Vehicles | G | 2 | 800000 | 585600 | NCB | Post Review | N.A. | 2014-05-01 | June 14 | July -Aug 2014 |  |  | _ |  | Dec 2014
|  |  | AF-GA3.3.2 | [10 empty] | July -Aug 2014 |  |  | _ |  | Dec 2014
|  |  | AF-GA3.4 | Procurement of Kitchen Equipments | G | 1 | 96903.5 | 70933.362 | S | Post Review | N.A. | July 13 | Aug 13 | 2013-09-17 | 96904 | 72543.42 | _ | 70336.52 | 2013-11-01
|  |  | AF-GA3.5 | Procurement of Office Equipments for Hasdal DMC | CANCELLED
|  |  | AF-GA3.5 / Rebidding | Procurement of Office Equipments for Hasdal DMC | G | 1 | 90000 | 34750 | S | Post Review | N.A. | Nov 13 | Nov 13 | 2014-02-07 | 104250 | 34579.41 | _ | 34750 | 2014-06-07
[17 empty] | Estimated Total | 1414813.75
A4 |  | 4 |  | Upgrading Emergency Response Capacity |  |  |  | 1200168 | [11 empty] | 7667700 | 7667700 | 7667700 | -3843000
|  |  | AF-GA.4.1 | Water Purification Systems | G | 1 | 43805.9973 | 32065.99 | S | Post Review | N.A | 2013-09-13 | Oct 13 | 2013-10-07 | 89990 | 33145.49 | _ | 32065.99 | 2014-02-04 | 1171200 | 1171200 | 1171200 | -805200
|  |  | AF-GA.4.2 | Mobile Surgery Hospital | CANCELLED
|  | Bid Group 02 | AF-GA.4.3.1 | NBC Protection Equipment for first responders teams | G | 1 | 605000 | 442860 | NCB | Post Review | N.A | Apr 14 | 2014-05-01 | July 2014 |  |  | _ |  | Nov 2014
|  |  | AF-GA.4.3.2 | Equipments for UMKE | G | 1 | 95000 | 55333.33 | S | Post Review | N.A | Jan 14 | Jan 14 | 2014-02-05 | 166000 | 54738.51 | _ | 55333.33 | 2014-04-16
|  |  | AF-GA.4.4 | Procurement of Vital Data Transfer and Monitoring System for Emergency Health Services | CANCELLED
|  |  | AF-GA.4.5.1 | Disaster Tents and Camp Beds | G | 1 | 661284 | 484059.888 | NCB | Post Review | N.A | 2014-05-01 | June 14 | July 14 |  |  | _ |  | Nov 14
|  |  | AF-GA.4.5.2 | Strecthers for UMKE Team | G | 1 | 95000 | 72779.41 | S | Post Review | N.A | Dec 13 | Dec 13- Jan 14 | 2014-01-06 | 98980 | 72747.32 | _ | 72779.41 | 2014-02-27
|  |  | AF-GA.4.6 | Containers | G |  | 115733.1557 | 84716.67 | NCB | Post Review | N.A | Oct 13 | Nov 2013 | 2014-02-07 | 254150 | 84300.78 | _ | 84716.67 | 2014-06-07
[17 empty] | Estimated Total | 1171815.288
A5 |  | 5 |  | Materials and Equipment for Public Awareness Campaign |  |  |  | 379861 | [11 empty] | 1244400 | 1244400 | 1244400 | -585600
|  |  | AF-GA5.1-5.5 | Procurement of Training Materials and public awareness campaign materials (will be procured as required) | G | 5 | 318935.7923 | 233461 | NCB/S | Post Review | NA | Nov 13- Aug 14 | Nov 13- Aug 14 | Nov 13- Aug 14 |  |  | _ |  | 2014-09-01 | 951600 | 951600 | 951600 | -585600
|  |  | AF-GA5.1 | Procurement of Publicity Film of ISMEP | G | 1 | 71584.6995 | 52400 | S | Post Review | NA | October 2012 | 19.10.2012 01.11.2012 20.11.2012 | 2012-11-30 | 52400 | 52400 |  | 52400 | 2013-05-24
|  |  | AF-GA5.2 | Procurement of Start Up Workshop of Safe Life Volunteers Campaign | G | 1 | 49153.8798 | 35980.64 | S | Post Review | NA | 2013-05-01 | 27.05.2013 07.06.2013 24.06.2013 | 2013-07-11 | 97763 | 38534.88 |  | 35980.64 | 2013-07-21
|  |  | AF-GA5.6 | Procurement of Training Materials and public awareness campaign materials for Disaster Related Institutions (AFAD, MoPWS, etc) | G | 5 | 200000 | 146400 | S | Post Review | NA | Nov 13- Aug 14 | Nov 13- Aug 14 | Nov 13- Aug 14 |  |  | _ |  | 2014-09-01
[17 empty] | Estimated Total | 379861
A5 |  | 6 |  | Materials and Equipment for Neigbourhood Volunteers |  |  |  | 80669.95 | [11 empty] | 1628700 | 1628700 | 1156442 | -969900
|  |  | AF-GA.6.1 | Search and Rescue Equipment for Local Disaster Volunteers | G | 1 | 95000 | 69540 | S | Post Review | N.A | Apr 14 | 2014-05-01 | July 2014 |  |  | _ |  | Dec 2014 | 677100 | 677100 | 863642 | -311100
|  |  | AF-GA.6.2 | Radio Set and Related Equipment for the Local Disaster Volunteers | G | 1 | 400000 | 292800 | NCB | Post review | N.A | 2013-12-01 | Jan 14 - Feb 14 | 2014-03-01 |  |  | _ |  | 2014-10-01
[17 empty] | Estimated Total | 69540
|  |  |  | Goods Subtotal |  |  | 31867165.6462 | 17678214.13 | [9 empty] | 4278139.67 |  | 23424000 | 23424000 | 21725642 | -7661840
| W |  |  | WORKS
|  |  | WA | Enhancing Emergency Preparedness (Component A) |  |  |  | 2310690.31
A1 |  | 1 |  | Minor Works for Installation of Telecommunication and Information Management System for İstanbul DED | W | 1 |  | 272070.31
|  |  | AF-WA1.1 | Procurement of Additional Minor Works for Hasdal DED | W | 1 | 90000 | 68251.49 | S | Post Review | N.A | Aug 13 | 2013-10-01 | 2013-11-08 | 193014.87 | 70841.54 | _ | 68251.49 | 2014-04-07
|  |  | AF-WA1.2 | Procurement of Various Signboard Construction Works | W | 1 | 90000 | 72058.82 | S | Post Review | N.A | Aug 13 | 2013-10-01 | 2013-08-12 | 98000 | 73700.83 | _ | 72058.82 | 2014-05-09
|  |  | AF-WA1.3-1.4 | Procurement of Addiditonal Minor Works for DMC | W | 2 | 180000 | 131760 | S | Post Review | N.A | 2014-05-01 | June 14 | July 14 |  |  |  |  | Oct 14
[17 empty] | Estimated Total | 272070.31
|  | 2 |  | Additional Works for Disaster Management Buildings and Annexes | W | 1 |  | 2038620 | NCB/S | Post Review | N.A
|  |  | AF-WA2.1 | Construction of Training and Exercise Field for SAR | W | 1 | 2500000 | 1830000 | NCB | Post Review | N.A | 2014-03-01 | 2014-05-01 | June 14 |  |  | _ |  | Dec 14
|  |  | AF-WA2.1.1 | Procurement of Additional Minor Construction Works for Hasdal DMC | W | 1 | 95000 | 69540 | S | Post Review | N.A | 2014-03-01 | 2014-05-01 | 2014-05-01 |  |  |  |  | Nov 14
|  |  | AF-WA2.1.2 | Procurement of Additional Minor Mechanical Works for Akfırat DMC | W | 1 | 95000 | 69540 | S | Post Review | N.A | Aug 14 | Aug-Sep 14 | Sep 14 |  |  |  |  | Dec 14
|  |  | AF-WA2.1.3 | Procurement of Additional Minor Electrical Works for Akfırat DMC | W | 1 | 95000 | 69540 | S | Post Review | N.A | Aug 14 | Aug-Sep 14 | Sep 14 |  |  |  |  | Dec 14
[17 empty] | Estimated Total | 2038620
|  |  | WB | Seismic Risk Mitigation for Public Facilities (Component B)
B1 |  | 1 |  | Reconstruction of Hospitals |  |  |  | 39991531.44 | [11 empty] | 47580000 | 47580000 | 47580000 | 1384418
|  |  | AF-WB1-Yapım-01 | Ümraniye Pediatric and Maternity Hospital | W | 1 | 66891281.9399 | 39991530.44 | ICB | Prior review | 17.08.2011 27.10.2011 18.04.2012 | 2012-05-01 | 16.05.2012 16.08.2012 18.10.2012 | 2012-11-29 | 113342835.66 | 48964418.38 | _ | 39991530.44 | 31.04.2016 (inc. 12 Month DLP) | 47580000 | 47580000 | 47580000 | 1384418
[17 empty] | Estimated Total | 39991530.44
B1 |  | 2 |  | Strengthening of Hospitals and Clinics |  |  |  | 14776788.12 | [11 empty] | 20496000 | 20496000 | 20496000 | 2539995
|  |  | AF-WB2-Gucl-Onar-1 | Üsküdar Validebağ Hospital | W | 1 | 4258238.9891 | 3117030.94 | NCB | Post review | NA | November 12 | 30.11.2012 31.01.2013 01.03.2013 | 2013-03-14 | 7680000 | 3268363.26 | _ | 3117030.94 | 2014-06-21
|  |  | AF-WB2-Gucl-Onar-2 | Zeynep Kamil Hospital | W | 1 | 13620386 | 8271186.44 | NCB | Post review | NA | Sep 13 | Nov 13 | 2014-01-21 | 24400000 | 8030278.1 | _ | 8271186.44 | 2014-12-24
|  |  | AF-WB2-Gucl-Onar-3 | Healthcare Centers (8 Units) | W | 3 | 1729472.3497 | 1243107.97 | NCB | Post review | NA | 2011-12-22 | 31.12.2011 03.02.2012 23.02.2012 | 2012-03-08 | 2972000 | 1265973.76 | _ | 1243107.97 | 2012-08-30
|  |  | AF-WB2-Gucl-Onar-4 | Healthcare Centers (6 Units) |  |  | 1380319.112 | 984212.62 | [5 empty] | 2012-03-08 | 2372000 | 1010393.59 | _ | 984212.62 | 2012-08-30
|  |  | AF-WB2-Gucl-Onar-5 | Healthcare Centers (6 Units) |  |  | 1240657.8279 | 908161.53 | [5 empty] | 2012-03-08 | 2132000 | 908161.53 | _ | 908161.53 | 2012-08-30
|  |  | AF-WB2-Gucl-Onar-6 | Healthcare Centers (6 units) | CANCELLED
|  |  | AF-WB2-Gucl-Onar-7 | Koşuyolu Training and Simulation Center | CANCELLED | [16 empty] | 5919600 | 2000000
|  |  | WB2_Gucl_Onar_11 | Retrofitting Works of Polyclinics (5) | W | 1 | 1016898.9071 | 253088.62 | NCB | Post Review | NA | February 12 | March 12 | 2012-06-22 | 1905000 | 744370 | 491281.11 | 253088.62 | 2013-01-17
[17 empty] | Estimated Total | 14776788.12
B1 |  | 3 |  | Strengthening of Public Schools |  |  |  | 13189248.34 | [13 empty] | 5358358 | 1355833
|  | Bid Group 01 | AF-WB3-Gucl-Onar-1 | Retrofitting and Repair Works of Educational Facilities(6) | W | 2 | 7320161 | 5035950.44 | NCB | Post review | N.A | 2013-04-13 | 2013-05-22 | 2013-06-24 | 6550000 | 2571451.01 |  | 2471563.76 | 2013-12-17
|  |  | AF-WB3-Gucl-Onar-2 | Retrofitting and Repair Works of Educational Facilities(7) | [10 empty] | 6845000 | 2687264.45 |  | 2564386.68 | 2013-12-27
|  |  | WB3_Gucl_Onar_79 | Retrofitting and Repair Works of Educational Facilities(5) | W | 1 | 3508265.0273 | 549009.4 | NCB | Post Review | NA | April 12 | 2012-05-01 | 2012-06-18 | 5993000 | 2568050 | 2019040.34 | 549009.4 | 2013-01-21
|  | Bid Group 01 | AF-WB3-Gucl-Onar-3 | Retrofitting and Repair Works of Educational Facilities(4) | W | 3 | 9562841.5301 | 7000000 | NCB | Post review | N.A | 2014-05-01 | May - June 14 | June - July 14 |  |  |  | 7604288.5 | Dec 14
|  |  | AF-WB3-Gucl-Onar-4 | Retrofitting and Repair Works of Educational Facilities(5)
|  |  | AF-WB3-Gucl-Onar-5 | Retrofitting and Repair Works of Educational Facilities(4)
[17 empty] | Estimated Total | 13189248.34
B1 |  | 5 |  | Reconstruction / Strengthening of Essential Administrative Buildings |  |  |  | 7943096 | [13 empty] | 2928000 | 2602196
|  |  | AF-WB5-Gucl-Onar-1 | Administrative Buildings (4) | W | 1 | 2226153.1148 | 1629544.08 | NCB | Post review | NA | 2011-11-22 | 01.12.2011 09.01.2012 01.02.2012 | 2012-03-02 | 3241000 | 1459646.91 | _ | 1629544.08 | 2012-12-15
|  |  | AF-WB5-Gucl-Onar-2 | Retrofitting of Administrative Buildings | W | 1 | 5433215.041 | 3977113.41 | NCB | Post Review | NA | Jan - Feb 14 | 2014-03-19 | 2014-05-01 |  |  |  |  | Dec 14
|  |  | WB5_Gucl_Onar_07 | Retrofitting of Administrative Buildings | W | 1 | 7522737.7049 | 2336438.77 | NCB | Post Review | NA | August 11 | September 11 | 2011-10-17 | 11790000 | 5506644 | 3170205.32 | 2336438.77 | 2014-02-19
[11 empty] | -0.26 | 71858.74 |  |  |  |  | Estimated Total | 7943096.26
B1 |  | 6 |  | Reconstruction / Strengthening of Dormitories and Social Service Buildings |  |  |  | 2210432 | [13 empty] | 2928000 | 2602196
|  |  | AF-WB6-Gucl-Onar-01 | Contract Package for Retrofitting and Repair Works of Dormitories and Social Service Buildings | W | 1 | 3019716.0109 | 2210432.12 | NCB | Post review | NA | April 12 | 2012-05-01 | 2013-09-30 | 6505765 | 2361267.78 | _ | 2210432.12 | 2014-03-26
[11 empty] | -0.12 | 199110.47 |  |  |  |  | Estimated Total | 2210432.12
|  |  |  | Works-Sub Total |  |  |  | 80421786.21 | [9 empty] | 66670003.68
|  |  |  | Sub total Works+ Goods and Technical Services |  |  |  | 98100000.34 | [9 empty] | 70948143.35
| CS |  |  | CONSULTANT SERVICES
| CA |  |  | Enhancing Emergency Preparedness (Component A)
A5 |  | 1 |  | Design and Implementation of Public Awareness Campaign |  |  |  | 845327 | [11 empty] | 2635200 | 2635200 | 1285200 | -2448000
|  |  | AF-CA1.1 | Consultancy Services for Safe Life Training for High Schools and Universities | CS | 1 | 944767.7596 | 691570 | SS | Prior review | Feb 14 - Mar 14 | Mar 14 | Mar - Apr 14 | Apr - May 14 |  |  | _ |  | June 15
|  |  | AF-CA1.2 | Consultancy Services for the Training of Target and Neighbourhood Groups & Consultancy services for the Evaluation of the overall ISMEP Financing | CS | 1 | 200000 | 150299.38 | CQS (#b) | Prior Review | 2012-12-14 | 2013-03-08 | 2013-06-06 | 2013-07-01 | 200000 | 153757.0231 | _ | 150299.38 | 2013-10-21 | 1537200 | 1537200 | 187200 | -1350000
[17 empty] | Estimated Total | 841869.38
A3 |  | 2 |  | Support to Develop Operational Capability for Governor Disaster Management Center |  |  |  | 1543367 | [11 empty] | 1427400 | 1427400 | 1427400 | -219600
|  |  | AF-CA2.1 | Technical Support to Operational Capability for Governor's Disaster Management Center (AYM) | CS | 5 | 250000 | 183000 | IND | Post Review | 2014-05-01 | 2014-05-01 | 2014-06-01 | July 14 |  |  |  |  | Dec 14
|  |  | AF-CA2.2 | Consultancy for GIS-DMIS-IT Integration | CS | 6 | 515000 | 376980 | CQ/IND | Post Review | Apr 14 | Apr 14 | 2014-05-01 | June 14 |  |  |  |  | Dec 14
|  |  | AF-CA2.3 | Preperation of Strategic Plans for Disaster Management | CANCELLED
|  |  | AF-CA2.4 | Pilot Study for Disaster and Emergency Plan of Public Institutions (schools, etc.) | CS | 1 | 200000 | 134976.97 | CQS | Post Review | 2013-07-08 | Oct 2013 | Nov 13 - Mar 14 | 2014-03-14 | 419090 | 134976.97 | _ | 134976.97 | 2014-12-30
|  |  | AF-CA2.5 | Consultancy Services for the Model of the Accreditation of the Volunteers | CANCELLED
|  |  | AF-CA2.6 | Consultant for Design of Disaster Exercises and M&E of results | CS | 5 | 300000 | 219600 | IND | Post Review | Apr 14 | Apr 14 | 2014-05-01 | June 14 |  |  |  |  | Dec 14
[17 empty] | Estimated Total | 914556.97
| CB |  |  | Seismic Risk Mitigation for Public Facilities (Component B)
B1 |  | 1 |  | Preperation of Design for Strengthening/Reconstruction of Key Facilities and Supervision of Retrofitting/Reconstruction Works |  |  |  | 6092476 | [11 empty] | 4758000 | 4758000 | 6108000 | 1481230
|  |  | CB1.4C | Consultancy Services for Design and Reconstruction Supervision of Koşuyolu Pediatric Hospital (only the Supervision Phase is financed under the original loan within this PP) | CS | 1 | 3569788.2514 | 1305015 | QCBS | Prior review | 1- 16.04.2008 2- 07.05.2008 3- 22.06.2008 | 1- 22.06.2008 | 1- 23.06.2008 2- 07.08.2008 3- 03.12.2008 | 2009-02-10 | 2395900 | 2613085 | 1648070 | 1135015 | 31.04.2016 (inc. 12 Month DLP) | 1281000 | 1281000 | 1281000 | -366000
|  |  | AF-CB1.1 | Consultancy Services for Retrofitting/Reconstruction of Public Buildings Including Hospital, Schools and Administrative Buildings in İstanbul | CS | 1 | 4464041.8443 | 3267678.63 | QCBS | Prior review | 1- 28.07.2012 2- 03.09.2012 3- 28.11.2012 | 1- 28.11.2012 | 1- 04.12.2012 2- 14.01.2013 3- 15.03.2013 | 2013-03-26 | 8150000 | 3267678.63 | _ | 3046659.36 | 2014-09-17 | 2013000 | 2013000 | 3363000 | 1350000
|  |  | AF-CB1.3 | Preperation of Retrofitting Design of Public Buildings | CS | 1 | 2010000 | 1516981 | QCBS | Prior review | 1-26.04.2012 2-01.06.2012 3- 13.03.2013 | 2013-03-13 | 1- 19.04.2013 2- 31.05.2013 3- July 2013 | Aug 2013 | 2010000 | 1546153.85 | _ | 1534551.17 | 2014-09-13
|  |  | CB3.1E | Consultancy Services for Quality Control of Works Projects with Base Isolation | THE CONTRACT AMOUNT HAS ALREADY BEEN PAID FROM THE BUDGET OF THR ORIGINAL LOAN NUMBERED TU-4784
|  |  | CB4.2 | Consultancy Services for Earthquake Performance Assessment and Preparation of Structural Seismic Retrofit Proposals for Cultural Heritage Buildings under the Responsibility of the Ministry of Culture and Tourism (CB 4.2) | CS | 1 | 2446605.1913 | 236310 | QCBS | Prior Review | August 06 December 06 March 07 | April 07 | 09.04.2007 29.05.2007 14.09.2007 | 2008-01-23 | 1575400 | 1790915 | 1554604.72 | 236310 | 2014-12-30
[17 empty] | Estimated Total | 5952535.53
B2 | CB |  |  | Carrying out of National Disaster Studies and Assessments |  |  |  | 94286
|  |  | AF-CB2.1 | Support to National Disaster Studies and Assessments | CS | 1 | 128806.0109 | 94286 | CQ/IND | Post Review | 2014-05-01 | June 14 | 2014-07-01 | July 14 |  |  |  |  | Dec 14
[17 empty] | Estimated Total | 94286
| CD |  |  | Technical Assistance to IPCU (Component D) |  |  |  | 324948 | [11 empty] | 0 | 0 | 0 | 133404
|  |  | AF-CD1 | Kit Miyomoto - Quality Control of Retrofitting Works | CS | 1 | 46950 | 34367.4 | IND/SSS | Prior Review | NA | NA | 2012-11-27 | 2012-12-06 | 46950 | 36083.9992 | _ | 36083.9992 | 2013-06-04
|  |  | AF-CD2 | Işıl Salihoğlu - Environmental Management and inspection | CS | 1 | 30641.3934 | 22429.5 | IND/SSS | Prior Review | NA | NA | 2012-12-10 | 2013-01-09 | 55,629.62 TL | 22429.5 | _ | 19747.93 | 2014-01-09
|  |  | AF-CD3 | Individual Consultant for Legal Advisor | CS | 1 | 91544.6448 | 67010.68 | IND/SSS | Prior Review | NA | NA | 2013-01-01 | 2013-01-25 | 140,035.45 TL | 67010.68 | _ | 64664.55 | 2014-01-25
|  |  | AF-CD4 | Individual Consultant for Inception Report for Economic Assessment Study | CS | 1 | 50000 | 36600 | IND | Post Review | NA | NA | Nov 13-May 14 | 2014-05-01 |  |  |  |  | Oct 14
|  |  | AF-CD5 | Individual Consultant for Preparing Strategic Plan for Awareness Raising Activities and Monitoring during Implementation | CS | 1 | 95000 | 69540 | IND/SSS | Prior Review | NA | NA | 2014-03-01 | 2014-03-25 |  |  |  |  | Dec 14
|  |  | AF-CD6 | Işıl Salihoğlu - Environmental Management and inspection | CS | 1 | 40983.6066 | 30000 | IND/SSS | Prior Review | NA | NA | December 13 | 2014-01-22 | 56746.21 | 19517.25 | - | 19900.55 | Dec 14
|  |  | AF-CD7 | Individual Consultant for Legal Advisor | CS | 1 | 88797.8142 | 65000 | IND/SSS | Prior Review | NA | NA | December 14 | 2014-01-01 | 150398.07 | 49130.43 | - | 59156.57 | Dec 14
|  |  | AF-CD8 | Individual Consultant for Independent Review of Retrofitting Designs | CS | 1 | 6830.6011 | 5000 | IND/SSS | Prior Review | NA | NA | April 14 - May 14 | 2014-05-01 |  |  |  |  | Nov 14
[17 empty] | Estimated Total | 310693.5992
|  |  |  | Consultancy-Sub Total |  |  |  | 8900404 | [9 empty] | 6302388.5092 |  | 8967000 | 8967000 | 8967000 | -1332319
| T |  |  | TRAINING
A3 | TA | 1 |  | Enhancing the knowledge and Capacity of IDED and other institutions for Emergency Preparedness |  |  |  | 456308.55 | [11 empty] | 439200 | 439200 | 439200 | -1464000
|  |  | AF-TR1.1 | Training and workshop for Istanbul Disaster and Emergency Directorate (IDED) Staff and other relevant entities | TR | 4 | 373224.0437 | 273200 | S | Post Review | NA | Nov 13- Aug 14 | Nov 13- Aug 14 | Nov 13- Aug 14 |  |  |  | _ | 2014-09-01 | 2014-09-01
|  |  | AF-TR-1.1.1 | Introduction meeting for "Plans for Preventing, Interventing,Improving Desaster Emergency Situation" for for Related Institutions | TR | 1 | 92891.1612 | 67996.33 | S | Post Review | NA | NA | 06.05.2013 13.05.2013 14.05.2013 | 2013-05-17 | 169397 | 67996.33 | - | 65980.33 | 2013-05-25
|  |  | AF-TR-1.1.2 | Istanbul Disaster and Emergency Directorate (IDED) Staff - Personel Development Trainings | TR | Multiple | 200000 | 146400 | S | Post Review | NA | NA | 2014-03-01 | April 14 |  |  |  |  | Nov 14
[17 empty] | Estimated Total | 212380.33
|  |  | AF-TR1.2 | Workshop for Istanbul Disaster and Emergency Directorate (IDED) and other Public Facilities | TR | 4 | 250148.2923 | 183108.55 | S | Post Review | NA | Nov 13- Aug 14 | Nov 13- Aug 14 | Nov 13- Aug 14 |  |  |  | _ | 2014-09-01 | 2014-09-01 | 366000 | 366000 | -146400
|  |  | AF-TR1.2.1 | Technical Visit for Building Permit procedures, Voluntary mechanisms, Emergency preparedness and Seismic Mitigation in İtaly | TR | 1 | 84045.3546 | 61521.1996 | S | Post Review | NA | NA | 08.03.2013 15.03.2013 18.03.2013 | 2013-03-19 | 108812 | 61521.1996 | - | 39391.81 | 2013-04-03
|  |  | AF-TR-1.2.2 | Hotel, and Catering Services fpr Introduction meeting for "Plans for Preventing, Interventing,Improving Desaster Emergency Situation" for for Related Institutions | TR | 1 | 97037.2 | 81104.94 | S | Post Review | NA | NA | 08.05.2013 15.05.2013 15.05.2013 | 2013-05-17 | 176450 | 81104.94 | - | 70516.74 | 2013-05-25
|  |  | AF-TR1.2.3 | Catering Services for Conference for "Cross Border Risk Analysis and Management" | G | 1 | 100000 | 73200 | S | Post Review | NA | 2014-05-01 | [6 empty] | June 18, 2014
[17 empty] | Estimated Total | 183108.55
B1 | TB | 2 |  | Seismic Risk Mitigation for Public Facilities |  |  |  | 153287
|  |  | AF-TR2 | Training and Workshop for Public Entities Staff or Seismic Risk Mitigation | TR | 5 | 209408.4699 | 153287 | S | Post Review | NA | Nov 13- Aug 14 | Nov 13- Aug 14 | Nov 13- Aug 14 |  |  |  | _ | 2014-09-01 | 2014-09-01
|  |  | CB6.1 | A Protection Regulation for Turkey on the field of Architectural Conservation Meetings | CS | 1 | 105064.1257 | 36385.43 | S | Post Review | 2012-05-01 | NA | 2012-05-25 | 2012-05-28 | 178000 | 76906.94 | 40521.51 | 36385.43 | 2013-03-29
|  |  | AF-TR2.1 | Training and Workshop for Public Entities Staff or Seismic Risk Mitigation in USA | TR | 1 | 22650.2732 | 16580 | S | Post Review | NA | NA | NA | 2013-03-22 | 38837.58 | 16578.83 | - | 16578.83 | 2013-03-22
[17 empty] | Estimated Total | 52964.26
|  |  |  | Training-Sub Total |  |  |  | 609595.55 | [9 empty] | 228853.14 |  | 549000 | 549000 | 549000 | -146400
| Sub total Consultancy + Training | [6 empty] | 9509999.55 | [9 empty] | 6531241.6492
D | D | 10 |  | Project Management
|  | 1 | AF-IND-01….-10 | IPCU Incremental Operating Costs including IPCU staff salaries (excluding government employees) and staff per diems and lodging as well as travel costs for field trips related to the implementation of the project, supplies, utilities, sanitary cleaning, communication and security cost including internet, transport costs for training of IPCU staff, seminars, training and workshops, office equipment, hardware and software, furniture and M&O including fuel, service and car insurance for vehicles and procurement/leasing/renting of vehicles. | OC | Multiple | 2991803.2787 | 2190000 | NA | Post review | NA | NA | 2011-1014 | 2011-1014 | 1005263.77 | 2190000 | _ | 2190000 | 2014
|  |  |  | Project Management Costs Subtotal |  |  | 2991803.2787 | 2190000
|  |  |  | GRAND TOTAL |  |  |  | 109799999.89 | [8 empty] | Signed Contract Amount: | 79669384.9992
| Notes | (#a): The Total Costs are inclusive of all local taxes (Including VAT 100% Financing).
(#b): All ICB, DC and SSS contracts are subject to the Bank's prior review. All QCBS, Fixed Cost and LCS contracts above US$350,000 equivalent are subject to the Bank's prior review. All IND contracts above US$100,000 equivalent are subject to the Bank's prior review.
(#c): NCB-Works and Technical Sevices threshold is < US$15 Million equivalent; NCB-Goods threshold is < US$1 Million equivalent; Shopping threshold is <US$100,000 equivalent; CQS threshold is <US$200,000 equivalent.
| Legend: |  |  |  |  | Abbreviations and Acronyms:
|  |  | Procurement Planned |  |  | W: Works |  |  | ICB: International Competitive Bidding |  |  | QCBS :Quality and Cost Based Selection
|  |  | Procurement Initiated |  |  | G: Goods |  |  | NCB: National Competitive Bidding |  |  | CQS: Selection Based on Consultants Qualification
|  |  | Contract Under Execution |  |  | CS: Consultants Services |  |  | S:Shopping |  |  | LCS: Least Cost Selection
|  |  | Contract Completed |  |  | TR: Training |  |  | DC: Direct Contracting |  |  | FBS: Fixed Budget Selection
|  |  | Contract Cancelled |  |  | TS: Technical Services (non-consulting services) | [5 empty] | IND: Individual Consultant Selection |  |  | 0.11
|  |  | Transferred Items from the Original Loan 4784-TU |  |  | OC:Incremental Operating Costs |  |  | NA: Not Applicable |  |  | SSS: Single Source Selection
Revised or Newly Added Items
Note on H21: lgerdan: 11.000.000 USD OLARAK REVİZE EDİLECEK!!!
Note on H80: fazili: yunus beye yaklaşık maliyet sorulacak
Note on P125: nkarakas: 100.000 usd "Technical Assistance to IPCU (CD)'ye aktarıldı.